## Guide
Guide - This page serves as a step-by-step procedure for processing monthly progress reporting submittals
| Doc Type | Purpose | Due |  | Steps
| Invoice Cover | Excel template to capture key figures for transfer into reporting database. | Due with invoice (beginning first Monday of each month until the 15th) |  | Due with invoice (due beginning first Monday of each month until the 15th)
Open Invoice-Cover worksheet
Fill in the white cells $ Billed Amount (Current), % Work Completed to date
Upload into SharePoint by using button on top right of Invoice cover worksheet (opens Sites Sharepoint - Project Controls -> A/P invoices)
Find Pre-existing record for this submittal. Filter Columns by:
Vendor - Pick your Company
Document Type - INV Cover
Work Period - Current Work/Billing period
Locate and Select Record for editing
Load file as an Attachment (use edit window on right)
Note: At mid-month, you will receive an updated version of this Invoice Cover template for next period's invoice
| Invoice | Submit Vendor/Consultant Periodic Billing | Beginning first Monday of each month until the 15th. |  | Prepare Monthly Invoice Document
Combine multiple files into one pdf file
Navigate into Sites Sharepoint - Project Controls -> A/P invoices
Find Pre-existing record for this submittal. Filter Columns by:
Vendor - Pick your Company
Document Type - INV Consultant
Work Period - Current Work Period
Locate and Select Record for editing
Load file as an Attachment (use edit window on right)
| Monthly Progress Report | Key device to measuring progress and backup documentation for invoice authorization | Consultants are to prepare a Monthly Progress Report Template (MPR) for a work period and submit it to Sharepoint by the first Monday of each month. |  | Select a) Deliverables Progress worksheet and enter… (Note: if your list is inaccurate, contact Project Controls)
% Work Complete figure per Deliverable (see table below sheet for reference on determining ratios)
A Proposed Completion Date only if it differs from current completion date (current date will be updated monthly)
A concise Justification for an Extension if you are proposing a new Completion date
A concise description of progress (Progress made during Work Period)
If there is an issue affecting timely completion of a deliverable, mark it with a "1" in column L and describe matters on General Issues page
Select b) Task Work Progress Worksheet and…
Enter a % Work Complete figure per Task
Describe progress for the work period per Task (Key Work Highlights for Current Work Period)
Describe upcoming key items per task during next work period (Key Work to be Performed Next Period)
Note: On the initial round only
Consultant will fill in the deliverables table assigning each deliverable to the proper task
Project Controls will fill in Deliverable ID's, lock down the list and return updated template.
Consultant will request changes to the deliverables list through a separate process.
Select c) General Issues worksheet and…
Enter into Issues / Challenges per row any issues / challenges / risks / opportunities you foresee affecting ability to deliver your project
Enter Approach to Resolving Mitigating Issues per each row that issues are identified
For Potential Impacts (budget, schedule, etc…), Enter a "1" into cells to serve as indicators
For Completed column, Enter a "1" into cells to serve as indicator the issue has been resolved or is no longer in play
Update a new template provided to you monthly, previous entries will be carried forward
Navigate into Sites Sharepoint - Project Controls -> A/P invoices
Find Pre-existing record for this submittal. Filter Columns by:
Vendor - Pick your Company
Document Type - MPR Monthy Progress
Work Period - Current Work Period
Locate and Select Record for editing
Load file as an Attachment (use edit window on right)
| Monthly Project Analysis | Method for identifying key items in project performance and initiating | Project controls will prepare a Progress Analysis (as needed) for a work period and submit it to Sharepoint. |  | A Monthly Progress Report Analysis is prepared as needed.
For users to locate, Navigate into Sites Sharepoint - Project Controls -> A/P invoices
Find Pre-existing record for this submittal. Filter Columns by:
Vendor - Pick your Company
Document Type - Monthy Progress Analysis
Work Period - Current Work Period
or set alerts to be notified of incoming Analysis files
Locate and Select Record
Respond by entering comments and attaching files
Guide on assigning % Completion values
| Deliverable Type | Phase |  | % Work Complete
| Meeting / Workshop | Scheduled |  | 10%
|  | Agenda & Advance Materials Sent |  | 30%
|  | Meeting Held |  | 60%
|  | Final Minutes Issued |  | 100%
| Memo/Tech Memo/Report (1) | Outline Complete |  | 10%
|  | Investigations, Testing, Document |  | 10% -> 80%
Text/Tables/Graphics Underway
|  | 1st Draft Ready for Internal Review |  | 80%
|  | Final Draft Ready for Client Review |  | 90%
|  | Document Finalized |  | 100%

## a) Deliverables
Monthly Progress Template BRI 2019-11 - 12-2-2019 Dec 03, 2019
|  | BRI Deliverables Progress for 2019-11 Work Period | [7 empty] | BRI Deliverables Progress for 2019-11 Work Period
| Phase | Task ID | Your Task # | Deliverable ID | Deliverable Name | Current Completion Date | % Complete | Proposed Completion Date | Justification for Extension | Progress made during Work Period | Issue
1 | 2 | G03 | G3.1 | SYS01 | Line List | 2019-12-31 | 50% |  |  | This is an ongoing Task - Data for this Task is located in the R/W GIS Tool; maintenance of Data, and inclusion of new information is ongoing
2 | 2 | G04 | G4.1 | PLN01 | Property Management Plan (1) | 2019-12-31 |  |  |  | This Task is As-Needed - No Current Need; No Current Billing
3 | 2 | G04 | G4.1 | PLN02 | Acquired Property Disposition Plan (1) | 2019-12-31 |  |  |  | This Task is As-Needed - No Current Need; No Current Billing
4 | 2
5 | 2
6 | 2
7 | 2
8 | 2
9 | 2
10 | 2
11 | 2
12 | 2
13 | 2
14 | 2
15 | 2
16 | 2
17 | 2
18 | 2
19 | 2
20 | 2
21 | 2
22 | 2
23 | 2
24 | 2
25 | 2
26 | 2
27 | 2
28 | 2
29 | 2
30 | 2
31 | 2
32 | 2
33 | 2
34 | 2
35 | 2 | [10 empty] | GIS | 36616
36 | 2
37 | 2
38 | 2
39 | 2
40 | 2
41 | 2
42 | 2
43 | 2
44 | 2
[12 empty] | Expenses | 19000
[12 empty] | Local/Landowner Outreach | 62940
[12 empty] | Statewide Outreach | 43920
[12 empty] | NGO Outreach | 37620
[12 empty] | Strategic Communications | 31920
[12 empty] | Message Development/Training | 18620
[12 empty] | Informational Materials Distribution | 95430
[12 empty] | Website Modifications and Management | 37650
[12 empty] | Video & Photography | 27645
[12 empty] | Authority/Reservoir Committee Public Affairs Support | 39920
[12 empty] | Media Relations | 24310
[12 empty] | Social Media | 22725
[12 empty] | Project Management | 97165
[12 empty] | Expenses | 85500
[12 empty] | Permitting and Resource Agency Technical Support | 295582.33
[12 empty] | Environmental Document Support | 363683.96
[12 empty] | Total Operations Technical Support | 358822.22
[12 empty] | Project Management | 118345.66
[12 empty] | Subs and ODCS | 135166
[12 empty] | Fugro PMP | 67220
[12 empty] | Data Review, Initial Site Visit,s and Develop 2019 Field Investigation Work Plan | 129310
[12 empty] | 2019 Site Investigation | 525325
[12 empty] | Future Site Investigation Work Plan for Design | 127815
[12 empty] | Project Management | 194177
[12 empty] | Expenses | 1255000
[12 empty] | Draft EIS/EIR Review and Strategic Consultation | 183585
[12 empty] | Prepare Admin Final Responses to Comments | 706108
[12 empty] | Prepare Administrative Final EIR/EIS | 715087
[12 empty] | Begin Preparation of Administrative Record for Final EIR/EIS | 39838
[12 empty] | Engagement | 84620
[12 empty] | Geotechnical Environmental Document | 100374
[12 empty] | Project Management | 118736
[12 empty] | Expenses | 4500
[12 empty] | Finalize Joint Biological Assessment | 1587973
[12 empty] | Finalize Geotechnical Permits and Fieldwork | 210858
[12 empty] | Prepare Section 106 Documents | 550076
[12 empty] | Begin Preperation of Permits and Agreements | 449881
[12 empty] | Prepare for 2020 Field Work Studies | 10669
[12 empty] | Strategize on Mitigation and Adaptive Management Planning | 157261
[12 empty] | Project Management | 178987
[12 empty] | Expenses | 217000
Formulas:
Current Completion Date = IF(A7<=DeliverableCount,INDEX(vw_Deliverables_wVendorTaskId[#All],MATCH(ConsultantChoice,vw_Deliverables_wVendorTaskId[Vendor_Alpha],0)+A7,11),"")
Monthly Progress Template
Cover Page
Monthly Progress Template
Invoice Data
Consultant Monthly Progress Template
Deliverables Progress
 Consultant's data entry is restricted to white shaded cells.
 Submit weekly to Sites Sharepoint (use link button below)
 In case you have trouble, email KStubblefield@brwncald.com
Link to Sites Sharepoint Project Controls - (A/P) Invoices
Note on L6: Enter a "1" to mark the deliverable encountering an issue identified on the General Issues page.

## b) Task Work
Monthly Progress Template BRI 2019-11 - 12-2-2019 Dec 03, 2019
BRI Work Progress for 2019-11 Period
Row | Consultant | Phase | Task # | Task Name | % Work Complete |  | Key Work Highlights for Current Work Period |  | Key Upcoming Work for Period 2019-12
1 | BRI | 2 | G01 | Develop Draft Right-of-Way Manual Sections | 0% | 1 | Limited Scope Task - No Current Activities; No Current Billing | 1 | Process and Procedure Development, As Needed
2 | BRI | 2 | G01 | Develop Draft Right-of-Way Manual Sections |  | 2 |  | 2
3 | BRI | 2 | G01 | Develop Draft Right-of-Way Manual Sections |  | 3 |  | 3
4 | BRI | 2 | G01 | Develop Draft Right-of-Way Manual Sections |  | 4 |  | 4
5 | BRI | 2 | G01 | Develop Draft Right-of-Way Manual Sections |  | 5 |  | 5
6 | BRI | 2 | G02 | Right-of-Way Planning Efforts | 0% | 1 | Limited Scope Task - No Current Activities; No Current Billing | 1 | Process and Procedure Development, As Needed
7 | BRI | 2 | G02 | Right-of-Way Planning Efforts |  | 2 |  | 2
8 | BRI | 2 | G02 | Right-of-Way Planning Efforts |  | 3 |  | 3
9 | BRI | 2 | G02 | Right-of-Way Planning Efforts |  | 4 |  | 4
10 | BRI | 2 | G02 | Right-of-Way Planning Efforts |  | 5 |  | 5
11 | BRI | 2 | G03 | Right-of-Entry / Early-Access Program | 50% | 1 | Integration / Coordination Meetings | 1 | Continued Coordination with Service Area Providers and Stakeholders
12 | BRI | 2 | G03 | Right-of-Entry / Early-Access Program |  | 2 | Coordination with Service Area Providers, USBR, MID, GCID, TCCA, Tribal Representatives regarding real estate matters | 2 | Programmatic Real Estate Support
13 | BRI | 2 | G03 | Right-of-Entry / Early-Access Program |  | 3 | Necessary Rights and Engagement for Geotech 2019 | 3 | Continued Support of Geotech 2019
14 | BRI | 2 | G03 | Right-of-Entry / Early-Access Program |  | 4 |  | 4
15 | BRI | 2 | G03 | Right-of-Entry / Early-Access Program |  | 5 |  | 5
16 | BRI | 2 | G04 | Property Management Program | 0% | 1 | As-Needed Task - No Current Need; No Current Billing | 1 | As Needed
17 | BRI | 2 | G04 | Property Management Program |  | 2 |  | 2
18 | BRI | 2 | G04 | Property Management Program |  | 3 |  | 3
19 | BRI | 2 | G04 | Property Management Program |  | 4 |  | 4
20 | BRI | 2 | G04 | Property Management Program |  | 5 |  | 5
21 | BRI | 2 | G05 | Public Outreach and Community Engagement | 50% | 1 | Coordination with External Communications Team | 1 | Coordination with External Communications Team
22 | BRI | 2 | G05 | Public Outreach and Community Engagement |  | 2 | Landowner / Stakeholder Outreach and Engagement | 2 | Landowner / Stakeholder Outreach and Engagement
23 | BRI | 2 | G05 | Public Outreach and Community Engagement |  | 3 | Support of Geotech 2019 | 3 | Continued Support of Geotech 2019
24 | BRI | 2 | G05 | Public Outreach and Community Engagement |  | 4 |  | 4
25 | BRI | 2 | G05 | Public Outreach and Community Engagement |  | 5 |  | 5
26 | BRI | 2 | G98 | Project Management / QC | 50% | 1 | Attendance at Meetings | 1 | Attendance at Meetings
27 | BRI | 2 | G98 | Project Management / QC |  | 2 | Tracking, Reporting | 2 | Tracking, Reporting
28 | BRI | 2 | G98 | Project Management / QC |  | 3 | Coordination Efforts - Other Service Area Providers, Subs, Personnel, etc | 3 | Coordination Efforts - Other Service Area Providers, Subs, Personnel, etc
29 | BRI | 2 | G98 | Project Management / QC |  | 4 |  | 4
30 | BRI | 2 | G98 | Project Management / QC |  | 5 |  | 5
31 | BRI | 2 | G99 | Expenses | na | 1 | Approved Expenses, as-needed to execute directed Tasks | 1 | Approved Expenses, as-needed to execute directed Tasks
32 | BRI | 2 | G99 | Expenses |  | 2 |  | 2
33 | BRI | 2 | G99 | Expenses |  | 3 |  | 3
34 | BRI | 2 | G99 | Expenses |  | 4 |  | 4
35 | BRI | 2 | G99 | Expenses |  | 5 |  | 5
36 | BRI | 2 |  |  |  | 1 |  | 1
37 | BRI | 2 |  |  |  | 2 |  | 2
38 | BRI | 2 |  |  |  | 3 |  | 3
39 | BRI | 2 |  |  |  | 4 |  | 4
40 | BRI | 2 |  |  |  | 5 |  | 5
41 | BRI | 2 |  |  |  | 1 |  | 1
42 | BRI | 2 |  |  |  | 2 |  | 2
43 | BRI | 2 |  |  |  | 3 |  | 3
44 | BRI | 2 |  |  |  | 4 |  | 4
45 | BRI | 2 |  |  |  | 5 |  | 5
46 | BRI | 2 |  |  |  | 1 |  | 1
47 | BRI | 2 |  |  |  | 2 |  | 2
48 | BRI | 2 |  |  |  | 3 |  | 3
49 | BRI | 2 |  |  |  | 4 |  | 4
50 | BRI | 2 |  |  |  | 5 |  | 5
51 | BRI | 2 |  |  |  | 1 |  | 1
52 | BRI | 2 |  |  |  | 2 |  | 2
53 | BRI | 2 |  |  |  | 3 |  | 3
54 | BRI | 2 |  |  |  | 4 |  | 4
55 | BRI | 2 |  |  |  | 5 |  | 5
56 | BRI | 2 |  |  |  | 1 |  | 1
57 | BRI | 2 |  |  |  | 2 |  | 2
58 | BRI | 2 |  |  |  | 3 |  | 3
59 | BRI | 2 |  |  |  | 4 |  | 4
60 | BRI | 2 |  |  |  | 5 |  | 5
61 | BRI | 2 |  |  |  | 1 |  | 1
62 | BRI | 2 |  |  |  | 2 |  | 2
63 | BRI | 2 |  |  |  | 3 |  | 3
64 | BRI | 2 |  |  |  | 4 |  | 4
65 | BRI | 2 |  |  |  | 5 |  | 5
66 | BRI | 2 |  |  |  | 1 |  | 1
67 | BRI | 2 |  |  |  | 2 |  | 2
68 | BRI | 2 |  |  |  | 3 |  | 3
69 | BRI | 2 |  |  |  | 4 |  | 4
70 | BRI | 2 |  |  |  | 5 |  | 5
71 | BRI | 2 |  |  |  | 1 |  | 1
72 | BRI | 2 |  |  |  | 2 |  | 2
73 | BRI | 2 |  |  |  | 3 |  | 3
74 | BRI | 2 |  |  |  | 4 |  | 4
75 | BRI | 2 |  |  |  | 5 |  | 5
76 | BRI | 2 |  |  |  | 1 |  | 1
77 | BRI | 2 |  |  |  | 2 |  | 2
78 | BRI | 2 |  |  |  | 3 |  | 3
79 | BRI | 2 |  |  |  | 4 |  | 4
80 | BRI | 2 |  |  |  | 5 |  | 5
81 | BRI | 2 |  |  |  | 1 |  | 1
82 | BRI | 2 |  |  |  | 2 |  | 2
83 | BRI | 2 |  |  |  | 3 |  | 3
84 | BRI | 2 |  |  |  | 4 |  | 4
85 | BRI | 2 |  |  |  | 5 |  | 5
86 | BRI | 2 |  |  |  | 1 |  | 1
87 | BRI | 2 |  |  |  | 2 |  | 2
88 | BRI | 2 |  |  |  | 3 |  | 3
89 | BRI | 2 |  |  |  | 4 |  | 4
90 | BRI | 2 |  |  |  | 5 |  | 5
91 | BRI | 2 |  |  |  | 1 |  | 1
92 | BRI | 2 |  |  |  | 2 |  | 2
93 | BRI | 2 |  |  |  | 3 |  | 3
94 | BRI | 2 |  |  |  | 4 |  | 4
95 | BRI | 2 |  |  |  | 5 |  | 5
96 | BRI | 2 |  |  |  | 1 |  | 1
97 | BRI | 2 |  |  |  | 2 |  | 2
98 | BRI | 2 |  |  |  | 3 |  | 3
99 | BRI | 2 |  |  |  | 4 |  | 4
100 | BRI | 2 |  |  |  | 5 |  | 5
101 | BRI | 2 |  |  |  | 1 |  | 1
102 | BRI | 2 |  |  |  | 2 |  | 2
103 | BRI | 2 |  |  |  | 3 |  | 3
104 | BRI | 2 |  |  |  | 4 |  | 4
105 | BRI | 2 |  |  |  | 5 |  | 5
Note on G5: Use filter to control # bullet lines
Note on H5: Fill in bullet points to explain items completed during current work period.
Monthly Progress Template
Cover Page
Monthly Progress Template
Invoice Data
Consultant Progress Template
Task Work Progress
 Consultant's data entry restricted to white cells.
 Make sure all % complete cells are updated.
 You can hide empty rows if you wish
Link to Sites Sharepoint Project Controls - (A/P) Invoices
 Submit weekly to Sharepoint (use link button below)
 In case you have trouble, email KStubblefield@brwncald.com
Monthly Progress Template
Invoice Data
Monthly Progress Template
Invoice Data

## c) General Issues
Monthly Progress Template BRI 2019-11 - 12-2-2019 Dec 03, 2019
Possible Impacts
Check all that apply
# | Issues / Challenges | Approach to Resolving or Mitigating Issues | Budget | Schedule | Scope | Completed | Comments
1 | Uncertainty regarding liklihood of Geotech Activities to occur in 2019. | Stay informed of latest information - maintain coordination |  | 1 |  | 1 | As of 10/7/2019, this Item is resolved
2 | Schedule regarding potential Geotech Activities that may occur in 2019 | Stay informed of latest information - maintain coordination |  | 1 |  | 1 | As of 10/7/2019, this Item is resolved
3 | Need for Geotechnical, Biological, Cultural, Environmental, Avian, Botanical, and other studies in 2020 | Stay informed of latest information - maintain coordination | 1 | 1 | 1
4 | Uncertainty regarding need for CPT at "Pipeline MID" Location - this will depend upon results of CPT-18 | Stay informed of latest information - maintain coordination | 1 | 1 | 1
5 | Uncertainty regarding 2020 Real Estate Need and Public Engagement Need | Stay informed of latest information - maintain coordination | 1 | 1 | 1
6
7
8
9
10
11
Monthly Progress Template
Cover Page
Monthly Progress Template
Invoice Data
Monthly Progress Template
General Issues
 Consultant's data entry restricted to white cells.
 Make sure all white cells are completed per row
 Add closure comments to indicate item has been remedied.
Link to Sites Sharepoint Project Controls - (A/P) Invoices
 Sharepoint account needed
 Submit weekly to Sharepoint (use link button below)
 In case you have trouble, email KStubblefield@brwncald.com
Note on C4: If you copy content from another source, please paste in as values
Note on D5: enter a "1" in cells that apply
Note on G5: Select a "1" to indicate Issue has been closed
Note on H6: Fill in comments only when the challenge has been met

## Output-Deliverables (hidden)
Firm | Phase | Work Period | Task ID | Your Task # | Deliverable ID | Deliverable Name | Current Completion Date | % Complete | Proposed Completion Date | Justification for Extension | Progress made during Work Period | Issue
BRI | 2 | 2019-11 | G03 | G3.1 | SYS01 | Line List | 2019-12-31 | 50% |  | 0 | This is an ongoing Task - Data for this Task is located in the R/W GIS Tool; maintenance of Data, and inclusion of new information is ongoing | 0
BRI | 2 | 2019-11 | G04 | G4.1 | PLN01 | Property Management Plan (1) | 2019-12-31 | 0% |  | 0 | This Task is As-Needed - No Current Need; No Current Billing | 0
BRI | 2 | 2019-11 | G04 | G4.1 | PLN02 | Acquired Property Disposition Plan (1) | 2019-12-31 | 0% |  | 0 | This Task is As-Needed - No Current Need; No Current Billing | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0
BRI | 2 | 2019-11 | [5 empty] | 0% |  | 0 | 0 | 0

## Output-Tasks (hidden)
Consultant | Phase | WorkPeriod | TaskID | Task_Name | PercentComplete | Item | Work Performed_Current | Item_M1 | Worktodo_M1
BRI | 2 | 2019-11 | G01 | Develop Draft Right-of-Way Manual Sections | 0% | 1 | Limited Scope Task - No Current Activities; No Current Billing | 1 | Process and Procedure Development, As Needed
BRI | 2 | 2019-11 | G01 | Develop Draft Right-of-Way Manual Sections | 0% | 2 | 0 | 2 | 0
BRI | 2 | 2019-11 | G01 | Develop Draft Right-of-Way Manual Sections | 0% | 3 | 0 | 3 | 0
BRI | 2 | 2019-11 | G01 | Develop Draft Right-of-Way Manual Sections | 0% | 4 | 0 | 4 | 0
BRI | 2 | 2019-11 | G01 | Develop Draft Right-of-Way Manual Sections | 0% | 5 | 0 | 5 | 0
BRI | 2 | 2019-11 | G02 | Right-of-Way Planning Efforts | 0% | 1 | Limited Scope Task - No Current Activities; No Current Billing | 1 | Process and Procedure Development, As Needed
BRI | 2 | 2019-11 | G02 | Right-of-Way Planning Efforts | 0% | 2 | 0 | 2 | 0
BRI | 2 | 2019-11 | G02 | Right-of-Way Planning Efforts | 0% | 3 | 0 | 3 | 0
BRI | 2 | 2019-11 | G02 | Right-of-Way Planning Efforts | 0% | 4 | 0 | 4 | 0
BRI | 2 | 2019-11 | G02 | Right-of-Way Planning Efforts | 0% | 5 | 0 | 5 | 0
BRI | 2 | 2019-11 | G03 | Right-of-Entry / Early-Access Program | 50% | 1 | Integration / Coordination Meetings | 1 | Continued Coordination with Service Area Providers and Stakeholders
BRI | 2 | 2019-11 | G03 | Right-of-Entry / Early-Access Program | 0% | 2 | Coordination with Service Area Providers, USBR, MID, GCID, TCCA, Tribal Representatives regarding real estate matters | 2 | Programmatic Real Estate Support
BRI | 2 | 2019-11 | G03 | Right-of-Entry / Early-Access Program | 0% | 3 | Necessary Rights and Engagement for Geotech 2019 | 3 | Continued Support of Geotech 2019
BRI | 2 | 2019-11 | G03 | Right-of-Entry / Early-Access Program | 0% | 4 | 0 | 4 | 0
BRI | 2 | 2019-11 | G03 | Right-of-Entry / Early-Access Program | 0% | 5 | 0 | 5 | 0
BRI | 2 | 2019-11 | G04 | Property Management Program | 0% | 1 | As-Needed Task - No Current Need; No Current Billing | 1 | As Needed
BRI | 2 | 2019-11 | G04 | Property Management Program | 0% | 2 | 0 | 2 | 0
BRI | 2 | 2019-11 | G04 | Property Management Program | 0% | 3 | 0 | 3 | 0
BRI | 2 | 2019-11 | G04 | Property Management Program | 0% | 4 | 0 | 4 | 0
BRI | 2 | 2019-11 | G04 | Property Management Program | 0% | 5 | 0 | 5 | 0
BRI | 2 | 2019-11 | G05 | Public Outreach and Community Engagement | 50% | 1 | Coordination with External Communications Team | 1 | Coordination with External Communications Team
BRI | 2 | 2019-11 | G05 | Public Outreach and Community Engagement | 0% | 2 | Landowner / Stakeholder Outreach and Engagement | 2 | Landowner / Stakeholder Outreach and Engagement
BRI | 2 | 2019-11 | G05 | Public Outreach and Community Engagement | 0% | 3 | Support of Geotech 2019 | 3 | Continued Support of Geotech 2019
BRI | 2 | 2019-11 | G05 | Public Outreach and Community Engagement | 0% | 4 | 0 | 4 | 0
BRI | 2 | 2019-11 | G05 | Public Outreach and Community Engagement | 0% | 5 | 0 | 5 | 0
BRI | 2 | 2019-11 | G98 | Project Management / QC | 50% | 1 | Attendance at Meetings | 1 | Attendance at Meetings
BRI | 2 | 2019-11 | G98 | Project Management / QC | 0% | 2 | Tracking, Reporting | 2 | Tracking, Reporting
BRI | 2 | 2019-11 | G98 | Project Management / QC | 0% | 3 | Coordination Efforts - Other Service Area Providers, Subs, Personnel, etc | 3 | Coordination Efforts - Other Service Area Providers, Subs, Personnel, etc
BRI | 2 | 2019-11 | G98 | Project Management / QC | 0% | 4 | 0 | 4 | 0
BRI | 2 | 2019-11 | G98 | Project Management / QC | 0% | 5 | 0 | 5 | 0
BRI | 2 | 2019-11 | G99 | Expenses | na | 1 | Approved Expenses, as-needed to execute directed Tasks | 1 | Approved Expenses, as-needed to execute directed Tasks
BRI | 2 | 2019-11 | G99 | Expenses | 0% | 2 | 0 | 2 | 0
BRI | 2 | 2019-11 | G99 | Expenses | 0% | 3 | 0 | 3 | 0
BRI | 2 | 2019-11 | G99 | Expenses | 0% | 4 | 0 | 4 | 0
BRI | 2 | 2019-11 | G99 | Expenses | 0% | 5 | 0 | 5 | 0
BRI | 2 | 2019-11 |  |  | 0% | 1 | 0 | 1 | 0
BRI | 2 | 2019-11 |  |  | 0% | 2 | 0 | 2 | 0
BRI | 2 | 2019-11 |  |  | 0% | 3 | 0 | 3 | 0
BRI | 2 | 2019-11 |  |  | 0% | 4 | 0 | 4 | 0
BRI | 2 | 2019-11 |  |  | 0% | 5 | 0 | 5 | 0
BRI | 2 | 2019-11 |  |  | 0% | 1 | 0 | 1 | 0
BRI | 2 | 2019-11 |  |  | 0% | 2 | 0 | 2 | 0
BRI | 2 | 2019-11 |  |  | 0% | 3 | 0 | 3 | 0
BRI | 2 | 2019-11 |  |  | 0% | 4 | 0 | 4 | 0
BRI | 2 | 2019-11 |  |  | 0% | 5 | 0 | 5 | 0
BRI | 2 | 2019-11 |  |  | 0% | 1 | 0 | 1 | 0
BRI | 2 | 2019-11 |  |  | 0% | 2 | 0 | 2 | 0
BRI | 2 | 2019-11 |  |  | 0% | 3 | 0 | 3 | 0
BRI | 2 | 2019-11 |  |  | 0% | 4 | 0 | 4 | 0
BRI | 2 | 2019-11 |  |  | 0% | 5 | 0 | 5 | 0
BRI | 2 | 2019-11 |  |  | 0% | 1 | 0 | 1 | 0
BRI | 2 | 2019-11 |  |  | 0% | 2 | 0 | 2 | 0
BRI | 2 | 2019-11 |  |  | 0% | 3 | 0 | 3 | 0
BRI | 2 | 2019-11 |  |  | 0% | 4 | 0 | 4 | 0
BRI | 2 | 2019-11 |  |  | 0% | 5 | 0 | 5 | 0
BRI | 2 | 2019-11 |  |  | 0% | 1 | 0 | 1 | 0
BRI | 2 | 2019-11 |  |  | 0% | 2 | 0 | 2 | 0
BRI | 2 | 2019-11 |  |  | 0% | 3 | 0 | 3 | 0
BRI | 2 | 2019-11 |  |  | 0% | 4 | 0 | 4 | 0
BRI | 2 | 2019-11 |  |  | 0% | 5 | 0 | 5 | 0
BRI | 2 | 2019-11 |  |  | 0% | 1 | 0 | 1 | 0
BRI | 2 | 2019-11 |  |  | 0% | 2 | 0 | 2 | 0
BRI | 2 | 2019-11 |  |  | 0% | 3 | 0 | 3 | 0
BRI | 2 | 2019-11 |  |  | 0% | 4 | 0 | 4 | 0
BRI | 2 | 2019-11 |  |  | 0% | 5 | 0 | 5 | 0
BRI | 2 | 2019-11 |  |  | 0% | 1 | 0 | 1 | 0
BRI | 2 | 2019-11 |  |  | 0% | 2 | 0 | 2 | 0
BRI | 2 | 2019-11 |  |  | 0% | 3 | 0 | 3 | 0
BRI | 2 | 2019-11 |  |  | 0% | 4 | 0 | 4 | 0
BRI | 2 | 2019-11 |  |  | 0% | 5 | 0 | 5 | 0
BRI | 2 | 2019-11 |  |  | 0% | 1 | 0 | 1 | 0
BRI | 2 | 2019-11 |  |  | 0% | 2 | 0 | 2 | 0
BRI | 2 | 2019-11 |  |  | 0% | 3 | 0 | 3 | 0
BRI | 2 | 2019-11 |  |  | 0% | 4 | 0 | 4 | 0
BRI | 2 | 2019-11 |  |  | 0% | 5 | 0 | 5 | 0
BRI | 2 | 2019-11 |  |  | 0% | 1 | 0 | 1 | 0
BRI | 2 | 2019-11 |  |  | 0% | 2 | 0 | 2 | 0
BRI | 2 | 2019-11 |  |  | 0% | 3 | 0 | 3 | 0
BRI | 2 | 2019-11 |  |  | 0% | 4 | 0 | 4 | 0
BRI | 2 | 2019-11 |  |  | 0% | 5 | 0 | 5 | 0
BRI | 2 | 2019-11 |  |  | 0% | 1 | 0 | 1 | 0
BRI | 2 | 2019-11 |  |  | 0% | 2 | 0 | 2 | 0
BRI | 2 | 2019-11 |  |  | 0% | 3 | 0 | 3 | 0
BRI | 2 | 2019-11 |  |  | 0% | 4 | 0 | 4 | 0
BRI | 2 | 2019-11 |  |  | 0% | 5 | 0 | 5 | 0
BRI | 2 | 2019-11 |  |  | 0% | 1 | 0 | 1 | 0
BRI | 2 | 2019-11 |  |  | 0% | 2 | 0 | 2 | 0
BRI | 2 | 2019-11 |  |  | 0% | 3 | 0 | 3 | 0
BRI | 2 | 2019-11 |  |  | 0% | 4 | 0 | 4 | 0
BRI | 2 | 2019-11 |  |  | 0% | 5 | 0 | 5 | 0
BRI | 2 | 2019-11 |  |  | 0% | 1 | 0 | 1 | 0
BRI | 2 | 2019-11 |  |  | 0% | 2 | 0 | 2 | 0
BRI | 2 | 2019-11 |  |  | 0% | 3 | 0 | 3 | 0
BRI | 2 | 2019-11 |  |  | 0% | 4 | 0 | 4 | 0
BRI | 2 | 2019-11 |  |  | 0% | 5 | 0 | 5 | 0
BRI | 2 | 2019-11 |  |  | 0% | 1 | 0 | 1 | 0
BRI | 2 | 2019-11 |  |  | 0% | 2 | 0 | 2 | 0
BRI | 2 | 2019-11 |  |  | 0% | 3 | 0 | 3 | 0
BRI | 2 | 2019-11 |  |  | 0% | 4 | 0 | 4 | 0
BRI | 2 | 2019-11 |  |  | 0% | 5 | 0 | 5 | 0
BRI | 2 | 2019-11 |  |  | 0% | 1 | 0 | 1 | 0
BRI | 2 | 2019-11 |  |  | 0% | 2 | 0 | 2 | 0
BRI | 2 | 2019-11 |  |  | 0% | 3 | 0 | 3 | 0
BRI | 2 | 2019-11 |  |  | 0% | 4 | 0 | 4 | 0
BRI | 2 | 2019-11 |  |  | 0% | 5 | 0 | 5 | 0

## Output-Issues (hidden)
Firm | Phase | Period | # | Issues / Challenges | Approach to Resolving or Mitigating Issues | Budget | Schedule | Scope | Completed | Comments
BRI | 2 | 2019-11 | 1 | Uncertainty regarding liklihood of Geotech Activities to occur in 2019. | Stay informed of latest information - maintain coordination | 0 | 1 | 0 | 1 | As of 10/7/2019, this Item is resolved
BRI | 2 | 2019-11 | 2 | Schedule regarding potential Geotech Activities that may occur in 2019 | Stay informed of latest information - maintain coordination | 0 | 1 | 0 | 1 | As of 10/7/2019, this Item is resolved
BRI | 2 | 2019-11 | 3 | Need for Geotechnical, Biological, Cultural, Environmental, Avian, Botanical, and other studies in 2020 | Stay informed of latest information - maintain coordination | 1 | 1 | 1 | 0
BRI | 2 | 2019-11 | 4 | Uncertainty regarding need for CPT at "Pipeline MID" Location - this will depend upon results of CPT-18 | Stay informed of latest information - maintain coordination | 1 | 1 | 1 | 0
BRI | 2 | 2019-11 | 5 | Uncertainty regarding 2020 Real Estate Need and Public Engagement Need | Stay informed of latest information - maintain coordination | 1 | 1 | 1 | 0
BRI | 2 | 2019-11 | 6 | 0 | 0 | 0 | 0 | 0 | 0
BRI | 2 | 2019-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BRI | 2 | 2019-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BRI | 2 | 2019-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BRI | 2 | 2019-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BRI | 2 | 2019-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BRI | 2 | 2019-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BRI | 2 | 2019-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BRI | 2 | 2019-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BRI | 2 | 2019-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BRI | 2 | 2019-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BRI | 2 | 2019-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BRI | 2 | 2019-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BRI | 2 | 2019-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BRI | 2 | 2019-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BRI | 2 | 2019-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Setup (hidden)
Service Areas
Service Area |  | Service_Areas | Service_ID | Service_Code | Firm_ID | Authority_Agent | PI_Lead
g) Real Estate |  | a) Project Integration | A | INT | HDR | Trapasso | John Buttz
|  | b) Project Controls | B | PCO | BC | Trapasso | Cathy Westcot
Consultant |  | c) Communications and Public Outreach | C | COM | K&A | Spesert | Kim Pallari
BRI | g-BRI | d) Operations Simulation Modeling | D | OPS | CH2-d | Rob Thomson | Steve Weaver
|  | e) Environmental Planning and Analysis | E | ENV | ICF-e | Rob Thomson | Laurie Warner Herson
Work Period |  | f) Permitting Agreeements | F | PER | ICF-f | Rob Thomson | John Spranza
2019-11 |  | g) Real Estate | G | ROW | BRI | Spesert | Erin Heydinger
|  | h) Engineering | H | ENG | TBD | TBD | Lee Frederiksen
Filename |  | i) Geotechnical Engineering | I | GEO | FUG | Jim Watson | Chris Krivanec
C:\Users\cmcdonald\Desktop\Sites Reservoir Project\Task Order No 2 - Project Management\Monthly Progress Report - November 2019\[Monthly Progress Template BRI 2019-11 - 12-2-2019.xlsx]c) General Issues
Work / Billing Periods
2019-01
2019-02
2019-03
2019-04
2019-05
2019-06
2019-07
2019-08
2019-09
2019-10
2019-11
2019-12
TaskCount
7
Phase
2
DeliverableCount
3

## vw_Deliverables_wVendorTaskId (hidden)
ID | Phase | Vendor_Alpha | Service_Area | Task_Number | Vendor_TaskID | Type | Deliverable_ID | Name | Original_Completion | Current_Completion
136 | 1 |  | A |  |  | IMG | IMG01 | Quick Start Plan
130 | 1 |  | A |  |  | IMG | IMG02 | 2019 Committee and Work Group Structure
131 | 1 |  | A |  |  | IMG | IMG03 | Phase 2A Organization Chart
132 | 1 |  | A |  |  | IMG | IMG04 | Document Management Flowchart
133 | 1 |  | A |  |  | IMG | IMG05 | Staff Approval Process
134 | 1 |  | A |  |  | IMG | IMG06 | Monthly Reservoir Committee and Board Meeting Cycle
135 | 1 |  | A |  |  | IMG | IMG07 | New Staff Guide Outline
129 | 1 |  | A |  |  | MEM | MEM01 | File naming convention
117 | 1 |  | A |  |  | PMA | PMA02 | Matrix of Authority Draft
112 | 1 |  | A |  |  | PMA | PMA03 | Document Management Plan Draft
113 | 1 |  | A |  |  | PMA | PMA04 | Internal Communications Plan Outline Draft
114 | 1 |  | A |  |  | PMA | PMA05 | Engineering Management Section Outline Draft
118 | 1 |  | A |  |  | PMA | PMA12 | QMP for Environmental Planning and Permitting Draft
115 | 1 |  | A |  |  | PMA | PMA13 | Staff Approval Process Draft
116 | 1 |  | A |  |  | PMB | PMB04 | IT and GIS Plan Outline Draft
110 | 1 |  | A |  |  | PMP | PMP00
111 | 1 |  | A |  |  | PMA | PMP01 | Project Management Plan Outline
137 | 1 |  | A |  |  | PRE | PRE01 | Right-of-Way Process Draft
140 | 1 |  | G |  |  | TMS | TMS01 | Compensation Protocol Draft
128 | 1 |  | A |  |  | TMS | TMS01
119 | 1 |  | A |  |  | TMS | TMS02 | Environmental Team Communication Protocols Draft
141 | 1 |  | G |  |  | TMS | TMS02 | Delegation and Approval Draft
142 | 1 |  | G |  |  | TMS | TMS03 | Notice To Proceed and Authorization Process Draft
120 | 1 |  | A |  |  | TMS | TMS03 | Project Breakdown Structure Draft
121 | 1 |  | A |  |  | TMS | TMS04 | Special Studies Plan
143 | 1 |  | G |  |  | TMS | TMS04 | Policies and Procedures Workshop Draft
144 | 1 |  | G |  |  | TMS | TMS05 | Programmatic Negotiations Policies Draft
122 | 1 |  | A |  |  | TMS | TMS05 | Initial IT and SharePoint Setup Draft
123 | 1 |  | A |  |  | TMS | TMS06 | Natomas Office Support Draft
125 | 1 |  | A |  |  | TMS | TMS07
126 | 1 |  | A |  |  | TMS | TMS08
127 | 1 |  | A |  |  | TMS | TMS09
124 | 1 |  | A |  |  | TMS | TMS10 | Staff Support Plan Draft
2 | 2 | HDR | A | A03 | A03 | SYS | SYS01 | Environmental Tracking Tool
1 | 2 | HDR | A | A03 | A03 | TMS | TMS11 | Environmental QA/QC process
3 | 2 | HDR | A | A04 | A04 | SCH | SCH01 | Permitting Schedule | 2019-07-01 | 2019-07-01
4 | 2 | HDR | A | A06 | A06 | TMS | TMS12 | Procurement Approach TM | 2019-09-01 | 2019-09-01
5 | 2 | HDR | A | A07 | A07 | TMS | TMS13 | Review comments on 2019 GIWP | 2019-07-31 | 2019-07-31
7 | 2 | HDR | A | A08 | A08 | SCH | SCH02 | Governance Meetings calendar | 2019-05-01 | 2019-05-01
6 | 2 | HDR | A | A08 | A08 | SYS | SYS02 | Smartsheet for Res Committee and Board Items | 2019-05-01 | 2019-05-01
8 | 2 | HDR | A | A11 | A11 | TMS | TMS14 | Field Trip Safety TM | 2019-06-01 | 2019-07-01
9 | 2 | HDR | A | A14 | A14 | PLN | PLN01 | 2019 IT Plan | 2019-07-01 | 2019-07-01
10 | 2 | HDR | A | A14 | A14 | SYS | SYS03 | GIS ROW Tool - Desktop and Mobile Apps | 2019-06-12 | 2019-06-12
11 | 2 | HDR | A | A15 | A15 | PLN | PLN02 | GIS Plan | 2019-07-01 | 2019-07-01
12 | 2 | HDR | A | A15 | A15 | SYS | SYS04 | GIS Database | 2019-06-01 | 2019-06-01
13 | 2 | HDR | A | A15 | A15 | SYS | SYS05 | Project GIS web-viewer | 2019-06-01 | 2019-06-21
14 | 2 | HDR | A | A15 | A15 | SYS | SYS06 | GIS Map Templates | 2019-06-30 | 2019-06-30
15 | 2 | HDR | A | A16 | A16 | PLN | PLN03 | Document Management Plan (final) | 2019-04-30 | 2019-06-14
16 | 2 | HDR | A | A16 | A16 | SYS | SYS07 | TO2 Deliverables Documents Library | 2019-05-17 | 2019-06-14
23 | 2 | BC | B | B01 | B1 | PRO | PRO01 | Process Diagram for Data Entry | 2019-06-28 | 2019-06-28
24 | 2 | BC | B | B01 | B1 | PRO | PRO02 | Process Map for Reporting Approval Workflow | 2019-07-26 | 2019-07-26
17 | 2 | BC | B | B01 | B1 | SYS | SYS01 | Data Dictionary | 2019-12-31 | 2019-12-31
20 | 2 | BC | B | B01 | B1 | SYS | SYS02 | Reporting Database | 2019-06-21 | 2019-06-21
21 | 2 | BC | B | B01 | B1 | SYS | SYS03 | Board-Level MPR | 2019-06-12 | 2019-06-12
22 | 2 | BC | B | B01 | B1 | SYS | SYS04 | Commitments Worksheet | 2019-06-12 | 2019-06-12
18 | 2 | BC | B | B01 | B1 | TEM | TEM01 | Consultant-Level MPR | 2019-05-15 | 2019-05-15
19 | 2 | BC | B | B01 | B1 | TEM | TEM02 | Task Order Template | 2019-06-12 | 2019-06-12
138 | 1 | BC | B | B01 | B1 | TMS | TMS01 | PMIS Evaluation and Workplan Draft
26 | 2 | BC | B | B01 | B1 | TMS | TMS03 | PMIS Selection Factor TM | 2019-07-15 | 2019-07-15
27 | 2 | BC | B | B01 | B1 | TMS | TMS04 | PMIS Package Survey | 2019-07-15 | 2019-07-15
25 | 2 | BC | B | B01 | B1 | TMS | TMS11 | Initial Business Reports Set | 2019-06-12 | 2019-06-12
28 | 2 | BC | B | B02 | B2 | PRO | PRO03 | Consultant Agreement Approval Process | 2019-07-31 | 2019-07-31
29 | 2 | BC | B | B02 | B2 | PRO | PRO04 | Consulting Agreement Change Process | 2019-07-31 | 2019-07-31
30 | 2 | BC | B | B02 | B2 | PRO | PRO05 | Task Order Approval Process | 2019-07-31 | 2019-07-31
31 | 2 | BC | B | B02 | B2 | PRO | PRO06 | Task Order Close Process | 2019-07-31 | 2019-07-31
32 | 2 | BC | B | B02 | B2 | PRO | PRO07 | Staff Approval Process | 2019-07-31 | 2019-07-31
33 | 2 | BC | B | B02 | B2 | PRO | PRO08 | New Subconsultant Approval Process | 2019-07-31 | 2019-07-31
34 | 2 | BC | B | B02 | B2 | TEM | TEM03 | Monthly templates for CWC | 2019-04-30 | 2019-04-30
35 | 2 | BC | B | B03 | B3 | SCH | SCH01 | Master program schedule and activity database (2019) | 2019-08-30 | 2019-08-30
36 | 2 | BC | B | B03 | B3 | SCH | SCH02 | Master activity database (2019) | 2019-08-30 | 2019-08-30
39 | 2 | BC | B | B05 | B5 | PMA |  | Contract Administration Plan - Process Flow Diagram/Short Narrative | 2019-07-31 | 2019-07-31
145 | 1 | BC | B | B05 | B5 | PMA | PMA02 | Change Management Plan
37 | 2 | BC | B | B05 | B5 | PMA | PMA06 | Schedule Management Plan -Process Flow Diagram/Short Narrative | 2019-07-31 | 2019-07-31
38 | 2 | BC | B | B05 | B5 | PMA | PMA07 | Cost Management Plan - Process Flow Diagram/Short Narrative | 2019-07-31 | 2019-07-31
43 | 2 | K&A | C | C01 | C1.1 | NWS | NWS01 | Newsletter No. 1 | 2019-07-01 | 2019-07-01
44 | 2 | K&A | C | C01 | C1.1 | NWS | NWS02 | Newsletter No. 2 | 2019-10-01 | 2019-10-01
42 | 2 | K&A | C | C01 | C1.1 | PLN | PLN01 | Landowner Engagement Plan | 2019-09-01 | 2019-09-01
40 | 2 | K&A | C | C01 | C1.1 | SYS | SYS01 | Database Update No. 1 (local) | 2019-08-01 | 2019-08-01
41 | 2 | K&A | C | C01 | C1.1 | SYS | SYS02 | Database Update No. 2 (local) | 2019-12-01 | 2019-12-01
48 | 2 | K&A | C | C02 | C1.2 | SCH | SCH01 | Outreach Calendar | 2019-12-31 | 2019-12-31
45 | 2 | K&A | C | C02 | C1.2 | SYS | SYS03 | Database Update No. 1 (state) | 2019-08-01 | 2019-08-01
46 | 2 | K&A | C | C02 | C1.2 | SYS | SYS04 | Database Update No. 2 (state) | 2019-12-01 | 2019-12-01
47 | 2 | K&A | C | C02 | C1.2 | TEM | TEM01 | Stakeholder Toolkit | 2019-07-01 | 2019-07-01
49 | 2 | K&A | C | C05 | C2.2 | PLN | PLN02 | Updated message platform No. 1
50 | 2 | K&A | C | C05 | C2.2 | PLN | PLN03 | Updated message platform No. 2
51 | 2 | K&A | C | C05 | C2.2 | TRA | TRA01 | Speaker Training | 2019-08-01 | 2019-08-01
53 | 2 | K&A | C | C06 | C3.1 | NWS | NWS03 | Email Blast No. 1 | 2019-07-01 | 2019-07-01
54 | 2 | K&A | C | C06 | C3.1 | NWS | NWS04 | Email Blast No. 2 | 2019-11-01 | 2019-11-01
52 | 2 | K&A | C | C06 | C3.1 | TEM | TEM02 | Branding Templates | 2019-05-01 | 2019-05-01
55 | 2 | K&A | C | C06 | C3.1 | TEM | TEM03 | PowerPoint Template - Programmatic | 2019-05-15 | 2019-05-15
56 | 2 | K&A | C | C06 | C3.1 | TEM | TEM04 | PowerPoint Template - Topic-Specific | 2019-09-15 | 2019-09-15
57 | 2 | K&A | C | C07 | C4.1 | SYS | SYS05 | Website Transitioned | 2019-06-01 | 2019-06-01
58 | 2 | K&A | C | C09 | C5.1 | REP | REP01 | Media List | 2019-07-01 | 2019-07-01
59 | 2 | K&A | C | C11 | C7.1 | REP | REP02 | Phase 2A Summary of Social Media Engagement | 2019-12-31 | 2019-12-31
61 | 2 | CH2-d | D | D01 | D1 | PER | PER01 | CalSim results for permits | 2019-08-23 | 2019-08-23
62 | 2 | CH2-d | D | D01 | D1 | PER | PER02 | Side-channel habitat results for permits | 2019-08-23 | 2019-08-23
60 | 2 | CH2-d | D | D01 | D1 | TMS | TMS01 | Daily modeling analysis results and TM (permitting) | 2019-08-23 | 2019-08-23
64 | 2 | CH2-d | D | D02 | D2 | EIR | EIR01 | CalSim results for EIR/S | 2019-10-25 | 2019-10-25
63 | 2 | CH2-d | D | D02 | D2 | TMS | TMS02 | Analytical Framework and Tools TM (environmental) | 2019-10-25 | 2019-10-25
65 | 2 | CH2-d | D | D02 | D2 | TMS | TMS03 | Modeling analysis results and TM (environmental) | 2019-10-25 | 2019-10-25
66 | 2 | CH2-d | D | D03 | D3 | MOD | MOD01 | CE-QUAL-W2 modeling files | 2019-08-02 | 2019-08-02
67 | 2 | CH2-d | D | D03 | D3 | TMS | TMS04 | Water Quality Modeling results and TM | 2019-08-02 | 2019-08-02
68 | 2 | CH2-d | D | D98 | D4 | PRE | PRE01 | Ops Work Group Presentation (ops rebalancing) | 2019-07-08 | 2019-07-08
70 | 2 | CH2-d | D | D98 | D4 | PRE | PRE02 | Ops Work Group Presentation (ops technical support) | 2019-07-08 | 2019-07-08
69 | 2 | CH2-d | D | D98 | D4 | TMS | TMS05 | Ops Rebalancing results and TM | 2019-07-08 | 2019-07-08
71 | 2 | CH2-d | D | D98 | D4 | TMS | TMS06 | Ops Technical Support TM | 2019-12-31 | 2019-12-31
72 | 2 | ICF-e | E | E01 | E1 | EIR | EIR01 | EIR/EIS Strategy Meeting | 2019-06-28 | 2019-06-28
73 | 2 | ICF-e | E | E02 | E2 | EIR | EIR02 | Admin Final EIR/EIS Master Responses | 2019-07-31 | 2019-07-31
74 | 2 | ICF-e | E | E02 | E2 | EIR | EIR03 | Admin Final EIR/EIS Comment Response Table No. 1 | 2019-06-28 | 2019-06-28
75 | 2 | ICF-e | E | E02 | E2 | EIR | EIR04 | Admin Final EIR/EIS Comment Response Table No. 2 | 2019-07-31 | 2019-07-31
76 | 2 | ICF-e | E | E03 | E3 | REP | EIR05 | Admin Final EIR/EIS | 2019-12-31 | 2019-12-31
77 | 2 | ICF-e | E | E03 | E3 | SYS | SYS01 | Comment Response Tracking Tool | 2019-05-31 | 2019-05-31
78 | 2 | ICF-e | E | E04 | E4 | EIR | EIR06 | Admin Record for Final EIR/EIS | 2019-12-31 | 2019-12-31
80 | 2 | ICF-e | E | E06 | E6 | EIR | EIR07 | Errata sheet for EA/IS | 2019-08-22 | 2019-08-22
81 | 2 | ICF-e | E | E06 | E6 | REP | EIR08 | Final EA/IS (Geotech) | 2019-08-28 | 2019-08-28
79 | 2 | ICF-e | E | E06 | E6 | TMS | TMS01 | Cultural Resources TM | 2019-06-17 | 2019-06-17
82 | 2 | ICF-f | F | F01 | F1 | REP | REP01 | Draft Species Accounts for Project | 2019-06-30 | 2019-06-30
83 | 2 | ICF-f | F | F01 | F1 | REP | REP02 | Draft Biological Assessment for Project | 2019-06-30 | 2019-06-30
84 | 2 | ICF-f | F | F01 | F1 | REP | REP03 | Final Biological Assessment for Project | 2019-09-30 | 2019-09-30
85 | 2 | ICF-f | F | F02 | F2 | LET | LET01 | Geotech Section 106 Initiation Letter (Draft) | 2019-06-17 | 2019-06-17
147 | 2 | ICF-f | F | F02 | F2 | LET | LET02 | Geotech Section 106 Initiation Letter (Final)
87 | 2 | ICF-f | F | F02 | F2 | PER | PER01 | Geotech CWA Section 404 Permit Application | 2019-06-19 | 2019-06-19
88 | 2 | ICF-f | F | F02 | F2 | PER | PER02 | Geotech CWA Section 401 Permit Application | 2019-06-19 | 2019-06-19
89 | 2 | ICF-f | F | F02 | F2 | PER | PER03 | Geotech Lake or Streambed Alteration Application Packet | 2019-06-19 | 2019-06-19
90 | 2 | ICF-f | F | F02 | F2 | PER | PER04 | Geotech Documentation for Section 408 approval | 2019-06-19 | 2019-06-19
91 | 2 | ICF-f | F | F02 | F2 | PER | PER05 | Geotech Encroachment permit application (CVFPB) | 2019-06-19 | 2019-06-19
152 | 2 | ICF-f | F | F02 | F2 | PER | PER06 | State Lands Permit Geotech | 2019-06-19 | 2019-06-19
86 | 2 | ICF-f | F | F02 | F2 | REP | REP04 | Geotech Section 106 Historic Properties Report (Draft) | 2019-06-17 | 2019-06-17
148 | 2 | ICF-f | F | F02 | F2 | REP | REP05 | Geotech Section 106 Historic Properties Report (Final)
92 | 2 | ICF-f | F | F02 | F2 | REP | REP06 | Geotech Joint Biological Assessment for NMFS and USFWS | 2019-06-17 | 2019-06-17
93 | 2 | ICF-f | F | F03 | F3 | PLN | PLN01 | Public Involvement & Tribal Consultation Plan (Preliminary Draft) | 2019-08-15 | 2019-08-15
149 | 2 | ICF-f | F | F03 | F3 | PLN | PLN02 | Public Involvement & Tribal Consultation Plan (Draft)
150 | 2 | ICF-f | F | F03 | F3 | PLN | PLN03 | Public Involvement & Tribal Consultation Plan (Final)
94 | 2 | ICF-f | F | F03 | F3 | REP | REP07 | Draft Archeological Resources Inventory Report | 2019-11-11 | 2019-11-11
95 | 2 | ICF-f | F | F03 | F3 | REP | REP08 | Draft Built Environmental Inventory/Evaluation Report | 2019-11-11 | 2019-11-11
151 | 2 | ICF-f | F | F03 | F3 | REP | REP09 | Concept Memo for PA Approach
96 | 2 | ICF-f | F | F03 | F3 | TMS | TMS01 | Draft Programmatic Agreement | 2019-11-11 | 2019-11-11
155 | 2 | ICF-f | F | F04 | F4 | PER | PER07 | 208/ITP (Draft) | 2019-12-31 | 2019-12-31
98 | 2 | ICF-f | F | F04 | F4 | TMS | TMS02 | Permitting Approach TM | 2019-12-31 | 2019-12-31
153 | 2 | ICF-f | F | F04 | F4 | TMS | TMS04 | Corps Permit Approach Memo
100 | 2 | ICF-f | F | F05 | F5 | REP | REP10 | Parcel spreadsheet for survey access | 2019-06-15 | 2019-06-15
154 | 2 | ICF-f | F | F05 | F5 | TMS | TMS05 | Field Survey Plans Bio
101 | 2 | ICF-f | F | F06 | F6 | TMS | TMS03 | Mitigation Approach TM | 2019-12-31 | 2019-12-31
102 | 2 | BRI | G | G03 | G3.1 | SYS | SYS01 | Line List | 2019-12-31 | 2019-12-31
103 | 2 | BRI | G | G04 | G4.1 | PLN | PLN01 | Property Management Plan (1) | 2019-12-31 | 2019-12-31
104 | 2 | BRI | G | G04 | G4.1 | PLN | PLN02 | Acquired Property Disposition Plan (1) | 2019-12-31 | 2019-12-31
108 | 2 | FUG | I | I01 | I1 | PLN | PLN01 | Feasibility Study Field Investigation Work Plan | 2019-07-30 | 2019-07-30
105 | 2 | FUG | I | I01 | I1 | REP | REP01 | Documents Reviewed Tabulation | 2019-06-30 | 2019-06-30
106 | 2 | FUG | I | I01 | I1 | REP | REP02 | Geologic & Geotechnical Data Requirements Tabulation | 2019-06-30 | 2019-06-30
107 | 2 | FUG | I | I01 | I1 | SYS | SYS01 | Historic Boring Location GIS Layer | 2019-06-30 | 2019-06-30

## vw_ConsultantTaskItems (hidden)
ID | VendorAlpha | Phase | Task | Status | Description | FullID | FullID2
22 | BC | 2 | B01 |  | Project Controls | B-BC | BC-B01
23 | BC | 2 | B02 |  | Contract Administration and Compliance | B-BC | BC-B02
24 | BC | 2 | B03 |  | Work Planning and Scheduling | B-BC | BC-B03
25 | BC | 2 | B04 |  | Project Administrative Support | B-BC | BC-B04
26 | BC | 2 | B05 |  | PMP Sections | B-BC | BC-B05
27 | BC | 2 | B98 |  | Project Management | B-BC | BC-B98
28 | BC | 2 | B99 |  | Expenses | B-BC | BC-B99
29 | BRI | 2 | G01 |  | Develop Draft Right-of-Way Manual Sections | G-BRI | BRI-G01
30 | BRI | 2 | G02 |  | Right-of-Way Planning Efforts | G-BRI | BRI-G02
31 | BRI | 2 | G03 |  | Right-of-Entry / Early-Access Program | G-BRI | BRI-G03
32 | BRI | 2 | G04 |  | Property Management Program | G-BRI | BRI-G04
33 | BRI | 2 | G05 |  | Public Outreach and Community Engagement | G-BRI | BRI-G05
34 | BRI | 2 | G98 |  | Project Management / QC | G-BRI | BRI-G98.1
36 | BRI | 2 | G99 |  | Expenses | G-BRI | BRI-G99.1
50 | CH2-d | 2 | D01 |  | Permitting and Resource Agency Technical Support | D-CH2-d | CH2-d-D01
51 | CH2-d | 2 | D02 |  | Environmental Document Support | D-CH2-d | CH2-d-D02
52 | CH2-d | 2 | D03 |  | Total Operations Technical Support | D-CH2-d | CH2-d-D03
53 | CH2-d | 2 | D98 |  | Project Management | D-CH2-d | CH2-d-D98
54 | CH2-d | 2 | D99 |  | Subs and ODCS | D-CH2-d | CH2-d-D99
55 | FUG | 2 | I01 |  | Data Review and Develop 2019 Feasibility Study Work Plan | I-FUG | FUG-I01
56 | FUG | 2 | I02 | C | - Obsolete - | I-FUG | FUG-I02
57 | FUG | 2 | I03 | C | 2019 Site Investigation | I-FUG | FUG-I03
58 | FUG | 2 | I04 | C | Future Site Investigation Work Plan for Design | I-FUG | FUG-I04
59 | FUG | 2 | I98 |  | Project Management | I-FUG | FUG-I98
60 | FUG | 2 | I99 |  | Expenses | I-FUG | FUG-I99
1 | HDR | 2 | A01 |  | Communications Int. | A-HDR | HDR-A01
2 | HDR | 2 | A02 |  | Ops Modeling Int. | A-HDR | HDR-A02
3 | HDR | 2 | A03 |  | Env. Planning Int. | A-HDR | HDR-A03
4 | HDR | 2 | A04 |  | Permitting Int. | A-HDR | HDR-A04
5 | HDR | 2 | A05 |  | Real Estate Int. | A-HDR | HDR-A05
6 | HDR | 2 | A06 |  | Engineering Int. | A-HDR | HDR-A06
7 | HDR | 2 | A07 |  | Geotech Int. | A-HDR | HDR-A07
8 | HDR | 2 | A08 |  | Controls Int. | A-HDR | HDR-A08
9 | HDR | 2 | A09 |  | General Int. | A-HDR | HDR-A09
10 | HDR | 2 | A10 |  | Authority's Engineer | A-HDR | HDR-A10
11 | HDR | 2 | A11 |  | Health, Safety & Loss Prevention | A-HDR | HDR-A11
12 | HDR | 2 | A12 |  | Quality Management | A-HDR | HDR-A12
13 | HDR | 2 | A13 |  | Risk Management | A-HDR | HDR-A13
14 | HDR | 2 | A14 |  | IT | A-HDR | HDR-A14
15 | HDR | 2 | A15 |  | GIS | A-HDR | HDR-A15
16 | HDR | 2 | A16 |  | Document Management | A-HDR | HDR-A16
17 | HDR | 2 | A17 |  | Staff Support | A-HDR | HDR-A17
18 | HDR | 2 | A18 |  | Satellite Project Office | A-HDR | HDR-A18
19 | HDR | 2 | A19 |  | Land Conservation Approach | A-HDR | HDR-A19
20 | HDR | 2 | A98 |  | HDR Project Management | A-HDR | HDR-A98
21 | HDR | 2 | A99 |  | Expenses | A-HDR | HDR-A99
61 | ICF-e | 2 | E01 |  | Draft EIS/EIR Review and Strategic Consultation | E-ICF-e | ICF-e-E01
62 | ICF-e | 2 | E02 |  | Prepare Admin Final Responses to Comments | E-ICF-e | ICF-e-E02
63 | ICF-e | 2 | E03 |  | Prepare Administrative Final EIR/EIS | E-ICF-e | ICF-e-E03
64 | ICF-e | 2 | E04 |  | Begin Preparation of Administrative Record for Fin | E-ICF-e | ICF-e-E04
65 | ICF-e | 2 | E05 |  | Engagement | E-ICF-e | ICF-e-E05
66 | ICF-e | 2 | E06 |  | Geotechnical Environmental Document | E-ICF-e | ICF-e-E06
67 | ICF-e | 2 | E98 |  | Project Management | E-ICF-e | ICF-e-E98
68 | ICF-e | 2 | E99 |  | Expenses | E-ICF-e | ICF-e-E99
69 | ICF-f | 2 | F01 |  | Finalize Joint Biological Assessment | F-ICF-f | ICF-f-F01
70 | ICF-f | 2 | F02 |  | Finalize Geotechnical Permits and Fieldwork | F-ICF-f | ICF-f-F02
71 | ICF-f | 2 | F03 |  | Prepare Section 106 Documents | F-ICF-f | ICF-f-F03
72 | ICF-f | 2 | F04 |  | Begin Preparation of Permits and Agreements | F-ICF-f | ICF-f-F04
73 | ICF-f | 2 | F05 |  | Prepare for 2020 Field Work Studies | F-ICF-f | ICF-f-F05
74 | ICF-f | 2 | F06 |  | Strategize on Mitigation and Adaptive Management P | F-ICF-f | ICF-f-F06
75 | ICF-f | 2 | F98 |  | Project Management | F-ICF-f | ICF-f-F98
76 | ICF-f | 2 | F99 |  | Expenses | F-ICF-f | ICF-f-F99
37 | K&A | 2 | C01 |  | Local/Landowner Outreach | C-K&A | K&A-C01
38 | K&A | 2 | C02 |  | Statewide Outreach | C-K&A | K&A-C02
39 | K&A | 2 | C03 |  | NGO Outreach | C-K&A | K&A-C03
40 | K&A | 2 | C04 |  | Strategic Communications | C-K&A | K&A-C04
41 | K&A | 2 | C05 |  | Message Development/Training | C-K&A | K&A-C05
42 | K&A | 2 | C06 |  | Informational Materials Distribution | C-K&A | K&A-C06
43 | K&A | 2 | C07 |  | Website Modifications and Management | C-K&A | K&A-C07
44 | K&A | 2 | C08 |  | Video & Photography | C-K&A | K&A-C08
45 | K&A | 2 | C09 |  | Authority/Reservoir Committee Public Affairs Support | C-K&A | K&A-C09
46 | K&A | 2 | C10 |  | Media Relations | C-K&A | K&A-C10
47 | K&A | 2 | C11 |  | Social Media | C-K&A | K&A-C11
48 | K&A | 2 | C98 |  | Project Management | C-K&A | K&A-C98
49 | K&A | 2 | C99 |  | Expenses | C-K&A | K&A-C99