## byCritical
Activity ID | Finish | Anticipated Status as of 12/31/21
Total | 2021-12-31
Critical Deliverables | 2021-12-31
Section 106 Programmatic Agreement | 2021-12-01
ITP-Section 2081 Permits | 2021-12-07
Clean Water Act 404/401 Permit Applications | 2021-12-07
Water Right Application Preparation | 2021-12-31
Draft EIR/EIS Project Description Chapter | 2020-12-28
Revised Admin Draft EIR/EIS | 2021-03-09
Revised Public Draft EIR/EIS | 2021-07-14
Public Review Period/Public Meetings | 2021-09-12
Response to Comments/Summary Report for CWC | 2021-12-03
Admin Final EIR/EIS Response to Comments | 2021-12-31
Full Operations Analysis | 2020-12-31
Project Description Key Project Features & Facilities | 2021-12-30
Cost Estimate, Feasibility, Constructability Analysis for Feasibility Report | 2021-05-10
Draft Feasibility Report | 2021-05-19
Final Feasibility Report | 2021-08-20
Deliverables | 2021-12-31
Ops/Modeling Coordination | 2021-11-29
Biological Assessment/Biological Opinion Support | 2021-06-28
Mitigation Plan | 2021-04-05
Adaptive Management Plan | 2021-03-18
Section 408 Draft Packet | 2021-12-31
Focused Species Surveys | 2020-12-28
Geotechnical Field Monitoring | 2021-03-30
Early Mitigation | 2021-11-23
Feasibility Design and CADD Drawings for Modified Alternative A | 2020-11-04
DSOD Engagement Plan | 2021-11-30
Program Design/Construction/Permit Implementation | 2021-11-30
Class 4 Cost Estimate | 2020-12-23
Preliminary Hydraulics Model | 2021-07-16
Geotechnical Permit Planning & Investigation Plan | 2021-11-30
Engineering Project Coordination | 2021-12-31
Economics and Financial for Feasibility Report | 2021-03-31
Site Plan with Proposed Borings | 2020-11-25
Geotechnical Data Reports | 2021-06-29
Preliminary Planning for Design | 2021-12-30
Field Data Collection Work Plan/Cost Estimate | 2021-03-30
Business Deliverables | 2021-12-31
WIFIA Application | 2021-06-29
Risk Workshop Outcomes TM | 2020-12-31
Project Master Schedule | 2021-12-31
State Invoice/Progress Reports & Quarterly Reports | 2021-12-31
Successor Agreement | 2021-12-31
Successor Agreement Work Plan | 2021-12-01
Plan of Finance | 2021-08-02
Accounts Payable and Receivable | 2021-12-31
Monthly Board/Res Comm Support | 2021-12-31
Contract Management | 2021-12-31
Communications | 2021-12-31
Government Affairs WP 2020 | 2020-12-31
Government Affairs WP 2021 | 2021-12-31
Real Estate Landowner Coordination | 2021-12-31
Executive Director | 2021-12-31
Strategic Planner | 2021-12-31
Legal Counsel | 2021-12-31
Organizational Assessment | 2020-12-31
IT and GIS Support | 2021-12-31
Document Management | 2021-12-31
Business Management Vendors | 2021-12-31
Business Management | 2021-12-31
Project Management | 2021-12-31

## BySubArea
Activity ID | Start | Finish | Anticipated Status as of 12/31/21
Key Deliverables | 2020-09-01 | 2021-12-31
Permitting | 2020-09-01 | 2021-12-31
Section 106 Programmatic Agreement | 2020-09-01 | 2021-12-01 | Circulate Final PA to SHPO and Consulting Parties for Signatures
ITP-Section 2081 Permits | 2020-10-01 | 2021-12-07 | Submit ITP Application to CDFW
Clean Water Act 404/401 Permit Applications | 2020-09-09 | 2021-12-07 | Submit 404/401 Application
Water Right Application | 2020-09-01 | 2021-12-31 | Admin draft complete (1/6/2022). Submitted 4/1/2022
Environmental Planning | 2020-09-01 | 2021-12-31
Draft EIR/EIS Project Description Chapter | 2020-09-01 | 2020-12-28 | Complete
Revised Admin Draft EIR/EIS | 2020-09-01 | 2021-03-09 | Complete
Revised Public Draft EIR/EIS | 2020-12-29 | 2021-07-14 | Complete
Public Review Period/Public Meetings | 2021-07-15 | 2021-09-12 | Complete
Response to Comments/Summary Report for CWC | 2021-09-28 | 2021-12-03 | Complete
Admin Final EIR/EIS Response to Comments | 2021-10-19 | 2021-12-31 | Begin Preparation of Final EIR/EIS Including Response to Comments
Modeling | 2020-09-01 | 2020-12-31
Full Operations Analysis | 2020-09-01 | 2020-12-31 | Complete
Engineering | 2020-09-01 | 2021-12-30
Project Description Key Project Features & Facilities | 2020-09-01 | 2021-12-30 | Complete
Cost Estimate, Feasibility, Constructability Analysis for Feasibility Report | 2020-10-01 | 2021-05-10 | Complete
Draft Feasibility Report | 2021-04-01 | 2021-05-19 | Complete
Final Feasibility Report | 2021-05-20 | 2021-08-20 | Complete
Deliverables | 2020-09-01 | 2021-12-31
Permitting | 2020-09-01 | 2021-12-31
Biological Assessment/Biological Opinion Support | 2020-10-01 | 2021-06-28
Mitigation Plan | 2020-09-01 | 2021-04-05 | Complete
Adaptive Management Plan | 2020-09-01 | 2021-03-18 | Complete
Section 408 Draft Packet | 2020-09-01 | 2021-12-31 | Draft complete 1/2/2022. Encroachment Permit/408 Sumitted 6/30/2022
Focused Species Surveys | 2020-11-12 | 2020-12-28 | Prepare Terrestrial Analysis
Geotechnical Field Monitoring | 2020-11-30 | 2021-03-30 | Complete
Early Mitigation | 2021-11-09 | 2021-11-23
Modeling | 2021-01-04 | 2021-11-29
Ops/Modeling Coordination | 2021-01-04 | 2021-11-29 | Complete
Engineering | 2020-09-01 | 2021-12-31
Feasibility Design and CADD Drawings for Modified Alternative A | 2020-09-01 | 2020-11-04 | Complete
DSOD Engagement Plan | 2021-07-15 | 2021-11-30 | Complete
Program Design/Construction/Permit Implementation | 2021-07-15 | 2021-11-30 | Complete
Class 4 Cost Estimate | 2020-10-16 | 2020-12-23 | Complete
Preliminary Hydraulics Model | 2021-05-20 | 2021-07-16 | Complete
Geotechnical Permit Planning & Investigation Plan | 2021-07-15 | 2021-11-30 | Complete
Engineering Project Coordination | 2020-09-01 | 2021-12-31 | Complete
Economics and Financial for Feasibility Report | 2021-03-04 | 2021-03-31 | Complete
Geotech | 2020-09-01 | 2021-12-30
Site Plan with Proposed Borings | 2020-09-01 | 2020-11-25 | Complete
Geotechnical Data Reports | 2021-01-29 | 2021-06-29 | Complete
Preliminary Planning for Design | 2021-05-28 | 2021-12-30 | Complete
Field Data Collection Work Plan/Cost Estimate | 2020-11-30 | 2021-03-30 | Complete
Business Deliverables | 2020-09-01 | 2021-12-31
Engineering | 2020-09-01 | 2020-12-31
Risk Workshop Outcomes TM | 2020-09-01 | 2020-12-31
Real Estate | 2020-09-01 | 2021-12-31
Real Estate Landowner Coordination | 2020-09-01 | 2021-12-31
Communications | 2020-09-01 | 2021-12-31
Communications | 2020-09-01 | 2021-12-31
Government Affairs WP 2020 | 2020-09-01 | 2020-12-31
Government Affairs WP 2021 | 2021-01-04 | 2021-12-31
Project Controls | 2020-09-01 | 2021-12-31
Project Master Schedule | 2020-09-01 | 2021-12-31
State Invoice/Progress Reports & Quarterly Reports | 2020-09-01 | 2021-12-31
Accounts Payable and Receivable | 2020-09-01 | 2021-12-31
Monthly Board/Res Comm Support | 2020-09-01 | 2021-12-31
Contract Management | 2020-09-01 | 2021-12-31
Funding | 2020-09-01 | 2021-12-31
WIFIA Application | 2021-01-05 | 2021-06-29
State Invoice/Progress Reports & Quarterly Reports | 2020-09-01 | 2021-12-31
Growth | 2020-09-01 | 2021-12-31
Successor Agreement | 2021-08-02 | 2021-12-31
Successor Agreement Work Plan | 2021-08-02 | 2021-12-01
Plan of Finance | 2021-03-01 | 2021-08-02
Organizational Assessment | 2020-09-01 | 2020-12-31
Management | 2020-09-01 | 2021-12-31
Executive Director | 2020-09-01 | 2021-12-31
Strategic Planner | 2020-09-01 | 2021-12-31
Business Management | 2020-09-01 | 2021-12-31
Project Management | 2020-09-01 | 2021-12-31
Support | 2020-09-01 | 2021-12-31
Legal Counsel | 2020-09-01 | 2021-12-31
IT and GIS Support | 2020-09-01 | 2021-12-31
Document Management | 2020-09-01 | 2021-12-31
Business Management Vendors | 2020-09-01 | 2021-12-31
Business Management | 2020-09-01 | 2021-12-31