## Ali
Sites Monthly Project Schedule Update |  |  |  |  | Data Date: | 2020-04-30
Activity ID | Activity Name | Ori Dur | Remaining Dur | Total Float | Physical % Comp | Baseline Start | Current Start | Actual Start | Baseline Finish | Current Finish | Actual Finish
Ali Forsythe |  | 856 | 856 | 0 |  | 2020-01-02 | 2020-01-02 |  | 2023-05-09 | 2023-05-12
VALUE PLANNING |  | 37 | 37 | 15 |  | 2020-01-02 | 2020-01-02 |  | 2020-02-21 | 2020-02-21
Value Planning Analysis |  | 37 | 37 | 15 |  | 2020-01-02 | 2020-01-02 |  | 2020-02-21 | 2020-02-21
VP-006 | Qualitative Permit Screening | 37 | 37 | 15 | 0% | 2020-01-02 | 2020-01-02 | A | 2020-02-21 | 2020-02-21 | A
VP-007 | Qualitative Env Screening | 37 | 37 | 15 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-02-21 | 2020-02-21
VP-008 | Qualitative Ops Screening | 37 | 37 | 15 | 100% | 2020-01-02 | 2020-01-02 |  | 2020-02-21 | 2020-02-21
PROJECT DESCRIPTION |  | 143 | 143 | 0 |  | 2020-02-11 | 2020-02-11 |  | 2020-08-31 | 2020-08-31
Determine Needs |  | 56 | 56 | 2 |  | 2020-02-11 | 2020-02-11 |  | 2020-04-28 | 2020-04-28
PDE-10 | Environmental Planning Needs | 56 | 56 | 2 | 0% | 2020-02-11 | 2020-02-11 |  | 2020-04-28 | 2020-04-28
PDE-20 | Permitting Needs | 56 | 56 | 2 | 0% | 2020-02-11 | 2020-02-11 |  | 2020-04-28 | 2020-04-28
PDE-30 | Operations Needs | 10 | 10 | 48 | 100% | 2020-02-11 | 2020-02-11 |  | 2020-02-24 | 2020-02-24
PDE-35 | Water Rights Needs (Reg Items/Study) | 46 | 46 | 12 | 0% | 2020-02-11 | 2020-02-11 |  | 2020-04-14 | 2020-04-14
Components |  | 56 | 56 | 51 |  | 2020-04-01 | 2020-04-01 |  | 2020-06-18 | 2020-06-18
PDE-40 | Identify Alternatives for EIR/EIS | 30 | 30 | 9 | 0% | 2020-04-01 | 2020-04-01 |  | 2020-05-12 | 2020-05-12
PDE-45 | Identify Project-Level vs Program Components (Planning) | 47 | 47 | 51 | 0% | 2020-04-14 | 2020-04-14 |  | 2020-06-18 | 2020-06-18
PDE-47 | Identify Project-Level vs Program Components (Permitting) | 47 | 47 | 51 | 0% | 2020-04-14 | 2020-04-14 |  | 2020-06-18 | 2020-06-18
Develop Project Description |  | 85 | 85 | 2 |  | 2020-04-29 | 2020-04-29 |  | 2020-08-27 | 2020-08-27
PDE-50 | Develop Project Description Construction | 85 | 85 | 2 | 0% | 2020-04-29 | 2020-04-29 |  | 2020-08-27 | 2020-08-27
PDE-55 | Project Description Operations Criteria Complete (see Ops Tasks) | 0 | 0 | 55 | 0% |  |  |  | 2020-06-12 | 2020-06-12
Project Description Complete |  | 0 | 0 | 0 |  | 2020-08-31 | 2020-08-31 |  | 2020-08-31 | 2020-08-31
PDE-60 | Project Description | 0 | 0 | 0 | 0% |  |  |  | 2020-08-31 | 2020-08-31
OPERATIONS |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
OPERATIONS |  | 171 | 171 | 70 |  | 2020-01-02 | 2020-01-02 |  | 2020-08-31 | 2020-08-31
EB-00-00 | Environmental Benefits Modeling 1B | 171 | 171 | 70 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-08-31 | 2020-08-31
Value Planning Operations |  | 71 | 71 | 0 |  | 2020-01-02 | 2020-01-02 |  | 2020-04-10 | 2020-04-10
OP-005 | Value Planning Model | 37 | 37 | 0 | 100% | 2020-01-02 | 2020-01-02 |  | 2020-02-21 | 2020-02-21
OP-007 | Stony Creek Evaluation | 37 | 37 | 0 | 100% | 2020-01-02 | 2020-01-02 |  | 2020-02-21 | 2020-02-21
OP-010 | Shasta Exchanges Post-Processing and Draft TM | 37 | 37 | 0 | 100% | 2020-01-02 | 2020-01-02 |  | 2020-02-21 | 2020-02-21
OP-015 | Value Planning TM/Document | 20 | 20 | 0 | 100% | 2020-02-03 | 2020-02-03 |  | 2020-02-28 | 2020-02-28
OP-020 | Storage to Release Ratios Table | 15 | 15 | 0 | 0% | 2020-02-10 | 2020-02-10 |  | 2020-02-28 | 2020-02-28
OP-070 | Reclamation Feasibility Complete (Milestone) - Critical Staffing Need | 0 | 0 | 0 | 0% |  |  |  | 2020-04-10 | 10-Apr-20*
Refine Operational Parameters |  | 89 | 89 | 0 |  | 2020-02-10 | 2020-02-10 |  | 2020-06-12 | 2020-06-11
OP-110 | Confirm Notched Fremont Weir Approach | 44 | 44 | 0 | 0% | 2020-02-10 | 2020-02-10 |  | 2020-04-09 | 2020-06-11
OP-120 | Model Reclamation with No Storage Investment | 44 | 44 | 0 | 0% | 2020-04-10 | 2020-04-10 |  | 2020-06-11 | 2020-06-11
OP-130 | Confirm Shasta Exchange Approach | 44 | 44 | 0 | 0% | 2020-02-10 | 2020-02-10 |  | 2020-04-09 | 2020-06-11
OP-140 | Confirm Sutter Bypass Approach | 44 | 44 | 0 | 0% | 2020-02-10 | 2020-02-10 |  | 2020-04-09 | 2020-06-11
OP-150 | Confirm Voluntary Agreement Weir Notching Approach | 44 | 44 | 0 | 0% | 2020-02-10 | 2020-02-10 |  | 2020-04-09 | 2020-06-11
OP-160 | Confirm Delta Water Quality Approach | 44 | 44 | 0 | 0% | 2020-02-10 | 2020-02-10 |  | 2020-04-09 | 2020-06-11
OP-170 | Confirm Sacramento River Mortality Approach | 44 | 44 | 0 | 0% | 2020-02-10 | 2020-02-10 |  | 2020-04-09 | 2020-06-11
OP-180 | Determine Baseline | 30 | 30 | 14 | 0% | 2020-02-10 | 2020-02-10 |  | 2020-03-20 | 2020-05-30
OP-190 | Confirm CVP/SWP Integration Approach | 44 | 44 | 0 | 0% | 2020-02-10 | 2020-02-10 |  | 2020-04-09 | 2020-06-11
OP-200 | Confirm Participation Demands Updated | 44 | 44 | 0 | 0% | 2020-02-10 | 2020-02-10 |  | 2020-04-09 | 2020-06-11
OP-210 | Confirm Model Refinements | 44 | 44 | 0 | 0% | 2020-04-10 | 2020-04-10 |  | 2020-06-11 | 2020-06-11
OP-220 | Finalize Operational Criteria | 0 | 0 | 0 | 0% |  |  |  | 2020-06-12 | 2020-06-12
Full Operations Analysis |  | 104 | 104 | 405 |  | 2020-06-15 | 2020-06-15 |  | 2020-11-09 | 2020-11-09
OP-00-10 | Full Operations Analysis | 49 | 49 | 405 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-11-09 | 2020-11-09
OP-230 | CalSim | 104 | 104 | 0 | 0% | 2020-06-15 | 2020-06-15 |  | 2020-11-09 | 2020-11-09
OP-240 | DSM2-Hydro | 104 | 104 | 0 | 0% | 2020-06-15 | 2020-06-15 |  | 2020-11-09 | 2020-11-09
OP-250 | USRWQM | 104 | 104 | 17 | 0% | 2020-06-15 | 2020-06-15 |  | 2020-11-09 | 2020-11-09
OP-260 | SALMOD | 104 | 104 | 0 | 0% | 2020-06-15 | 2020-06-15 |  | 2020-11-09 | 2020-11-09
OP-270 | IOS | 104 | 104 | 17 | 0% | 2020-06-15 | 2020-06-15 |  | 2020-11-09 | 2020-11-09
OP-280 | DSM2-Qual | 104 | 104 | 17 | 0% | 2020-06-15 | 2020-06-15 |  | 2020-11-09 | 2020-11-09
OP-290 | OBAN | 104 | 104 | 6 | 0% | 2020-06-15 | 2020-06-15 |  | 2020-11-09 | 2020-11-09
OP-300 | Fish Mortality Models | 104 | 104 | 6 | 0% | 2020-06-15 | 2020-06-15 |  | 2020-11-09 | 2020-11-09
OP-310 | Power | 104 | 104 | 17 | 0% | 2020-06-15 | 2020-06-15 |  | 2020-11-09 | 2020-11-09
OP-315 | Economics | 104 | 104 | 17 | 0% | 2020-06-15 | 2020-06-15 |  | 2020-11-09 | 2020-11-09
OP-410 | Initial Modeling Evaluation | 45 | 45 | 0 | 0% | 2020-06-15 | 2020-06-15 |  | 2020-08-17 | 2020-08-17
OP-420 | Preliminary Results Available for Strategy Discussions | 0 | 0 | 0 | 0% |  |  |  | 2020-08-17 | 2020-08-17
OP-430 | Define and Finalize | 48 | 48 | 0 | 0% | 2020-08-18 | 2020-08-18 |  | 2020-10-23 | 2020-10-23
OP-440 | Power and Economics | 10 | 10 | 0 | 0% | 2020-10-26 | 2020-10-26 |  | 2020-11-06 | 2020-11-06
OP-450 | Final Operations Analysis's Output | 0 | 0 | 0 | 0% |  |  |  | 2020-11-09 | 2020-11-09
Term Sheets for Key Ops Agreements |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
OP-460 | Term Sheets for key Operational Agreements | 509 | 509 | 347 | 0% | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-06-30
Operations Plan, Ver 1 |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
OP-470 | Operations Plan, Version 1 | 509 | 509 | 347 | 0% | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
Coordination |  | 350 | 350 | 370 |  | 2020-07-14 | 2020-07-14 |  | 2021-11-29 | 2021-11-29
OP-00-20 | Ops/Modeling Coordination | 231 | 231 | 405 | 0% | 2020-11-10 | 2020-11-10 |  | 2021-10-07 | 2021-10-07
OP-320 | Documentation for EIR/EIS and BA/ITP | 40 | 40 | 17 | 0% | 2020-11-10 | 2020-11-10 |  | 2021-01-08 | 2021-01-08
OP-330 | Ongoing Support to EPP, Engineering, & Financial | 350 | 350 | 12 | 0% | 2020-07-14 | 2020-07-14 |  | 2021-11-29 | 2021-11-29
OP-340 | Cumulative and Climate Change | 62 | 62 | 0 | 0% | 2020-11-10 | 2020-11-10 |  | 2021-02-09 | 2021-02-09
OP-350 | Bridging Simulation | 126 | 126 | 117 | 0% | 2020-11-10 | 2020-11-10 |  | 2021-05-10 | 2021-05-10
OP-360 | Ops Support for Local Feasibility - Water Commission | 160 | 160 | 83 | 0% | 2020-11-10 | 2020-11-10 |  | 2021-06-28 | 2021-06-28
EIR/EIS |  | 548 | 548 | 308 |  | 2020-01-02 | 2020-01-02 |  | 2022-02-25 | 2022-02-25
EIR/EIS |  | 127 | 127 | 729 |  | 2020-01-02 | 2020-01-02 |  | 2020-06-29 | 2020-06-29
ENV-00-00 | On-Going Environmental Planning & Permitting | 127 | 127 | 729 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-06-29 | 2020-06-29
Work Plan & Outline |  | 224 | 224 | 0 |  | 2020-02-11 | 2020-02-11 |  | 2020-12-28 | 2020-12-28
EIR-001 | Prepare EIR/EIS Work Plan | 56 | 56 | 19 | 0% | 2020-02-11 | 2020-02-11 |  | 2020-04-28 | 2020-04-28
EIR-010 | Prepare Annotated Outline | 68 | 68 | 9 | 0% | 2020-05-13 | 2020-05-13 |  | 2020-08-18 | 2020-08-18
EIR-015 | Introduction Chapter/Recirculation Story | 68 | 68 | 9 | 0% | 2020-05-13 | 2020-05-13 |  | 2020-08-18 | 2020-08-18
EIR-021 | Prepare Draft EIR/EIS Project Description Chapter | 81 | 81 | 0 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-12-28 | 2020-12-28
Draft EIR/EIS |  | 221 | 221 | 464 |  | 2020-09-01 | 2020-09-01 |  | 2021-07-14 | 2021-07-15
EIR-00-00 | Prepare Revised Admin Draft EIR/EIS | 131 | 131 | 554 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-03-09 | 2021-03-09
EIR-00-10 | Prepare Revised Public Draft EIR/EIS | 139 | 139 | 465 | 0% | 2020-12-29 | 2020-12-29 |  | 2021-07-14 | 2021-07-14
EIR-019 | Prepare Revised Draft EIR/EIS Analysis (Construction) | 70 | 70 | 0 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-12-10 | 2020-12-10
EIR-020 | Prepare Revised Draft EIR/EIS Analysis (Operations) | 61 | 61 | 0 | 0% | 2020-12-11 | 2020-12-11 |  | 2021-03-09 | 2021-03-09
EIR-023 | Status Update to Board | 5 | 5 | 17 | 0% | 2021-01-11 | 2021-01-11 |  | 2021-01-15 | 2021-01-15
EIR-025 | Prepare Cumulative and Climate Change Sections | 20 | 20 | 0 | 0% | 2021-02-10 | 2021-02-10 |  | 2021-03-09 | 2021-03-09
EIR-026 | Prepare Complete Admin Draft EIR/EIS | 60 | 60 | 0 | 0% | 2020-12-29 | 2020-12-29 |  | 2021-03-23 | 2021-03-23
EIR-030 | Authority/Reclamation/Integration Review of Admin Draft EIR/EIS | 9 | 9 | 0 | 0% | 2021-03-24 | 2021-03-24 |  | 2021-04-05 | 2021-04-05
EIR-040 | Revise Draft EIR/EIS Based on Comments | 20 | 20 | 0 | 0% | 2021-04-06 | 2021-04-06 |  | 2021-05-03 | 2021-05-03
EIR-045 | Live Edit Meeting | 1 | 1 | 0 | 0% | 2021-05-04 | 2021-05-04 |  | 2021-05-04 | 2021-05-04
EIR-050 | Work Group & Legal Review of Revised Draft EIR/EIS | 22 | 22 | 0 | 0% | 2021-05-05 | 2021-05-05 |  | 2021-06-03 | 2021-06-04
EIR-060 | Resolve Work Group Comments | 15 | 15 | 0 | 0% | 2021-06-04 | 2021-06-07 |  | 2021-06-24 | 2021-06-25
EIR-065 | Live Edit Meeting | 2 | 2 | 0 | 0% | 2021-06-25 | 2021-06-28 |  | 2021-06-28 | 2021-06-29
EIR-067 | Final Editing, Formatting and Doc Production | 10 | 10 | 0 | 0% | 2021-06-29 | 2021-06-30 |  | 2021-07-13 | 2021-07-14
EIR-070 | Authority Approval of Release Revised Draft EIR/EIS | 1 | 1 | 0 | 0% | 2021-07-14 | 2021-07-15 |  | 2021-07-14 | 2021-07-15
EIR-080 | Release Revised Draft EIR/EIS and Issue Public Notices | 0 | 0 | 0 | 0% |  |  |  | 2021-07-14 | 2021-07-15
Public Review |  | 60 | 60 | 0 |  | 2021-07-15 | 2021-07-16 |  | 2021-09-12 | 2021-09-13
EIR-090 | Public Review Period | 60 | 60 | 0 | 0% | 2021-07-15 | 2021-07-16 |  | 2021-09-12 | 2021-09-13
Summary Report |  | 67 | 67 | 0 |  | 2021-08-30 | 2021-08-30 |  | 2021-12-03 | 2021-12-03
EIR-095 | Categorize and Sort Comments by Topic | 20 | 20 | 0 | 0% | 2021-08-30 | 2021-08-30 |  | 2021-09-27 | 2021-09-27
EIR-100 | Approach to Response to Comments | 15 | 15 | 0 | 0% | 2021-09-28 | 2021-09-28 |  | 2021-10-18 | 2021-10-18
EIR-105 | Authority/Reclamation/Legal Review | 5 | 5 | 0 | 0% | 2021-10-19 | 2021-10-19 |  | 2021-10-25 | 2021-10-25
EIR-110 | Prepare Summary Report | 20 | 20 | 0 | 0% | 2021-10-26 | 2021-10-26 |  | 2021-11-22 | 2021-11-22
EIR-115 | Work Group & Legal Review of Summary Report | 5 | 5 | 0 | 0% | 2021-11-23 | 2021-11-23 |  | 2021-12-01 | 2021-12-01
EIR-117 | Live Edit Meeting of Summary Report | 1 | 1 | 0 | 0% | 2021-12-02 | 2021-12-02 |  | 2021-12-02 | 2021-12-02
EIR-120 | Draft EIR Summary Report Submittal to CWC | 0 | 0 | 0 | 0% |  |  |  | 2021-12-03 | 2021-12-03
Response to Comments |  | 90 | 90 | 308 |  | 2021-10-19 | 2021-10-19 |  | 2022-02-25 | 2022-02-25
EIR-00-RC | Response to Comments Amend 2 | 51 | 51 | 347 | 0% | 2021-10-19 | 2021-10-19 |  | 2021-12-31 | 2021-12-31
EIR-130 | Begin Preparation of Final EIR/EIS Including Response to Comments | 90 | 90 | 193 | 0% | 2021-10-19 | 2021-10-19 |  | 2022-02-25 | 2022-02-25
PERMITTING |  | 783 | 783 | 0 |  | 2020-04-14 | 2020-04-14 |  | 2023-05-09 | 2023-05-12
Early Mitigation |  | 338 | 338 | 347 |  | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
EM-00-10 | Early Mitigation | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
Biological Assessment |  | 307 | 307 | 476 |  | 2020-04-14 | 2020-04-14 |  | 2021-06-28 | 2021-06-28
BA-00-10 | Biological Assessment/Biological Opinion | 188 | 188 | 476 | 0% | 2020-10-01 | 2020-10-01 |  | 2021-06-28 | 2021-06-28
BA-00-20 | Mitigation Planning | 150 | 150 | 535 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-04-05 | 2021-04-05
BA-00-30 | Adaptive Management Plan | 138 | 138 | 547 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-03-18 | 2021-03-18
BA-001 | Initial Desktop Analysis | 60 | 60 | 24 | 0% | 2020-10-01 | 2020-10-01 |  | 2020-12-28 | 2020-12-28
BA-010 | Mitigation Planning | 202 | 202 | 16 | 0% | 2020-04-14 | 2020-04-14 |  | 2021-01-29 | 2021-01-29
BA-015 | Adaptive Management Plan | 202 | 202 | 21 | 0% | 2020-04-14 | 2020-04-14 |  | 2021-01-29 | 2021-01-29
BA-019 | Confirm Federal Scope of Action (ESA) | 38 | 38 | 72 | 0% | 2020-04-14 | 2020-04-14 |  | 2020-06-05 | 2020-06-05
BA-020 | Permitting Construction Project Description | 16 | 16 | 72 | 0% | 2020-06-08 | 2020-06-08 |  | 2020-06-29 | 2020-06-29
BA-022 | Permitting Operations Project Description | 20 | 20 | 6 | 0% | 2020-10-20 | 2020-10-20 |  | 2020-11-16 | 2020-11-16
BA-024 | Prepare Construction Analysis | 97 | 97 | 7 | 0% | 2020-10-01 | 2020-10-01 |  | 2021-02-18 | 2021-02-18
BA-025 | Prepare Operations Analysis | 60 | 60 | 6 | 0% | 2020-11-17 | 2020-11-17 |  | 2021-02-12 | 2021-02-12
BA-030 | Finalize Admin Draft BA | 20 | 20 | 7 | 0% | 2021-02-19 | 2021-02-19 |  | 2021-03-18 | 2021-03-18
BA-032 | Submit Final Admin Draft BA | 0 | 0 | 7 | 0% |  |  |  | 2021-03-18 | 2021-03-18
BA-035 | Independent Review Draft BA | 30 | 30 | 11 | 0% | 2021-03-19 | 2021-03-19 |  | 2021-04-17 | 2021-04-17
BA-055 | Reclamation, Legal, and Work Group Review | 30 | 30 | 11 | 0% | 2021-03-19 | 2021-03-19 |  | 2021-04-17 | 2021-04-17
BA-057 | Revise Admin Draft BA | 30 | 30 | 8 | 0% | 2021-04-19 | 2021-04-19 |  | 2021-05-28 | 2021-05-28
BA-060 | Submit Revised Admin Draft BA to Reclamation | 0 | 0 | 23 | 0% |  |  |  | 2021-05-28 | 2021-05-28
BA-075 | Final Reclamation and Solicitor Office Review | 30 | 30 | 36 | 0% | 2021-05-29 | 2021-05-29 |  | 2021-06-27 | 2021-06-27
BA-100 | Reclamation Submit BA to USFWS & NMFS | 0 | 0 | 25 | 0% |  |  |  | 2021-06-28 | 2021-06-28
BO Incidental Task Authorization |  | 135 | 135 | 36 |  | 2021-06-28 | 2021-06-28 |  | 2021-11-09 | 2021-11-09
BA-1110 | BO Incidental Take Authorization | 135 | 135 | 36 | 0% | 2021-06-28 | 2021-06-28 |  | 2021-11-09 | 2021-11-09
ITP - CESA (Se 2081) Operations |  | 300 | 300 | 364 |  | 2020-10-01 | 2020-10-01 |  | 2021-12-07 | 2021-12-07
CES-00-10 | Incidental Take Permit (ITP) Operations | 300 | 300 | 364 | 0% | 2020-10-01 | 2020-10-01 |  | 2021-12-07 | 2021-12-07
CES-190 | Prepare Operations Analysis | 30 | 30 | 6 | 0% | 2021-01-12 | 2021-01-12 |  | 2021-02-22 | 2021-02-22
CES-200 | Additional Mitigation Planning | 30 | 30 | 6 | 0% | 2021-02-23 | 2021-02-23 |  | 2021-04-05 | 2021-04-05
CES-210 | Prepare Draft ITP Application Operations | 60 | 60 | 8 | 0% | 2021-06-01 | 2021-06-01 |  | 2021-08-24 | 2021-08-24
CES-220 | Legal Review of Draft ITP App | 30 | 30 | 10 | 0% | 2021-08-25 | 2021-08-25 |  | 2021-09-23 | 2021-09-23
CES-230 | Work Group Review of Draft ITP App | 30 | 30 | 10 | 0% | 2021-08-25 | 2021-08-25 |  | 2021-09-23 | 2021-09-23
CES-240 | Revise Draft ITP Application Operations | 20 | 20 | 6 | 0% | 2021-09-23 | 2021-09-23 |  | 2021-10-21 | 2021-10-21
CES-250 | Authority Board Approval of ITP App | 30 | 30 | 6 | 0% | 2021-10-21 | 2021-10-21 |  | 2021-12-06 | 2021-12-06
CES-260 | Submit ITP Application to CDFW | 0 | 0 | 6 | 0% |  |  |  | 2021-12-07 | 2021-12-07
ITP - CESA (Se 2081) Construction |  | 300 | 300 | 6 |  | 2020-10-01 | 2020-10-01 |  | 2021-12-07 | 2021-12-07
CES-015 | Initial Desktop Analysis | 30 | 30 | 86 | 0% | 2020-10-01 | 2020-10-01 |  | 2020-11-11 | 2020-11-11
CES-020 | Prepare Terrestrial Analysis | 30 | 30 | 86 | 0% | 2020-11-12 | 2020-11-12 |  | 2020-12-28 | 2020-12-28
CES-025 | Mitigation Planning | 30 | 30 | 86 | 0% | 2020-12-29 | 2020-12-29 |  | 2021-02-09 | 2021-02-09
CES-030 | Prepare Draft ITP Application Construction | 60 | 60 | 8 | 0% | 2021-06-01 | 2021-06-01 |  | 2021-08-24 | 2021-08-24
CES-040 | Legal Review of Draft ITP App | 30 | 30 | 10 | 0% | 2021-08-25 | 2021-08-25 |  | 2021-09-23 | 2021-09-23
CES-060 | Work Group Review of Draft ITP App | 30 | 30 | 10 | 0% | 2021-08-25 | 2021-08-25 |  | 2021-09-23 | 2021-09-23
CES-070 | Revise Draft ITP Application Construction | 20 | 20 | 6 | 0% | 2021-09-23 | 2021-09-23 |  | 2021-10-21 | 2021-10-21
CES-080 | Authority Board Approval of ITP App | 30 | 30 | 6 | 0% | 2021-10-21 | 2021-10-21 |  | 2021-12-06 | 2021-12-06
CES-090 | Submit ITP Application to CDFW | 0 | 0 | 6 | 0% |  |  |  | 2021-12-07 | 2021-12-07
Section 106 |  | 317 | 317 | 10 |  | 2020-09-01 | 2020-09-01 |  | 2021-12-02 | 2021-12-02
106-000 | Confirmation of Section 106 Federal Lead Agency | 0 | 0 | 22 | 0% |  |  |  | 2020-09-08 | 2020-09-08
106-001 | Prepare SHPO Initiation Package | 20 | 20 | 7 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-09-29 | 2020-09-29
106-002 | Authority/Reclamation/Integration Reviews | 10 | 10 | 7 | 0% | 2020-09-30 | 2020-09-30 |  | 2020-10-13 | 2020-10-13
106-003 | Management/Work Group Reviews | 10 | 10 | 7 | 0% | 2020-10-14 | 2020-10-14 |  | 2020-10-27 | 2020-10-27
106-004 | Revisions | 10 | 10 | 7 | 0% | 2020-10-28 | 2020-10-28 |  | 2020-11-10 | 2020-11-10
106-005 | Reclamation Submits to SHPO | 0 | 0 | 7 | 0% |  |  |  | 2020-11-17 | 2020-11-17
106-006 | SHPO Review and Comments | 30 | 30 | 13 | 0% | 2020-11-18 | 2020-11-18 |  | 2020-12-17 | 2020-12-17
106-021 | Prepare Consultation Information Package | 15 | 15 | 8 | 0% | 2020-12-17 | 2020-12-17 |  | 2021-01-11 | 2021-01-11
106-022 | Authority/Reclamation/Integration Reviews | 10 | 10 | 8 | 0% | 2021-01-11 | 2021-01-11 |  | 2021-01-25 | 2021-01-25
106-023 | Management/Work Group Reviews | 10 | 10 | 8 | 0% | 2021-01-25 | 2021-01-25 |  | 2021-02-08 | 2021-02-08
106-024 | Revisions | 10 | 10 | 8 | 0% | 2021-02-08 | 2021-02-08 |  | 2021-02-22 | 2021-02-22
106-025 | Reclamation Distributes to SHPO and Invited Consulting Parties | 5 | 5 | 19 | 0% | 2021-02-22 | 2021-02-22 |  | 2021-03-01 | 2021-03-01
106-026 | Parties Accept Invitation for Consulting Party Status | 30 | 30 | 39 | 0% | 2021-03-02 | 2021-03-02 |  | 2021-03-31 | 2021-03-31
106-032 | Arrange Meeting Logistics and Prepare Materials | 20 | 20 | 8 | 0% | 2021-02-22 | 2021-02-22 |  | 2021-03-22 | 2021-03-22
106-033 | Conduct Meetings | 10 | 10 | 19 | 0% | 2021-03-01 | 2021-03-01 |  | 2021-03-15 | 2021-03-15
106-042 | Authority/Reclamation/Integration Reviews | 10 | 10 | 8 | 0% | 2021-03-30 | 2021-03-30 |  | 2021-04-13 | 2021-04-13
106-043 | Management/Work Group Reviews | 10 | 10 | 8 | 0% | 2021-04-13 | 2021-04-13 |  | 2021-04-27 | 2021-04-27
106-044 | Revisions | 10 | 10 | 24 | 0% | 2021-04-27 | 2021-04-27 |  | 2021-05-11 | 2021-05-11
106-052 | Circulate Draft PA to SHPO and Consulting Parties | 5 | 5 | 8 | 0% | 2021-04-27 | 2021-04-27 |  | 2021-05-04 | 2021-05-04
106-053 | Deadline for Comments on Draft PA | 30 | 30 | 12 | 0% | 2021-05-05 | 2021-05-05 |  | 2021-06-03 | 2021-06-03
106-061 | Prepare Draft Final PA | 20 | 20 | 8 | 0% | 2021-06-03 | 2021-06-03 |  | 2021-07-01 | 2021-07-01
106-062 | Authority/Reclamation/Integration Reviews | 10 | 10 | 8 | 0% | 2021-07-01 | 2021-07-01 |  | 2021-07-16 | 2021-07-16
106-063 | Management/Work Group Reviews | 10 | 10 | 8 | 0% | 2021-07-16 | 2021-07-16 |  | 2021-07-30 | 2021-07-30
106-064 | Revisions | 10 | 10 | 8 | 0% | 2021-07-30 | 2021-07-30 |  | 2021-08-13 | 2021-08-13
106-072 | Circulate Draft Final PA to SHPO and Consulting Parties | 5 | 5 | 8 | 0% | 2021-08-13 | 2021-08-13 |  | 2021-08-20 | 2021-08-20
106-073 | Deadline for Comments on Draft Final PA | 30 | 30 | 12 | 0% | 2021-08-21 | 2021-08-21 |  | 2021-09-19 | 2021-09-19
106-081 | Prepare Final PA | 15 | 15 | 10 | 0% | 2021-09-20 | 2021-09-20 |  | 2021-10-08 | 2021-10-08
106-082 | Authority/Reclamation/Integration Reviews | 10 | 10 | 10 | 0% | 2021-10-11 | 2021-10-11 |  | 2021-10-22 | 2021-10-22
106-083 | Management/Work Group Reviews | 10 | 10 | 10 | 0% | 2021-10-25 | 2021-10-25 |  | 2021-11-05 | 2021-11-05
106-084 | Revisions | 10 | 10 | 10 | 0% | 2021-11-08 | 2021-11-08 |  | 2021-11-19 | 2021-11-19
106-091 | Consult with SHPO and Consulting Parties on Final PA | 5 | 5 | 11 | 0% | 2021-11-22 | 2021-11-22 |  | 2021-11-30 | 2021-11-30
106-092 | Circulate Final PA to SHPO and Consulting Parties for Signatures | 5 | 5 | 10 | 0% | 2021-11-22 | 2021-11-22 |  | 2021-11-30 | 2021-11-30
106-093 | Deadline for Signatures on Final PA | 0 | 0 | 14 | 0% |  |  |  | 2021-12-02 | 2021-12-02
Water Rights |  | 685 | 685 | 0 |  | 2020-09-01 | 2020-09-01 |  | 2023-05-09 | 2023-05-12
WR-00-00 | Water Rights | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
WR-005 | Water Availability Analysis & Planning/Coordination with SWRCB | 210 | 210 | 11 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-06-29 | 2021-06-29
WR-025 | Prepare Water Right Application | 121 | 121 | 0 | 0% | 2021-07-15 | 2021-07-16 |  | 2022-01-06 | 2022-01-07
WR-035 | QA/QC and Legal Review of Draft Water Right Application | 15 | 15 | 0 | 0% | 2022-01-07 | 2022-01-10 |  | 2022-01-27 | 2022-01-28
WR-045 | Revise Draft Water Right Application | 25 | 25 | 0 | 0% | 2022-01-28 | 2022-01-31 |  | 2022-03-03 | 2022-03-04
WR-055 | Work Group Review of Draft Water Right Application | 10 | 10 | 0 | 0% | 2022-03-04 | 2022-03-07 |  | 2022-03-17 | 2022-03-18
WR-065 | Resolve Work Group Comments | 10 | 10 | 0 | 0% | 2022-03-18 | 2022-03-21 |  | 2022-03-31 | 2022-04-01
WR-075 | Authority Approval of Water Right Application, Submit to SWRCB | 1 | 1 | 0 | 0% | 2022-04-01 | 2022-04-04 |  | 2022-04-01 | 2022-04-04
WR-085 | Submit Water Right Application | 0 | 0 | 0 | 0% |  |  |  | 2022-04-01 | 2022-04-04
WR-095 | SWRCB Review of Water Right Application | 60 | 60 | 0 | 0% | 2022-04-02 | 2022-04-05 |  | 2022-05-31 | 2022-06-03
WR-105 | Receive Protests to Application | 44 | 44 | 0 | 0% | 2022-05-31 | 2022-06-03 |  | 2022-08-02 | 2022-08-05
WR-115 | Resolve Protests and Schedule Protest Hearing | 80 | 80 | 0 | 0% | 2022-08-02 | 2022-08-05 |  | 2022-11-23 | 2022-11-30
WR-125 | Notice Water Rights Hearing | 22 | 22 | 0 | 0% | 2022-11-23 | 2022-11-30 |  | 2022-12-28 | 2023-01-03
WR-135 | Conduct In-House Mock Water Right Hearing | 15 | 15 | 7 | 0% | 2022-12-28 | 2023-01-03 |  | 2023-01-19 | 2023-01-24
WR-145 | Conduct Water Right Hearing | 1 | 1 | 0 | 0% | 2023-01-30 | 2023-02-02 |  | 2023-01-31 | 2023-02-03
WR-155 | Negotiate Permit Terms | 44 | 44 | 0 | 0% | 2023-01-31 | 2023-02-03 |  | 2023-04-03 | 2023-04-06
WR-165 | SWRCB Prepare Draft Permit and CEQA Findings | 21 | 21 | 0 | 0% | 2023-04-03 | 2023-04-06 |  | 2023-05-02 | 2023-05-05
WR-175 | SWRCB Issue Water Right Permit | 5 | 5 | 0 | 0% | 2023-05-02 | 2023-05-05 |  | 2023-05-09 | 2023-05-12
WR-185 | Water Right Permit | 0 | 0 | 0 | 0% |  |  |  | 2023-05-09 | 2023-05-12
Section 404 |  | 419 | 419 | 364 |  | 2020-04-14 | 2020-04-14 |  | 2021-12-07 | 2021-12-07
404-00-00 | Section 404 Application | 300 | 300 | 364 | 0% | 2020-10-01 | 2020-10-01 |  | 2021-12-07 | 2021-12-07
404-001 | Agreement with Reclamation for LEDPA Analysis | 15 | 15 | 22 | 0% | 2020-04-14 | 2020-04-14 |  | 2020-05-04 | 2020-05-04
404-003 | USACE LEDPA & NEPA , 404/408 and WD Approach on Secion 404 Application | 88 | 88 | 22 | 0% | 2020-05-05 | 2020-05-05 |  | 2020-09-08 | 2020-09-08
404-010 | Desktop Wetland Delineation Analysis (includes Waters of the State) | 150 | 150 | 11 | 0% | 2020-10-01 | 2020-10-01 |  | 2021-05-04 | 2021-05-04
404-020 | Submit Delineation to USACE | 0 | 0 | 11 | 0% |  |  |  | 2021-05-05 | 2021-05-05
404-025 | Pre-Application Meeting | 1 | 1 | 54 | 0% | 2021-06-01 | 2021-06-01 |  | 2021-06-02 | 2021-06-02
404-030 | Preliminary Wetland Delineation Acceptance | 90 | 90 | 15 | 0% | 2021-05-06 | 2021-05-06 |  | 2021-08-03 | 2021-08-03
404-035 | Prepare Compensatory Mitigation Plan | 161 | 161 | 6 | 0% | 2021-02-23 | 2021-02-23 |  | 2021-10-08 | 2021-10-08
404-050 | Prepare Draft 404 Application | 42 | 42 | 11 | 0% | 2021-08-03 | 2021-08-03 |  | 2021-10-01 | 2021-10-01
404-060 | Authority/Integration/Work Group Review of Draft 404 Application | 20 | 20 | 6 | 0% | 2021-10-11 | 2021-10-11 |  | 2021-11-05 | 2021-11-05
404-070 | Prepare Final 404 Application | 20 | 20 | 6 | 0% | 2021-11-08 | 2021-11-08 |  | 2021-12-07 | 2021-12-07
404-120 | Submit 404 Application | 0 | 0 | 6 | 0% |  |  |  | 2021-12-07 | 2021-12-07
Section 408 |  | 505 | 505 | 180 |  | 2020-09-01 | 2020-09-01 |  | 2022-08-26 | 2022-08-26
408-00-00 | Section 408/Encroachment Permit | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
408-005 | Coordinate with CVFPB and USACE on Section 408/Encroachment Permit | 20 | 20 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-09-29 | 2020-09-29
408-010 | Assume Start of 50% Design of 408 Jurisdictional Features | 0 | 0 | 180 | 0% |  |  |  | 2021-07-01 | 2021-07-01
408-130 | Prepare Draft Encroachment Permit/408 Request w/Engineering Team | 129 | 129 | 180 | 0% | 2021-07-05 | 2021-07-05 |  | 2022-01-06 | 2022-01-06
408-135 | Continue Draft Encroachment Permit/408 Request w/Engineering Team | 124 | 124 | 180 | 0% | 2022-01-07 | 2022-01-07 |  | 2022-06-30 | 2022-06-30
408-140 | Authority/Integration/Work Group Review of Draft | 20 | 20 | 180 | 0% | 2022-07-01 | 2022-07-01 |  | 2022-07-29 | 2022-07-29
408-150 | Prepare Encroachment Permit/408 Request | 20 | 20 | 180 | 0% | 2022-08-01 | 2022-08-01 |  | 2022-08-26 | 2022-08-26
408-160 | Submit Encroachment Permit/408 Request | 0 | 0 | 180 | 0% |  |  |  | 2022-08-26 | 2022-08-26
Section 401 Water Quality |  | 311 | 311 | 11 |  | 2020-09-09 | 2020-09-09 |  | 2021-11-30 | 2021-11-30
401-00-00 | Section 401 Water Quality | 311 | 311 | 11 | 0% | 2020-09-09 | 2020-09-09 |  | 2021-11-30 | 2021-11-30
401-120 | Coordinate with RWQCB and SWRCB | 84 | 84 | 156 | 0% | 2020-09-09 | 2020-09-09 |  | 2021-01-08 | 2021-01-08
401-130 | Prepare Draft 401 Application | 42 | 42 | 11 | 0% | 2021-08-03 | 2021-08-03 |  | 2021-10-01 | 2021-10-01
401-140 | Authority/Integration/Work Group Review of Draft 401 | 20 | 20 | 11 | 0% | 2021-10-01 | 2021-10-01 |  | 2021-10-29 | 2021-10-29
401-150 | Prepare Final 401 Application | 20 | 20 | 11 | 0% | 2021-10-29 | 2021-10-29 |  | 2021-11-30 | 2021-11-30
401-160 | Submit 401 Application | 0 | 0 | 11 | 0% |  |  |  | 2021-11-30 | 2021-11-30
FEASIBILITY-LEVEL GEOTECH |  | 85 | 85 | 539 |  | 2020-11-30 | 2020-11-30 |  | 2021-03-30 | 2021-03-30
Field Investigation |  | 85 | 85 | 539 |  | 2020-11-30 | 2020-11-30 |  | 2021-03-30 | 2021-03-30
GSR-015 | Geotechnical Field Monitoring | 85 | 85 | 539 | 0% | 2020-11-30 | 2020-11-30 |  | 2021-03-30 | 2021-03-30
Note on B32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Removed as a deliverable

## Lee
Sites Monthly Project Schedule Update |  |  |  |  | Data Date: | 2020-04-30
Activity ID | Activity Name | Ori Dur | Remaining Dur | Total Float | Physical % Comp | Baseline Start | Current Start | Actual Start | Baseline Finish | Current Finish | Actual Finish
Lee Frederiksen |  | 595 | 595 | 261 |  | 2020-01-02 | 2020-01-02 |  | 2022-05-03 | 2022-05-03
VALUE PLANNING |  | 73 | 73 | 0 |  | 2020-01-02 | 2020-01-02 |  | 2020-04-13 | 2020-04-13
Value Planning Analysis |  | 44 | 44 | 4 |  | 2020-01-02 | 2020-01-02 |  | 2020-03-03 | 2020-03-03
VP-001 | Refine Value Planning Options | 3 | 3 | 4 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-01-06 | 2020-01-06
VP-002 | Screen Value Planning Options | 20 | 20 | 4 | 0% | 2020-01-07 | 2020-01-07 |  | 2020-02-03 | 2020-02-03
VP-013 | Prepare Costs For Value Planning Alternatives | 15 | 15 | 4 | 0% | 2020-02-04 | 2020-02-04 |  | 2020-02-24 | 2020-02-24
VP-015 | Screen Alternatives | 2 | 2 | 4 | 0% | 2020-03-02 | 2020-03-02 |  | 2020-03-03 | 2020-03-03
VP-020 | Recommend Preferred Option | 0 | 0 | 4 | 0% |  |  |  | 2020-03-03 | 2020-03-03
Value Planning Report |  | 42 | 42 | 0 |  | 2020-02-14 | 2020-02-14 |  | 2020-04-13 | 2020-04-13
VP-025 | Value Planning Draft Report | 21 | 21 | 0 | 0% | 2020-02-14 | 2020-02-14 |  | 2020-03-13 | 2020-03-13
VP-070 | Select and Confirm Preferred Project | 21 | 21 | 0 | 0% | 2020-03-16 | 2020-03-16 |  | 2020-04-13 | 2020-04-13
VP-090 | Value Planning Final Report | 17 | 17 | 0 | 0% | 2020-03-20 | 2020-03-20 |  | 2020-04-13 | 2020-04-13
Preferred Project |  | 0 | 0 | 0 |  | 2020-04-13 | 2020-04-13 |  | 2020-04-13 | 2020-04-13
VP-095 | Approve Preferred Project | 0 | 0 | 0 | 0% |  |  |  | 2020-04-13 | 2020-04-13
PROJECT DESCRIPTION |  | 141 | 141 | 687 |  | 2020-02-11 | 2020-02-11 |  | 2020-08-27 | 2020-08-27
PROJECT DESCRIPTION |  | 141 | 141 | 687 |  | 2020-02-11 | 2020-02-11 |  | 2020-08-27 | 2020-08-27
PDE-00-00 | Project Description | 141 | 141 | 687 | 0% | 2020-02-11 | 2020-02-11 |  | 2020-08-27 | 2020-08-27
Determine Needs |  | 46 | 46 | 12 |  | 2020-02-11 | 2020-02-11 |  | 2020-04-14 | 2020-04-14
PDE-25 | Engineering Needs | 46 | 46 | 12 | 0% | 2020-02-11 | 2020-02-11 |  | 2020-04-14 | 2020-04-14
Components |  | 30 | 30 | 47 |  | 2020-05-13 | 2020-05-13 |  | 2020-06-24 | 2020-06-24
PDE-42 | Determine Preliminary Project Construction Sequencing | 30 | 30 | 47 | 0% | 2020-05-13 | 2020-05-13 |  | 2020-06-24 | 2020-06-24
FEASIBILITY-LEVEL GEOTECH |  | 449 | 449 | 348 |  | 2020-03-25 | 2020-03-25 |  | 2021-12-30 | 2021-12-30
FEASIBILITY-LEVEL GEOTECH |  | 112 | 112 | 685 |  | 2020-03-25 | 2020-03-25 |  | 2020-08-31 | 2020-08-31
GPP-00-00 | Geotech Permitting & Planning -1B | 112 | 112 | 685 | 0% | 2020-03-25 | 2020-03-25 |  | 2020-08-31 | 2020-08-31
Geotechnical Permitting & Planning |  | 173 | 173 | 11 |  | 2020-03-25 | 2020-03-25 |  | 2020-11-25 | 2020-11-25
GSR-000 | Identify near-term Geotechnical Needs | 112 | 112 | 11 | 0% | 2020-03-25 | 2020-03-25 |  | 2020-08-31 | 2020-08-31
GSR-010 | Geotechnical Permitting & Planning, Right of Access | 61 | 61 | 11 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-11-25 | 2020-11-25
Field Investigation |  | 85 | 85 | 11 |  | 2020-11-30 | 2020-11-30 |  | 2021-03-30 | 2021-03-30
GSR-020 | Conduct Geotechnical Field Investigation | 85 | 85 | 11 | 0% | 2020-11-30 | 2020-11-30 |  | 2021-03-30 | 2021-03-30
Data Evaluation and Reporting |  | 234 | 234 | 348 |  | 2021-01-29 | 2021-01-29 |  | 2021-12-30 | 2021-12-30
GSR-030 | Data Evaluation and Prepare Geotechnical Data Reports | 107 | 107 | 11 | 0% | 2021-01-29 | 2021-01-29 |  | 2021-06-29 | 2021-06-29
GSR-040 | Data Gap Assessment and Preliminary Planning for Design Level Inv for Preferred Alt | 149 | 149 | 348 | 0% | 2021-05-28 | 2021-05-28 |  | 2021-12-30 | 2021-12-30
ENGINEERING |  | 536 | 536 | 261 |  | 2020-03-24 | 2020-03-24 |  | 2022-05-03 | 2022-05-03
Support of Project Description |  | 449 | 449 | 348 |  | 2020-03-24 | 2020-03-24 |  | 2021-12-30 | 2021-12-30
ENG-110 | Engineering Consultants Brought On Board (complete prior to Sept 1) | 0 | 0 | 11 | 0% |  |  |  | 2020-03-24 | 2020-03-24
ENG-120 | Coordination of CADD and GIS Standards | 5 | 5 | 11 | 0% | 2020-03-25 | 2020-03-25 |  | 2020-03-31 | 2020-03-31
ENG-130 | Coordination to Identify Alternatives for EIR/EIS & Related Studies | 5 | 5 | 9 | 0% | 2020-03-25 | 2020-03-25 |  | 2020-03-31 | 2020-03-31
ENG-140 | Coordination to Finalize Storage & Conveyance Capacities | 5 | 5 | 22 | 0% | 2020-03-25 | 2020-03-25 |  | 2020-03-31 | 2020-03-31
ENG-145 | Coordination with Reclamantion on Approach | 5 | 5 | 0 | 0% | 2020-03-25 | 2020-03-25 |  | 2020-03-31 | 2020-03-31
ENG-150 | Gather Data from Prior Draft EIR/EIS | 10 | 10 | 15 | 0% | 2020-03-25 | 2020-03-25 |  | 2020-04-07 | 2020-04-07
ENG-160 | Prepare Project Base Map | 20 | 20 | 0 | 0% | 2020-04-01 | 2020-04-01 |  | 2020-04-28 | 2020-04-28
ENG-170 | Prepare Basis of Feasibility Design | 22 | 22 | 0 | 0% | 2020-04-01 | 2020-04-01 |  | 2020-04-30 | 2020-04-30
ENG-180 | Conduct Field Reviews (as needed) | 5 | 5 | 17 | 0% | 2020-04-01 | 2020-04-01 |  | 2020-04-07 | 2020-04-07
ENG-190 | Prepare Preliminary Feasibility Level Design | 55 | 55 | 0 | 0% | 2020-05-01 | 2020-05-01 |  | 2020-07-20 | 2020-07-20
ENG-193 | Develop Hydaulic Model | 30 | 30 | 25 | 0% | 2020-05-01 | 2020-05-01 |  | 2020-06-12 | 2020-06-12
ENG-195 | Prepare Final Feasibility Level Design | 30 | 30 | 0 | 0% | 2020-07-21 | 2020-07-21 |  | 2020-08-31 | 2020-08-31
ENG-200 | Develop CADD Drawings of Key Features | 85 | 85 | 0 | 0% | 2020-05-01 | 2020-05-01 |  | 2020-08-31 | 2020-08-31
ENG-210 | Provide Information on Key Project Features & Facilities | 21 | 21 | 80 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-09-30 | 2020-09-30
ENG-220 | Convert Drawings to GIS Geodatabase File Format to Support Environmental & Permitting | 21 | 21 | 7 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-09-30 | 2020-09-30
ENG-230 | Support to Environmental and Permitting Team | 316 | 316 | 348 | 0% | 2020-10-01 | 2020-10-01 |  | 2021-12-30 | 2021-12-30
ENG-233 | Engineering Support for Alternative A | 46 | 46 | 639 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-11-04 | 2020-11-04
ENG-236 | Engineering Support for Modified Alternative A | 46 | 46 | 639 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-11-04 | 2020-11-04
Cost Estimate, Feasibility, Constructability |  | 424 | 424 | 261 |  | 2020-09-01 | 2020-09-01 |  | 2022-05-03 | 2022-05-03
ENG-240 | Identify Project Objectives | 11 | 11 | 80 | 0% | 2020-10-01 | 2020-10-01 |  | 2020-10-15 | 2020-10-15
ENG-250 | Feasibility Project Description | 0 | 0 | 80 | 0% |  |  |  | 2020-10-15 | 2020-10-15
ENG-260 | Obtain Operations Simulation Results of Preferred Option | 0 | 0 | 88 | 0% |  |  |  | 2020-11-16 | 2020-11-16
ENG-270 | Develop Costs Associated with Mitigation Measures | 15 | 15 | 80 | 0% | 2020-10-16 | 2020-10-16 |  | 2020-11-05 | 2020-11-05
ENG-280 | Develop Class 4 Cost Estimate | 25 | 25 | 108 | 0% | 2020-11-17 | 2020-11-17 |  | 2020-12-23 | 2020-12-23
ENG-290 | Risk and Uncertainty Assessment | 20 | 20 | 80 | 0% | 2020-11-06 | 2020-11-06 |  | 2020-12-07 | 2020-12-07
ENG-300 | Coordinate with Operations to Confirm Project Benefits | 45 | 45 | 88 | 0% | 2020-11-17 | 2020-11-17 |  | 2021-01-22 | 2021-01-22
ENG-310 | Project Benefits Consist with the Ops Plan | 40 | 40 | 80 | 0% | 2020-12-08 | 2020-12-08 |  | 2021-02-03 | 2021-02-03
ENG-320 | Cost Allocation | 20 | 20 | 80 | 0% | 2021-02-04 | 2021-02-04 |  | 2021-03-03 | 2021-03-03
ENG-330 | Technical Feasibility | 20 | 20 | 100 | 0% | 2021-02-04 | 2021-02-04 |  | 2021-03-03 | 2021-03-03
ENG-340 | Obtain the Finding of Env Feasibility with Mitigation | 5 | 5 | 82 | 0% | 2021-05-04 | 2021-05-04 |  | 2021-05-10 | 2021-05-10
ENG-370 | Constructability | 20 | 20 | 80 | 0% | 2021-03-04 | 2021-03-04 |  | 2021-03-31 | 2021-03-31
ENG-400 | Develop DSOD Engagement Plan | 96 | 96 | 11 | 0% | 2021-07-15 | 2021-07-15 |  | 2021-11-30 | 2021-11-30
ENG-404 | Coordinate on a Geotechnical Investigation Plan | 96 | 96 | 11 | 0% | 2021-07-15 | 2021-07-15 |  | 2021-11-30 | 2021-11-30
ENG-406 | Coordinate to Develop Geotechnical Permitting Plan | 96 | 96 | 11 | 0% | 2021-07-15 | 2021-07-15 |  | 2021-11-30 | 2021-11-30
ENG-410 | Develop Program Design/Construction/Permit Implementation Plan | 96 | 96 | 11 | 0% | 2021-07-15 | 2021-07-15 |  | 2021-11-30 | 2021-11-30
ENG-430 | Engineering Project Coordination and Project Management | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
ENG-450 | Project Level Survey/Mapping | 86 | 86 | 261 | 0% | 2022-01-04 | 2022-01-04 |  | 2022-05-03 | 2022-05-03
ENG-460 | Update Project Seimicity | 86 | 86 | 261 | 0% | 2022-01-04 | 2022-01-04 |  | 2022-05-03 | 2022-05-03
Economics and Financial |  | 20 | 20 | 80 |  | 2021-03-04 | 2021-03-04 |  | 2021-03-31 | 2021-03-31
ENG-350 | Economic Feasibility | 5 | 5 | 95 | 0% | 2021-03-04 | 2021-03-04 |  | 2021-03-10 | 2021-03-10
ENG-360 | Financial Feasibility | 20 | 20 | 80 | 0% | 2021-03-04 | 2021-03-04 |  | 2021-03-31 | 2021-03-31
Authority Feasibility Report |  | 70 | 70 | 80 |  | 2021-04-01 | 2021-04-01 |  | 2021-07-09 | 2021-07-09
ENG-380 | Prepare Draft Feasibility Report | 30 | 30 | 80 | 0% | 2021-04-01 | 2021-04-01 |  | 2021-05-12 | 2021-05-12
ENG-382 | Executive Summary (Storyboard) | 5 | 5 | 105 | 0% | 2021-04-01 | 2021-04-01 |  | 2021-04-07 | 2021-04-07
ENG-384 | Executive Summary Final | 5 | 5 | 85 | 0% | 2021-05-06 | 2021-05-06 |  | 2021-05-12 | 2021-05-12
ENG-385 | Work Group Review | 5 | 5 | 80 | 0% | 2021-05-13 | 2021-05-13 |  | 2021-05-19 | 2021-05-19
ENG-390 | Prepare Final Feasibility Report | 30 | 30 | 80 | 0% | 2021-05-20 | 2021-05-20 |  | 2021-07-01 | 2021-07-01
ENG-392 | Reservoir Committee and Board Approval | 5 | 5 | 80 | 0% | 2021-07-05 | 2021-07-05 |  | 2021-07-09 | 2021-07-09
Hydraulics Model |  | 63 | 63 | 82 |  | 2021-05-20 | 2021-05-20 |  | 2021-08-18 | 2021-08-18
ENG-420 | Advance Preliminary Hydraulics Model | 40 | 40 | 82 | 0% | 2021-05-20 | 2021-05-20 |  | 2021-07-16 | 2021-07-16
ENG-440 | Final Hydraulics Model | 23 | 23 | 82 | 0% | 2021-07-19 | 2021-07-19 |  | 2021-08-18 | 2021-08-18
PROP 1 |  | 289 | 289 | 0 |  | 2020-10-23 | 2020-10-23 |  | 2021-12-15 | 2021-12-15
CWC Feasibility Review |  | 180 | 180 | 0 |  | 2021-03-31 | 2021-03-31 |  | 2021-12-15 | 2021-12-15
CWC-391 | Release for CWC Review Pkg 1: Engineering | 0 | 0 | 80 | 0% |  |  |  | 2021-07-09 | 2021-07-09
CWC-393 | Release for CWC Review Pkg 2: Economic and Finance | 0 | 0 | 150 | 0% |  |  |  | 2021-03-31 | 2021-03-31
CWC-396 | Release for CWC Review Pkg 3: Environmental with Res Ops | 0 | 0 | 0 | 0% |  |  |  | 2021-12-03 | 2021-12-03
CWC-397 | CWC Review Pkg 1: Engineering | 30 | 30 | 80 | 0% | 2021-07-12 | 2021-07-12 |  | 2021-08-20 | 2021-08-20
CWC-407 | CWC Review Pkg 2: Economic and Finance | 30 | 30 | 150 | 0% | 2021-04-01 | 2021-04-01 |  | 2021-05-12 | 2021-05-12
CWC-417 | CWC Review Pkg 3: Environmental with Res Ops | 8 | 8 | 0 | 0% | 2021-12-06 | 2021-12-06 |  | 2021-12-15 | 2021-12-15
Revised Public Benefits |  | 0 | 0 | 259 |  | 2020-10-23 | 2020-10-23 |  | 2020-10-23 | 2020-10-23
CWC-420 | Provide CWC with Revised Public Benefits | 0 | 0 | 259 | 0% |  |  |  | 2020-10-23 | 2020-10-23
CWC Review of Public Draft EIR/EIS |  | 30 | 30 | 1 |  | 2021-07-15 | 2021-07-16 |  | 2021-08-25 | 2021-08-26
CWC-450 | CWC Public Review Draft EIR/EIS | 30 | 30 | 1 | 0% | 2021-07-15 | 2021-07-16 |  | 2021-08-25 | 2021-08-26
CWC Determination |  | 0 | 0 | 0 |  | 2021-12-15 | 2021-12-15 |  | 2021-12-15 | 2021-12-15
CWC-500 | State Determination of Feasibility | 0 | 0 | 0 | 0% |  |  |  | 2021-12-15 | 15-Dec-21*

## Joe
Sites Monthly Project Schedule Update |  |  |  |  | Data Date: | 2020-04-30
Activity ID | Activity Name | Ori Dur | Remaining Dur | Total Float | Physical % Comp | Baseline Start | Current Start | Actual Start | Baseline Finish | Current Finish | Actual Finish
Joe Trapasso |  | 510 | 510 | 346 |  | 2020-01-02 | 2020-01-02 |  | 2022-01-02 | 2022-01-04
LOCAL FUNDING |  | 510 | 510 | 346 |  | 2020-01-02 | 2020-01-02 |  | 2022-01-02 | 2022-01-04
Execute Participation Ageement 1B |  | 95 | 95 | 746 |  | 2020-01-23 | 2020-01-23 |  | 2020-06-04 | 2020-06-04
PA-00-1B | Participation Agreement Amend 1B | 95 | 95 | 746 | 0% | 2020-01-23 | 2020-01-23 |  | 2020-06-04 | 2020-06-04
PA-010 | Amend Task Orders | 26 | 26 | 25 | 0% | 2020-01-23 | 2020-01-23 |  | 2020-02-27 | 2020-02-27
PA-020 | Final Participation Agreement Amendment 1B | 15 | 15 | 58 | 0% | 2020-03-18 | 2020-03-18 |  | 2020-04-08 | 2020-04-08
PA-030 | Engineering Task Orders (HC, HR) | 30 | 30 | 25 | 0% | 2020-01-23 | 2020-01-23 |  | 2020-03-04 | 2020-03-04
PA-040 | Amendment 1B Exhibit B | 5 | 5 | 58 | 0% | 2020-04-01 | 2020-04-01 |  | 2020-04-08 | 2020-04-08
PA-050 | Executed 1B | 0 | 0 | 58 | 0% |  |  |  | 2020-06-04 | 2020-06-04
Execute Participation Agreement 2 |  | 114 | 114 | 0 |  | 2020-03-18 | 2020-03-18 |  | 2020-08-26 | 2020-08-26
PA-120 | Draft Participation Agreement Amend 2 for Home Board Review | 15 | 15 | 14 | 0% | 2020-03-18 | 2020-03-18 |  | 2020-04-08 | 2020-04-08
PA-130 | Home Board Review - Determine Participation Level | 44 | 44 | 7 | 0% | 2020-04-17 | 2020-04-17 |  | 2020-06-18 | 2020-06-18
PA-140 | Rebalance Participation | 8 | 8 | 7 | 0% | 2020-06-19 | 2020-06-19 |  | 2020-06-30 | 2020-06-30
PA-150 | Final Participation Agreement Amend 2 with Exhibits | 0 | 0 | 7 | 0% |  |  |  | 2020-06-30 | 2020-06-30
PA-160 | Execute Amendment 2 | 0 | 0 | 0 | 0% |  |  |  | 2020-08-26 | 2020-08-26
Execute Successor Participation Areement 2 |  | 107 | 107 | 346 |  | 2021-08-02 | 2021-08-02 |  | 2021-12-31 | 2022-01-04
PA-00-020 | Participation and Rebalancing | 106 | 106 | 347 | 0% | 2021-08-02 | 2021-08-02 |  | 2021-12-31 | 2021-12-31
PA-210 | Prepare Successor Agreement Work Plan | 85 | 85 | 346 | 0% | 2021-08-02 | 02-Aug-21* |  | 2021-12-01 | 2021-12-01
PA-220 | Execute Successor Agreement | 22 | 22 | 346 | 0% | 2021-12-02 | 2021-12-02 |  | 2021-12-31 | 2022-01-04
Work Plan Amend 1B |  | 40 | 40 | 80 |  | 2020-01-02 | 2020-01-02 |  | 2020-02-26 | 2020-02-26
WP-005 | Incorporate Comments from Dec Res Comm Mtg | 9 | 9 | 0 | 0% | 2020-01-02 | 02-Jan-20* |  | 2020-01-14 | 2020-01-14
WP-015 | Prepare Final Work Plan | 14 | 14 | 2 | 0% | 2020-01-15 | 2020-01-15 |  | 2020-02-03 | 2020-02-03
WP-020 | Budget & Finance Work Group Review | 5 | 5 | 2 | 0% | 2020-02-04 | 2020-02-04 |  | 2020-02-10 | 2020-02-10
WP-025 | Work Plan 1B Approved | 0 | 0 | 80 | 0% |  |  |  | 2020-02-26 | 2020-02-26
Work Plan Amend 2 |  | 153 | 153 | 0 |  | 2020-01-28 | 2020-01-28 |  | 2020-09-01 | 2020-09-01
WP-035 | Budget Scenarios and Assumptions | 2 | 2 | 7 | 0% | 2020-02-11 | 2020-02-11 |  | 2020-02-12 | 2020-02-12
WP-040 | Develop Draft Schedule thru Dec 31, 2021 | 13 | 13 | 3 | 0% | 2020-01-28 | 2020-01-28 |  | 2020-02-13 | 2020-02-13
WP-050 | Draft Work Plan Task List | 13 | 13 | 6 | 0% | 2020-01-28 | 2020-01-28 |  | 2020-02-13 | 2020-02-13
WP-055 | Draft Work Plan Budget | 13 | 13 | 6 | 0% | 2020-01-28 | 2020-01-28 |  | 2020-02-13 | 2020-02-13
WP-060 | Develop Final Schedule through Dec 2021 | 10 | 10 | 21 | 0% | 2020-02-24 | 2020-02-24 |  | 2020-03-06 | 2020-03-06
WP-070 | Final Work Plan Scope Document | 31 | 31 | 0 | 0% | 2020-02-24 | 2020-02-24 |  | 2020-04-06 | 2020-04-06
WP-090 | Final Work Plan Budget | 31 | 31 | 0 | 0% | 2020-02-24 | 2020-02-24 |  | 2020-04-06 | 2020-04-06
WP2-095 | Final Amendment 2 Work Plan | 5 | 5 | 0 | 0% | 2020-04-07 | 2020-04-07 |  | 2020-04-13 | 2020-04-13
WP2-110 | Develop Task Orders (Sep 2020 to Dec 2021) | 51 | 51 | 47 | 0% | 2020-04-14 | 2020-04-14 |  | 2020-06-24 | 2020-06-24
WP2-120 | Work Plan 2 Approved | 0 | 0 | 47 | 0% |  |  |  | 2020-06-24 | 2020-06-24
WP2-130 | Start of Amend 2 | 0 | 0 | 0 | 0% | 2020-09-01 | 2020-09-01
Amendment 3 |  | 0 | 0 | 376 |  | 2022-01-02 | 2022-01-02 |  | 2022-01-02 | 2022-01-02
WP3-010 | Start of Amend 3 | 0 | 0 | 376 | 0% |  |  |  | 2022-01-02 | 02-Jan-22*
VALUE PLANNING |  | 4 | 4 | 4 |  | 2020-02-25 | 2020-02-25 |  | 2020-02-28 | 2020-02-28
Value Planning Analysis |  | 4 | 4 | 4 |  | 2020-02-25 | 2020-02-25 |  | 2020-02-28 | 2020-02-28
VP-014 | Affordability Analysis | 4 | 4 | 4 | 0% | 2020-02-25 | 2020-02-25 |  | 2020-02-28 | 2020-02-28
PROJECT OPERATIONS AND FINANCES |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
PROJECT OPERATIONS AND FINANCES |  | 171 | 171 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2020-08-31 | 2020-08-31
REP-005 | Quarterly Reporting Amend 1B | 171 | 171 | 347 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-08-31 | 2020-08-31
Contract Amendments |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
CON-00-20 | Contract Amendments | 20 | 20 | 836 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-01-29 | 2020-01-29
CON-010 | Contract Management | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
CON-022 | Revise Service Area Task Orders for Approval | 20 | 20 | 9 | 0% | 2020-02-04 | 2020-02-04 |  | 2020-03-02 | 2020-03-02
Accounts Payable & Receivable |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
AP-010 | Accounts Payable & Accounts Receivable | 171 | 171 | 347 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-08-31 | 2020-08-31
AP-012 | Accounts Payable & Accounts Receivable | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
Invoicing & Reporting |  | 499 | 499 | 347 |  | 2020-01-16 | 2020-01-16 |  | 2021-12-31 | 2021-12-31
INV-00-30 | CWC Invoicing Amend 1B | 161 | 161 | 685 | 0% | 2020-01-16 | 2020-01-16 |  | 2020-08-31 | 2020-08-31
INV-010 | CWC Invoicing Amend 2 | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
INV-032 | Prepare 4Q2019 CWC invoice | 17 | 17 | 685 | 0% | 2020-01-16 | 16-Jan-20* |  | 2020-02-07 | 2020-02-07
INV-033 | Prepare Q12020 CWC invoice | 18 | 18 | 828 | 0% | 2020-01-16 | 16-Jan-20* |  | 2020-02-10 | 2020-02-10
REP-010 | Quarterly Reporting Amend 2 | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
REP-020 | Annual Reporting | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
Project Scheduling |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
PS-010 | Project Scheduling | 171 | 171 | 347 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-08-31 | 2020-08-31
PS-020 | Project Scheduling | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
Monthly Board/Res Comm Support |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
MB-000 | Monthly Board/Res Comm Support | 171 | 171 | 347 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-08-31 | 2020-08-31
MB-010 | Monthly Board/Res Comm Support | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
Financial Assistance Agreement |  | 79 | 79 | 11 |  | 2020-01-14 | 2020-01-14 |  | 2020-05-01 | 2020-05-01
FAA-005 | Prepare Draft FA Scope and Form 424 | 15 | 15 | 11 | 0% | 2020-01-14 | 2020-01-14 |  | 2020-02-03 | 2020-02-03
FAA-010 | Review Scope with USBR | 5 | 5 | 11 | 0% | 2020-02-04 | 2020-02-04 |  | 2020-02-10 | 2020-02-10
FAA-015 | Prepare Budget Estimates, Narrative and Form 424A/B, SFLLL | 44 | 44 | 11 | 0% | 2020-02-11 | 2020-02-11 |  | 2020-04-10 | 2020-04-10
FAA-020 | Review with USBR | 5 | 5 | 11 | 0% | 2020-04-13 | 2020-04-13 |  | 2020-04-17 | 2020-04-17
FAA-025 | Finalize Draft FA | 10 | 10 | 11 | 0% | 2020-04-20 | 2020-04-20 |  | 2020-05-01 | 2020-05-01
Plan of Finance |  | 319 | 319 | 452 |  | 2020-04-30 | 2020-04-30 |  | 2021-08-02 | 2021-08-02
POF-00-00 | Plan of Finance | 109 | 109 | 452 | 0% | 2021-03-01 | 2021-03-01 |  | 2021-08-02 | 2021-08-02
POF-005 | Plan of Finance Update 1 (Update Affordability) | 0 | 0 | 771 | 0% | 2020-04-30 | 30-Apr-20*
POF-010 | Plan of Finance (Fin Feas) | 0 | 0 | 452 | 0% | 2021-03-01 | 01-Mar-21*
POF-015 | Plan of Finance (WIFIA Loan) | 0 | 0 | 538 | 0% | 2021-04-01 | 01-Apr-21*
POF-020 | WIFIA/LOI | 0 | 0 | 475 | 0% | 2021-06-30 | 30-Jun-21*
POF-025 | Plan of Finance (Home Board Pkg) | 0 | 0 | 452 | 0% |  |  |  | 2021-08-02 | 02-Aug-21*
WIFIA Loan Application |  | 381 | 381 | 475 |  | 2020-01-02 | 2020-01-02 |  | 2021-06-29 | 2021-06-29
WL-00-00 | WIFIA Loan Application Prep | 171 | 171 | 685 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-08-31 | 2020-08-31
WL-00-010 | WIFIA Loan Application | 125 | 125 | 475 | 0% | 2021-01-05 | 2021-01-05 |  | 2021-06-29 | 2021-06-29
WL-005 | Prepare Initial Loan Application | 60 | 60 | 475 | 0% | 2021-01-05 | 2021-01-05 |  | 2021-03-29 | 2021-03-29
WL-010 | Review Loan Application | 35 | 35 | 475 | 0% | 2021-03-30 | 2021-03-30 |  | 2021-05-17 | 2021-05-17
WL-015 | Prepare Loan Application for Facilities | 30 | 30 | 475 | 0% | 2021-05-18 | 2021-05-18 |  | 2021-06-29 | 2021-06-29
Strategic Planner |  | 338 | 338 | 347 |  | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
STP-010 | Strategic Planner | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
Program Management |  | 338 | 338 | 347 |  | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
BUS-00-00 | Business Management | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
MGT-070 | Project Management | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
Misc Expenses |  | 338 | 338 | 347 |  | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
MGT-030 | Rent | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
MGT-040 | Misc Vendors | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
MGT-050 | IT/GIS Support | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
MGT-060 | Document Management | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31

## Kevin
Sites Monthly Project Schedule Update |  |  |  |  | Data Date: | 2020-04-30
Activity ID | Activity Name | Ori Dur | Remaining Dur | Total Float | Physical % Comp | Baseline Start | Current Start | Actual Start | Baseline Finish | Current Finish | Actual Finish
Kevin Spesert |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
PROJECT OPERATIONS AND FINANCES |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
REAL ESTATE |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
RE-200 | Real Estate Landowner Coordination | 171 | 171 | 347 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-08-31 | 2020-08-31
RE-210 | Real Estate Landowner Coordination | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
COMMUNICATIONS & GOVERNMENT AFFAIRS |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
CG-000 | Communication & Government Affairs | 171 | 171 | 347 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-08-31 | 2020-08-31
CG-10 | Communication | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
GS-20 | Government Affairs Work Plan 2020 | 84 | 84 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-12-31 | 2020-12-31
GS-30 | Government Affairs Work Plan 2021 | 254 | 254 | 347 | 0% | 2021-01-04 | 2021-01-04 |  | 2021-12-31 | 2021-12-31

## Jim
Sites Monthly Project Schedule Update |  |  |  |  | Data Date: | 2020-04-30
Activity ID | Activity Name | Ori Dur | Remaining Dur | Total Float | Physical % Comp | Baseline Start | Current Start | Actual Start | Baseline Finish | Current Finish | Actual Finish
Jim Watson |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
PROJECT OPERATIONS AND FINANCES |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
Organizational Assessment |  | 255 | 255 | 601 |  | 2020-01-02 | 2020-01-02 |  | 2020-12-31 | 2020-12-31
ORA-000 | Organizational Assessment Direction | 171 | 171 | 685 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-08-31 | 2020-08-31
ORA-010 | Organizational Assessment | 84 | 84 | 601 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-12-31 | 2020-12-31
Executive Director |  | 338 | 338 | 347 |  | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
EXD-010 | Executive Director | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
Risk Assessment |  | 217 | 217 | 601 |  | 2020-02-25 | 2020-02-25 |  | 2020-12-31 | 2020-12-31
RA-00-1B | Update Risk Assessment | 50 | 50 | 768 | 0% | 2020-02-25 | 2020-02-25 |  | 2020-05-04 | 2020-05-04
RA-00-2A | Risk Assessment | 84 | 84 | 601 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-12-31 | 2020-12-31
RA-005 | Risk Analysis of Recommend Option Meeting | 40 | 40 | 768 | 0% | 2020-02-25 | 2020-02-25 |  | 2020-04-20 | 2020-04-20
RA-010 | Prepare Cost Risk Update | 10 | 10 | 768 | 0% | 2020-04-21 | 2020-04-21 |  | 2020-05-04 | 2020-05-04
RA-020 | Prepare RA | 66 | 66 | 623 | 0% | 2020-08-26 | 2020-08-26 |  | 2020-11-30 | 30-Nov-20*
RA-030 | Submit Admin Final RA | 0 | 0 | 623 | 0% |  |  |  | 2020-11-30 | 30-Nov-20*
General Counsel |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
GC-010 | General Counsel | 171 | 171 | 347 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-08-31 | 2020-08-31
GC-020 | General Counsel | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
Cost of Year Deliveries |  | 51 | 51 | 1 |  | 2020-01-02 | 2020-01-02 |  | 2020-03-12 | 2020-03-12
CYD-005 | Prepare Progress Report | 30 | 30 | 1 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-02-12 | 2020-02-12
CYD-010 | In-progress Briefing | 1 | 1 | 3 | 0% | 2020-02-13 | 2020-02-13 |  | 2020-02-13 | 2020-02-13
CYD-015 | Prepare Final Report | 20 | 20 | 1 | 0% | 2020-02-13 | 2020-02-13 |  | 2020-03-11 | 2020-03-11
CYD-020 | In-progress Briefing | 1 | 1 | 1 | 0% | 2020-03-12 | 2020-03-12 |  | 2020-03-12 | 2020-03-12

## ALL
Sites Monthly Project Schedule Update |  |  |  |  | Data Date: | 2020-04-30
Activity ID | Activity Name | Ori Dur | Remaining Dur | Total Float | Physical % Comp | Baseline Start | Current Start | Actual Start | Baseline Finish | Current Finish | Actual Finish
SITES PROJECT |  | 856 | 856 | 0 |  | 2020-01-02 | 2020-01-02 |  | 2023-05-09 | 2023-05-12
MILESTONES |  | 425 | 425 | 358 |  | 2020-04-13 | 2020-04-13 |  | 2021-12-15 | 2021-12-15
MS-001-LF | Local Funding (Go/No-go #1) | 0 | 0 | 685 | 0% |  |  |  | 2020-08-31 | 2020-08-31
MS-002-LF | Local Funding (Go/No-go #2) | 0 | 0 | 596 | 0% |  |  |  | 2021-01-08 | 2021-01-08
MS-003-LF | Local Funding (Go/No-go #3) | 0 | 0 | 272 | 0% |  |  |  | 2021-12-15 | 2021-12-15
MS-005-VP | Approve Preferred Project | 0 | 0 | 0 | 0% |  |  |  | 2020-04-13 | 2020-04-13
MS-007-PD | Project Description Complete | 0 | 0 | 0 | 0% |  |  |  | 2020-08-31 | 2020-08-31
MS-009-OP | Finalize Operational Analysis | 0 | 0 | 0 | 0% |  |  |  | 2020-11-09 | 2020-11-09
MS-011-DE | Release Revised Draft EIR/EIS | 0 | 0 | 0 | 0% |  |  |  | 2021-07-14 | 2021-07-15
LOCAL FUNDING |  | 510 | 510 | 346 |  | 2020-01-02 | 2020-01-02 |  | 2022-01-02 | 2022-01-04
Execute Participation Ageement 1B |  | 95 | 95 | 746 |  | 2020-01-23 | 2020-01-23 |  | 2020-06-04 | 2020-06-04
PA-00-1B | Participation Agreement Amend 1B | 95 | 95 | 746 | 0% | 2020-01-23 | 2020-01-23 |  | 2020-06-04 | 2020-06-04
PA-010 | Amend Task Orders | 26 | 26 | 25 | 0% | 2020-01-23 | 2020-01-23 |  | 2020-02-27 | 2020-02-27
PA-020 | Final Participation Agreement Amendment 1B | 15 | 15 | 58 | 0% | 2020-03-18 | 2020-03-18 |  | 2020-04-08 | 2020-04-08
PA-030 | Engineering Task Orders (HC, HR) | 30 | 30 | 25 | 0% | 2020-01-23 | 2020-01-23 |  | 2020-03-04 | 2020-03-04
PA-040 | Amendment 1B Exhibit B | 5 | 5 | 58 | 0% | 2020-04-01 | 2020-04-01 |  | 2020-04-08 | 2020-04-08
PA-050 | Executed 1B | 0 | 0 | 58 | 0% |  |  |  | 2020-06-04 | 2020-06-04
Execute Participation Agreement 2 |  | 114 | 114 | 0 |  | 2020-03-18 | 2020-03-18 |  | 2020-08-26 | 2020-08-26
PA-120 | Draft Participation Agreement Amend 2 for Home Board Review | 15 | 15 | 14 | 0% | 2020-03-18 | 2020-03-18 |  | 2020-04-08 | 2020-04-08
PA-130 | Home Board Review - Determine Participation Level | 44 | 44 | 7 | 0% | 2020-04-17 | 2020-04-17 |  | 2020-06-18 | 2020-06-18
PA-140 | Rebalance Participation | 8 | 8 | 7 | 0% | 2020-06-19 | 2020-06-19 |  | 2020-06-30 | 2020-06-30
PA-150 | Final Participation Agreement Amend 2 with Exhibits | 0 | 0 | 7 | 0% |  |  |  | 2020-06-30 | 2020-06-30
PA-160 | Execute Amendment 2 | 0 | 0 | 0 | 0% |  |  |  | 2020-08-26 | 2020-08-26
Execute Successor Participation Areement 2 |  | 107 | 107 | 346 |  | 2021-08-02 | 2021-08-02 |  | 2021-12-31 | 2022-01-04
PA-00-020 | Participation and Rebalancing | 106 | 106 | 347 | 0% | 2021-08-02 | 2021-08-02 |  | 2021-12-31 | 2021-12-31
PA-210 | Prepare Successor Agreement Work Plan | 85 | 85 | 346 | 0% | 2021-08-02 | 02-Aug-21* |  | 2021-12-01 | 2021-12-01
PA-220 | Execute Successor Agreement | 22 | 22 | 346 | 0% | 2021-12-02 | 2021-12-02 |  | 2021-12-31 | 2022-01-04
Work Plan Amend 1B |  | 40 | 40 | 80 |  | 2020-01-02 | 2020-01-02 |  | 2020-02-26 | 2020-02-26
WP-005 | Incorporate Comments from Dec Res Comm Mtg | 9 | 9 | 0 | 0% | 2020-01-02 | 02-Jan-20* |  | 2020-01-14 | 2020-01-14
WP-015 | Prepare Final Work Plan | 14 | 14 | 2 | 0% | 2020-01-15 | 2020-01-15 |  | 2020-02-03 | 2020-02-03
WP-020 | Budget & Finance Work Group Review | 5 | 5 | 2 | 0% | 2020-02-04 | 2020-02-04 |  | 2020-02-10 | 2020-02-10
WP-025 | Work Plan 1B Approved | 0 | 0 | 80 | 0% |  |  |  | 2020-02-26 | 2020-02-26
Work Plan Amend 2 |  | 153 | 153 | 0 |  | 2020-01-28 | 2020-01-28 |  | 2020-09-01 | 2020-09-01
Develop Schedule |  | 29 | 29 | 21 |  | 2020-01-28 | 2020-01-28 |  | 2020-03-06 | 2020-03-06
WP-040 | Develop Draft Schedule thru Dec 31, 2021 | 13 | 13 | 3 | 0% | 2020-01-28 | 2020-01-28 |  | 2020-02-13 | 2020-02-13
WP-060 | Develop Final Schedule through Dec 2021 | 10 | 10 | 21 | 0% | 2020-02-24 | 2020-02-24 |  | 2020-03-06 | 2020-03-06
Work Plan Scope Document |  | 50 | 50 | 0 |  | 2020-01-28 | 2020-01-28 |  | 2020-04-06 | 2020-04-06
WP-050 | Draft Work Plan Task List | 13 | 13 | 6 | 0% | 2020-01-28 | 2020-01-28 |  | 2020-02-13 | 2020-02-13
WP-070 | Final Work Plan Scope Document | 31 | 31 | 0 | 0% | 2020-02-24 | 2020-02-24 |  | 2020-04-06 | 2020-04-06
Work Plan Budget |  | 50 | 50 | 0 |  | 2020-01-28 | 2020-01-28 |  | 2020-04-06 | 2020-04-06
WP-035 | Budget Scenarios and Assumptions | 2 | 2 | 7 | 0% | 2020-02-11 | 2020-02-11 |  | 2020-02-12 | 2020-02-12
WP-055 | Draft Work Plan Budget | 13 | 13 | 6 | 0% | 2020-01-28 | 2020-01-28 |  | 2020-02-13 | 2020-02-13
WP-090 | Final Work Plan Budget | 31 | 31 | 0 | 0% | 2020-02-24 | 2020-02-24 |  | 2020-04-06 | 2020-04-06
Amendment 2 |  | 103 | 103 | 0 |  | 2020-04-07 | 2020-04-07 |  | 2020-09-01 | 2020-09-01
WP2-095 | Final Amendment 2 Work Plan | 5 | 5 | 0 | 0% | 2020-04-07 | 2020-04-07 |  | 2020-04-13 | 2020-04-13
WP2-110 | Develop Task Orders (Sep 2020 to Dec 2021) | 51 | 51 | 47 | 0% | 2020-04-14 | 2020-04-14 |  | 2020-06-24 | 2020-06-24
WP2-120 | Work Plan 2 Approved | 0 | 0 | 47 | 0% |  |  |  | 2020-06-24 | 2020-06-24
WP2-130 | Start of Amend 2 | 0 | 0 | 0 | 0% | 2020-09-01 | 2020-09-01
Amendment 3 |  | 0 | 0 | 376 |  | 2022-01-02 | 2022-01-02 |  | 2022-01-02 | 2022-01-02
WP3-010 | Start of Amend 3 | 0 | 0 | 376 | 0% |  |  |  | 2022-01-02 | 02-Jan-22*
VALUE PLANNING |  | 73 | 73 | 0 |  | 2020-01-02 | 2020-01-02 |  | 2020-04-13 | 2020-04-13
Value Planning Analysis |  | 44 | 44 | 8 |  | 2020-01-02 | 2020-01-02 |  | 2020-03-03 | 2020-03-03
VP-001 | Refine Value Planning Options | 3 | 3 | 4 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-01-06 | 2020-01-06
VP-002 | Screen Value Planning Options | 20 | 20 | 4 | 0% | 2020-01-07 | 2020-01-07 |  | 2020-02-03 | 2020-02-03
VP-006 | Qualitative Permit Screening | 37 | 37 | 15 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-02-21 | 2020-02-21
VP-007 | Qualitative Env Screening | 37 | 37 | 15 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-02-21 | 2020-02-21
VP-008 | Qualitative Ops Screening | 37 | 37 | 15 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-02-21 | 2020-02-21
VP-013 | Prepare Costs For Value Planning Alternatives | 15 | 15 | 4 | 0% | 2020-02-04 | 2020-02-04 |  | 2020-02-24 | 2020-02-24
VP-014 | Affordability Analysis | 4 | 4 | 4 | 0% | 2020-02-25 | 2020-02-25 |  | 2020-02-28 | 2020-02-28
VP-015 | Screen Alternatives | 2 | 2 | 4 | 0% | 2020-03-02 | 2020-03-02 |  | 2020-03-03 | 2020-03-03
VP-020 | Recommend Preferred Option | 0 | 0 | 4 | 0% |  |  |  | 2020-03-03 | 2020-03-03
Value Planning Report |  | 42 | 42 | 0 |  | 2020-02-14 | 2020-02-14 |  | 2020-04-13 | 2020-04-13
VP-025 | Value Planning Draft Report | 21 | 21 | 0 | 0% | 2020-02-14 | 2020-02-14 |  | 2020-03-13 | 2020-03-13
VP-070 | Select and Confirm Preferred Project | 21 | 21 | 0 | 0% | 2020-03-16 | 2020-03-16 |  | 2020-04-13 | 2020-04-13
VP-090 | Value Planning Final Report | 17 | 17 | 0 | 0% | 2020-03-20 | 2020-03-20 |  | 2020-04-13 | 2020-04-13
Preferred Project |  | 0 | 0 | 0 |  | 2020-04-13 | 2020-04-13 |  | 2020-04-13 | 2020-04-13
VP-095 | Approve Preferred Project | 0 | 0 | 0 | 0% |  |  |  | 2020-04-13 | 2020-04-13
PROJECT DESCRIPTION |  | 143 | 143 | 685 |  | 2020-02-11 | 2020-02-11 |  | 2020-08-31 | 2020-08-31
PDE-00-00 | Project Description | 141 | 141 | 687 | 0% | 2020-02-11 | 2020-02-11 |  | 2020-08-27 | 2020-08-27
Determine Needs |  | 56 | 56 | 2 |  | 2020-02-11 | 2020-02-11 |  | 2020-04-28 | 2020-04-28
PDE-10 | Environmental Planning Needs | 56 | 56 | 2 | 0% | 2020-02-11 | 2020-02-11 |  | 2020-04-28 | 2020-04-28
PDE-20 | Permitting Needs | 56 | 56 | 2 | 0% | 2020-02-11 | 2020-02-11 |  | 2020-04-28 | 2020-04-28
PDE-25 | Engineering Needs | 46 | 46 | 12 | 0% | 2020-02-11 | 2020-02-11 |  | 2020-04-14 | 2020-04-14
PDE-30 | Operations Needs | 10 | 10 | 48 | 0% | 2020-02-11 | 2020-02-11 |  | 2020-02-24 | 2020-02-24
PDE-35 | Water Rights Needs (Reg Items/Study) | 46 | 46 | 12 | 0% | 2020-02-11 | 2020-02-11 |  | 2020-04-14 | 2020-04-14
Components |  | 60 | 60 | 47 |  | 2020-04-01 | 2020-04-01 |  | 2020-06-24 | 2020-06-24
PDE-40 | Identify Alternatives for EIR/EIS | 30 | 30 | 9 | 0% | 2020-04-01 | 2020-04-01 |  | 2020-05-12 | 2020-05-12
PDE-42 | Determine Preliminary Project Construction Sequencing | 30 | 30 | 47 | 0% | 2020-05-13 | 2020-05-13 |  | 2020-06-24 | 2020-06-24
PDE-45 | Identify Project-Level vs Program Components (Planning) | 47 | 47 | 51 | 0% | 2020-04-14 | 2020-04-14 |  | 2020-06-18 | 2020-06-18
PDE-47 | Identify Project-Level vs Program Components (Permitting) | 47 | 47 | 51 | 0% | 2020-04-14 | 2020-04-14 |  | 2020-06-18 | 2020-06-18
Develop Project Description |  | 85 | 85 | 2 |  | 2020-04-29 | 2020-04-29 |  | 2020-08-27 | 2020-08-27
PDE-50 | Develop Project Description Construction | 85 | 85 | 2 | 0% | 2020-04-29 | 2020-04-29 |  | 2020-08-27 | 2020-08-27
PDE-55 | Project Description Operations Criteria Complete (see Ops Tasks) | 0 | 0 | 55 | 0% |  |  |  | 2020-06-12 | 2020-06-12
Project Description Complete |  | 0 | 0 | 0 |  | 2020-08-31 | 2020-08-31 |  | 2020-08-31 | 2020-08-31
PDE-60 | Project Description | 0 | 0 | 0 | 0% |  |  |  | 2020-08-31 | 2020-08-31
OPERATIONS |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
EB-00-00 | Environmental Benefits Modeling 1B | 171 | 171 | 70 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-08-31 | 2020-08-31
Value Planning Operations |  | 71 | 71 | 0 |  | 2020-01-02 | 2020-01-02 |  | 2020-04-10 | 2020-04-10
OP-005 | Value Planning Model | 37 | 37 | 0 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-02-21 | 2020-02-21
OP-007 | Stony Creek Evaluation | 37 | 37 | 0 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-02-21 | 2020-02-21
OP-010 | Shasta Exchanges Post-Processing and Draft TM | 37 | 37 | 0 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-02-21 | 2020-02-21
OP-015 | Value Planning TM/Document | 20 | 20 | 0 | 0% | 2020-02-03 | 2020-02-03 |  | 2020-02-28 | 2020-02-28
OP-020 | Storage to Release Ratios Table | 15 | 15 | 0 | 0% | 2020-02-10 | 2020-02-10 |  | 2020-02-28 | 2020-02-28
OP-070 | Reclamation Feasibility Complete (Milestone) - Critical Staffing Need | 0 | 0 | 0 | 0% |  |  |  | 2020-04-10 | 10-Apr-20*
Refine Operational Parameters |  | 89 | 89 | 0 |  | 2020-02-10 | 2020-02-10 |  | 2020-06-12 | 2020-06-12
OP-110 | Confirm Notched Fremont Weir Approach | 44 | 44 | 0 | 0% | 2020-02-10 | 2020-02-10 |  | 2020-04-09 | 2020-04-09
OP-120 | Model Reclamation with No Storage Investment | 44 | 44 | 0 | 0% | 2020-04-10 | 2020-04-10 |  | 2020-06-11 | 2020-06-11
OP-130 | Confirm Shasta Exchange Approach | 44 | 44 | 0 | 0% | 2020-02-10 | 2020-02-10 |  | 2020-04-09 | 2020-04-09
OP-140 | Confirm Sutter Bypass Approach | 44 | 44 | 0 | 0% | 2020-02-10 | 2020-02-10 |  | 2020-04-09 | 2020-04-09
OP-150 | Confirm Voluntary Agreement Weir Notching Approach | 44 | 44 | 0 | 0% | 2020-02-10 | 2020-02-10 |  | 2020-04-09 | 2020-04-09
OP-160 | Confirm Delta Water Quality Approach | 44 | 44 | 0 | 0% | 2020-02-10 | 2020-02-10 |  | 2020-04-09 | 2020-04-09
OP-170 | Confirm Sacramento River Mortality Approach | 44 | 44 | 0 | 0% | 2020-02-10 | 2020-02-10 |  | 2020-04-09 | 2020-04-09
OP-180 | Determine Baseline | 30 | 30 | 14 | 0% | 2020-02-10 | 2020-02-10 |  | 2020-03-20 | 2020-03-20
OP-190 | Confirm CVP/SWP Integration Approach | 44 | 44 | 0 | 0% | 2020-02-10 | 2020-02-10 |  | 2020-04-09 | 2020-04-09
OP-200 | Confirm Participation Demands Updated | 44 | 44 | 0 | 0% | 2020-02-10 | 2020-02-10 |  | 2020-04-09 | 2020-04-09
OP-210 | Confirm Model Refinements | 44 | 44 | 0 | 0% | 2020-04-10 | 2020-04-10 |  | 2020-06-11 | 2020-06-11
OP-220 | Finalize Operational Criteria | 0 | 0 | 0 | 0% |  |  |  | 2020-06-12 | 2020-06-12
Full Operations Analysis |  | 104 | 104 | 405 |  | 2020-06-15 | 2020-06-15 |  | 2020-11-09 | 2020-11-09
OP-00-10 | Full Operations Analysis | 49 | 49 | 405 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-11-09 | 2020-11-09
OP-230 | CalSim | 104 | 104 | 0 | 0% | 2020-06-15 | 2020-06-15 |  | 2020-11-09 | 2020-11-09
OP-240 | DSM2-Hydro | 104 | 104 | 0 | 0% | 2020-06-15 | 2020-06-15 |  | 2020-11-09 | 2020-11-09
OP-250 | USRWQM | 104 | 104 | 17 | 0% | 2020-06-15 | 2020-06-15 |  | 2020-11-09 | 2020-11-09
OP-260 | SALMOD | 104 | 104 | 0 | 0% | 2020-06-15 | 2020-06-15 |  | 2020-11-09 | 2020-11-09
OP-270 | IOS | 104 | 104 | 17 | 0% | 2020-06-15 | 2020-06-15 |  | 2020-11-09 | 2020-11-09
OP-280 | DSM2-Qual | 104 | 104 | 17 | 0% | 2020-06-15 | 2020-06-15 |  | 2020-11-09 | 2020-11-09
OP-290 | OBAN | 104 | 104 | 6 | 0% | 2020-06-15 | 2020-06-15 |  | 2020-11-09 | 2020-11-09
OP-300 | Fish Mortality Models | 104 | 104 | 6 | 0% | 2020-06-15 | 2020-06-15 |  | 2020-11-09 | 2020-11-09
OP-310 | Power | 104 | 104 | 17 | 0% | 2020-06-15 | 2020-06-15 |  | 2020-11-09 | 2020-11-09
OP-315 | Economics | 104 | 104 | 17 | 0% | 2020-06-15 | 2020-06-15 |  | 2020-11-09 | 2020-11-09
OP-410 | Initial Modeling Evaluation | 45 | 45 | 0 | 0% | 2020-06-15 | 2020-06-15 |  | 2020-08-17 | 2020-08-17
OP-420 | Preliminary Results Available for Strategy Discussions | 0 | 0 | 0 | 0% |  |  |  | 2020-08-17 | 2020-08-17
OP-430 | Define and Finalize | 48 | 48 | 0 | 0% | 2020-08-18 | 2020-08-18 |  | 2020-10-23 | 2020-10-23
OP-440 | Power and Economics | 10 | 10 | 0 | 0% | 2020-10-26 | 2020-10-26 |  | 2020-11-06 | 2020-11-06
OP-450 | Final Operations Analysis's Output | 0 | 0 | 0 | 0% |  |  |  | 2020-11-09 | 2020-11-09
Term Sheets for Key Ops Agreements |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
OP-460 | Term Sheets for key Operational Agreements | 509 | 509 | 347 | 0% | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
Operations Plan, Ver 1 |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
OP-470 | Operations Plan, Version 1 | 509 | 509 | 347 | 0% | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
Coordination |  | 350 | 350 | 370 |  | 2020-07-14 | 2020-07-14 |  | 2021-11-29 | 2021-11-29
OP-00-20 | Ops/Modeling Coordination | 231 | 231 | 405 | 0% | 2020-11-10 | 2020-11-10 |  | 2021-10-07 | 2021-10-07
OP-320 | Documentation for EIR/EIS and BA/ITP | 40 | 40 | 17 | 0% | 2020-11-10 | 2020-11-10 |  | 2021-01-08 | 2021-01-08
OP-330 | Ongoing Support to EPP, Engineering, & Financial | 350 | 350 | 12 | 0% | 2020-07-14 | 2020-07-14 |  | 2021-11-29 | 2021-11-29
OP-340 | Cumulative and Climate Change | 62 | 62 | 0 | 0% | 2020-11-10 | 2020-11-10 |  | 2021-02-09 | 2021-02-09
OP-350 | Bridging Simulation | 126 | 126 | 117 | 0% | 2020-11-10 | 2020-11-10 |  | 2021-05-10 | 2021-05-10
OP-360 | Ops Support for Local Feasibility - Water Commission | 160 | 160 | 83 | 0% | 2020-11-10 | 2020-11-10 |  | 2021-06-28 | 2021-06-28
EIR/EIS |  | 548 | 548 | 308 |  | 2020-01-02 | 2020-01-02 |  | 2022-02-25 | 2022-02-25
ENV-00-00 | On-Going Environmental Planning & Permitting | 127 | 127 | 729 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-06-29 | 2020-06-29
Work Plan & Outline |  | 224 | 224 | 0 |  | 2020-02-11 | 2020-02-11 |  | 2020-12-28 | 2020-12-28
EIR-001 | Prepare EIR/EIS Work Plan | 56 | 56 | 19 | 0% | 2020-02-11 | 2020-02-11 |  | 2020-04-28 | 2020-04-28
EIR-010 | Prepare Annotated Outline | 68 | 68 | 9 | 0% | 2020-05-13 | 2020-05-13 |  | 2020-08-18 | 2020-08-18
EIR-015 | Introduction Chapter/Recirculation Story | 68 | 68 | 9 | 0% | 2020-05-13 | 2020-05-13 |  | 2020-08-18 | 2020-08-18
EIR-021 | Prepare Draft EIR/EIS Project Description Chapter | 81 | 81 | 0 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-12-28 | 2020-12-28
Draft EIR/EIS |  | 221 | 221 | 464 |  | 2020-09-01 | 2020-09-01 |  | 2021-07-14 | 2021-07-15
EIR-00-00 | Prepare Revised Admin Draft EIR/EIS | 131 | 131 | 554 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-03-09 | 2021-03-09
EIR-00-10 | Prepare Revised Public Draft EIR/EIS | 139 | 139 | 465 | 0% | 2020-12-29 | 2020-12-29 |  | 2021-07-14 | 2021-07-14
EIR-019 | Prepare Revised Draft EIR/EIS Analysis (Construction) | 70 | 70 | 0 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-12-10 | 2020-12-10
EIR-020 | Prepare Revised Draft EIR/EIS Analysis (Operations) | 61 | 61 | 0 | 0% | 2020-12-11 | 2020-12-11 |  | 2021-03-09 | 2021-03-09
EIR-023 | Status Update to Board | 5 | 5 | 17 | 0% | 2021-01-11 | 2021-01-11 |  | 2021-01-15 | 2021-01-15
EIR-025 | Prepare Cumulative and Climate Change Sections | 20 | 20 | 0 | 0% | 2021-02-10 | 2021-02-10 |  | 2021-03-09 | 2021-03-09
EIR-026 | Prepare Complete Admin Draft EIR/EIS | 60 | 60 | 0 | 0% | 2020-12-29 | 2020-12-29 |  | 2021-03-23 | 2021-03-23
EIR-030 | Authority/Reclamation/Integration Review of Admin Draft EIR/EIS | 9 | 9 | 0 | 0% | 2021-03-24 | 2021-03-24 |  | 2021-04-05 | 2021-04-05
EIR-040 | Revise Draft EIR/EIS Based on Comments | 20 | 20 | 0 | 0% | 2021-04-06 | 2021-04-06 |  | 2021-05-03 | 2021-05-03
EIR-045 | Live Edit Meeting | 1 | 1 | 0 | 0% | 2021-05-04 | 2021-05-04 |  | 2021-05-04 | 2021-05-04
EIR-050 | Work Group & Legal Review of Revised Draft EIR/EIS | 22 | 22 | 0 | 0% | 2021-05-05 | 2021-05-05 |  | 2021-06-03 | 2021-06-04
EIR-060 | Resolve Work Group Comments | 15 | 15 | 0 | 0% | 2021-06-04 | 2021-06-07 |  | 2021-06-24 | 2021-06-25
EIR-065 | Live Edit Meeting | 2 | 2 | 0 | 0% | 2021-06-25 | 2021-06-28 |  | 2021-06-28 | 2021-06-29
EIR-067 | Final Editing, Formatting and Doc Production | 10 | 10 | 0 | 0% | 2021-06-29 | 2021-06-30 |  | 2021-07-13 | 2021-07-14
EIR-070 | Authority Approval of Release Revised Draft EIR/EIS | 1 | 1 | 0 | 0% | 2021-07-14 | 2021-07-15 |  | 2021-07-14 | 2021-07-15
EIR-080 | Release Revised Draft EIR/EIS and Issue Public Notices | 0 | 0 | 0 | 0% |  |  |  | 2021-07-14 | 2021-07-15
Public Review |  | 60 | 60 | 0 |  | 2021-07-15 | 2021-07-16 |  | 2021-09-12 | 2021-09-13
EIR-090 | Public Review Period | 60 | 60 | 0 | 0% | 2021-07-15 | 2021-07-16 |  | 2021-09-12 | 2021-09-13
Summary Report |  | 67 | 67 | 0 |  | 2021-08-30 | 2021-08-30 |  | 2021-12-03 | 2021-12-03
EIR-095 | Categorize and Sort Comments by Topic | 20 | 20 | 0 | 0% | 2021-08-30 | 2021-08-30 |  | 2021-09-27 | 2021-09-27
EIR-100 | Approach to Response to Comments | 15 | 15 | 0 | 0% | 2021-09-28 | 2021-09-28 |  | 2021-10-18 | 2021-10-18
EIR-105 | Authority/Reclamation/Legal Review | 5 | 5 | 0 | 0% | 2021-10-19 | 2021-10-19 |  | 2021-10-25 | 2021-10-25
EIR-110 | Prepare Summary Report | 20 | 20 | 0 | 0% | 2021-10-26 | 2021-10-26 |  | 2021-11-22 | 2021-11-22
EIR-115 | Work Group & Legal Review of Summary Report | 5 | 5 | 0 | 0% | 2021-11-23 | 2021-11-23 |  | 2021-12-01 | 2021-12-01
EIR-117 | Live Edit Meeting of Summary Report | 1 | 1 | 0 | 0% | 2021-12-02 | 2021-12-02 |  | 2021-12-02 | 2021-12-02
EIR-120 | Draft EIR Summary Report Submittal to CWC | 0 | 0 | 0 | 0% |  |  |  | 2021-12-03 | 2021-12-03
Response to Comments |  | 90 | 90 | 308 |  | 2021-10-19 | 2021-10-19 |  | 2022-02-25 | 2022-02-25
EIR-00-RC | Response to Comments Amend 2 | 51 | 51 | 347 | 0% | 2021-10-19 | 2021-10-19 |  | 2021-12-31 | 2021-12-31
EIR-130 | Begin Preparation of Final EIR/EIS Including Response to Comments | 90 | 90 | 193 | 0% | 2021-10-19 | 2021-10-19 |  | 2022-02-25 | 2022-02-25
PERMITTING |  | 783 | 783 | 0 |  | 2020-04-14 | 2020-04-14 |  | 2023-05-09 | 2023-05-12
Early Mitigation |  | 338 | 338 | 347 |  | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
EM-00-10 | Early Mitigation | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
Biological Assessment |  | 307 | 307 | 476 |  | 2020-04-14 | 2020-04-14 |  | 2021-06-28 | 2021-06-28
BA-00-10 | Biological Assessment/Biological Opinion | 188 | 188 | 476 | 0% | 2020-10-01 | 2020-10-01 |  | 2021-06-28 | 2021-06-28
BA-00-20 | Mitigation Planning | 150 | 150 | 535 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-04-05 | 2021-04-05
BA-00-30 | Adaptive Management Plan | 138 | 138 | 547 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-03-18 | 2021-03-18
BA-001 | Initial Desktop Analysis | 60 | 60 | 24 | 0% | 2020-10-01 | 2020-10-01 |  | 2020-12-28 | 2020-12-28
BA-010 | Mitigation Planning | 202 | 202 | 16 | 0% | 2020-04-14 | 2020-04-14 |  | 2021-01-29 | 2021-01-29
BA-015 | Adaptive Management Plan | 202 | 202 | 21 | 0% | 2020-04-14 | 2020-04-14 |  | 2021-01-29 | 2021-01-29
BA-019 | Confirm Federal Scope of Action (ESA) | 38 | 38 | 72 | 0% | 2020-04-14 | 2020-04-14 |  | 2020-06-05 | 2020-06-05
BA-020 | Permitting Construction Project Description | 16 | 16 | 72 | 0% | 2020-06-08 | 2020-06-08 |  | 2020-06-29 | 2020-06-29
BA-022 | Permitting Operations Project Description | 20 | 20 | 6 | 0% | 2020-10-20 | 2020-10-20 |  | 2020-11-16 | 2020-11-16
BA-024 | Prepare Construction Analysis | 97 | 97 | 7 | 0% | 2020-10-01 | 2020-10-01 |  | 2021-02-18 | 2021-02-18
BA-025 | Prepare Operations Analysis | 60 | 60 | 6 | 0% | 2020-11-17 | 2020-11-17 |  | 2021-02-12 | 2021-02-12
BA-030 | Finalize Admin Draft BA | 20 | 20 | 7 | 0% | 2021-02-19 | 2021-02-19 |  | 2021-03-18 | 2021-03-18
BA-032 | Submit Final Admin Draft BA | 0 | 0 | 7 | 0% |  |  |  | 2021-03-18 | 2021-03-18
BA-035 | Independent Review Draft BA | 30 | 30 | 11 | 0% | 2021-03-19 | 2021-03-19 |  | 2021-04-17 | 2021-04-17
BA-055 | Reclamation, Legal, and Work Group Review | 30 | 30 | 11 | 0% | 2021-03-19 | 2021-03-19 |  | 2021-04-17 | 2021-04-17
BA-057 | Revise Admin Draft BA | 30 | 30 | 8 | 0% | 2021-04-19 | 2021-04-19 |  | 2021-05-28 | 2021-05-28
BA-060 | Submit Revised Admin Draft BA to Reclamation | 0 | 0 | 23 | 0% |  |  |  | 2021-05-28 | 2021-05-28
BA-075 | Final Reclamation and Solicitor Office Review | 30 | 30 | 36 | 0% | 2021-05-29 | 2021-05-29 |  | 2021-06-27 | 2021-06-27
BA-100 | Reclamation Submit BA to USFWS & NMFS | 0 | 0 | 25 | 0% |  |  |  | 2021-06-28 | 2021-06-28
BO Incidental Task Authorization |  | 135 | 135 | 36 |  | 2021-06-28 | 2021-06-28 |  | 2021-11-09 | 2021-11-09
BA-1110 | BO Incidental Take Authorization | 135 | 135 | 36 | 0% | 2021-06-28 | 2021-06-28 |  | 2021-11-09 | 2021-11-09
ITP - CESA (Se 2081) Operations |  | 300 | 300 | 364 |  | 2020-10-01 | 2020-10-01 |  | 2021-12-07 | 2021-12-07
CES-00-10 | Incidental Take Permit (ITP) Operations | 300 | 300 | 364 | 0% | 2020-10-01 | 2020-10-01 |  | 2021-12-07 | 2021-12-07
CES-190 | Prepare Operations Analysis | 30 | 30 | 6 | 0% | 2021-01-12 | 2021-01-12 |  | 2021-02-22 | 2021-02-22
CES-200 | Additional Mitigation Planning | 30 | 30 | 6 | 0% | 2021-02-23 | 2021-02-23 |  | 2021-04-05 | 2021-04-05
CES-210 | Prepare Draft ITP Application Operations | 60 | 60 | 8 | 0% | 2021-06-01 | 2021-06-01 |  | 2021-08-24 | 2021-08-24
CES-220 | Legal Review of Draft ITP App | 30 | 30 | 10 | 0% | 2021-08-25 | 2021-08-25 |  | 2021-09-23 | 2021-09-23
CES-230 | Work Group Review of Draft ITP App | 30 | 30 | 10 | 0% | 2021-08-25 | 2021-08-25 |  | 2021-09-23 | 2021-09-23
CES-240 | Revise Draft ITP Application Operations | 20 | 20 | 6 | 0% | 2021-09-23 | 2021-09-23 |  | 2021-10-21 | 2021-10-21
CES-250 | Authority Board Approval of ITP App | 30 | 30 | 6 | 0% | 2021-10-21 | 2021-10-21 |  | 2021-12-06 | 2021-12-06
CES-260 | Submit ITP Application to CDFW | 0 | 0 | 6 | 0% |  |  |  | 2021-12-07 | 2021-12-07
ITP - CESA (Se 2081) Construction |  | 300 | 300 | 6 |  | 2020-10-01 | 2020-10-01 |  | 2021-12-07 | 2021-12-07
CES-015 | Initial Desktop Analysis | 30 | 30 | 86 | 0% | 2020-10-01 | 2020-10-01 |  | 2020-11-11 | 2020-11-11
CES-020 | Prepare Terrestrial Analysis | 30 | 30 | 86 | 0% | 2020-11-12 | 2020-11-12 |  | 2020-12-28 | 2020-12-28
CES-025 | Mitigation Planning | 30 | 30 | 86 | 0% | 2020-12-29 | 2020-12-29 |  | 2021-02-09 | 2021-02-09
CES-030 | Prepare Draft ITP Application Construction | 60 | 60 | 8 | 0% | 2021-06-01 | 2021-06-01 |  | 2021-08-24 | 2021-08-24
CES-040 | Legal Review of Draft ITP App | 30 | 30 | 10 | 0% | 2021-08-25 | 2021-08-25 |  | 2021-09-23 | 2021-09-23
CES-060 | Work Group Review of Draft ITP App | 30 | 30 | 10 | 0% | 2021-08-25 | 2021-08-25 |  | 2021-09-23 | 2021-09-23
CES-070 | Revise Draft ITP Application Construction | 20 | 20 | 6 | 0% | 2021-09-23 | 2021-09-23 |  | 2021-10-21 | 2021-10-21
CES-080 | Authority Board Approval of ITP App | 30 | 30 | 6 | 0% | 2021-10-21 | 2021-10-21 |  | 2021-12-06 | 2021-12-06
CES-090 | Submit ITP Application to CDFW | 0 | 0 | 6 | 0% |  |  |  | 2021-12-07 | 2021-12-07
Section 106 |  | 317 | 317 | 10 |  | 2020-09-01 | 2020-09-01 |  | 2021-12-02 | 2021-12-02
106-000 | Confirmation of Section 106 Federal Lead Agency | 0 | 0 | 22 | 0% |  |  |  | 2020-09-08 | 2020-09-08
106-001 | Prepare SHPO Initiation Package | 20 | 20 | 7 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-09-29 | 2020-09-29
106-002 | Authority/Reclamation/Integration Reviews | 10 | 10 | 7 | 0% | 2020-09-30 | 2020-09-30 |  | 2020-10-13 | 2020-10-13
106-003 | Management/Work Group Reviews | 10 | 10 | 7 | 0% | 2020-10-14 | 2020-10-14 |  | 2020-10-27 | 2020-10-27
106-004 | Revisions | 10 | 10 | 7 | 0% | 2020-10-28 | 2020-10-28 |  | 2020-11-10 | 2020-11-10
106-005 | Reclamation Submits to SHPO | 0 | 0 | 7 | 0% |  |  |  | 2020-11-17 | 2020-11-17
106-006 | SHPO Review and Comments | 30 | 30 | 13 | 0% | 2020-11-18 | 2020-11-18 |  | 2020-12-17 | 2020-12-17
106-021 | Prepare Consultation Information Package | 15 | 15 | 8 | 0% | 2020-12-17 | 2020-12-17 |  | 2021-01-11 | 2021-01-11
106-022 | Authority/Reclamation/Integration Reviews | 10 | 10 | 8 | 0% | 2021-01-11 | 2021-01-11 |  | 2021-01-25 | 2021-01-25
106-023 | Management/Work Group Reviews | 10 | 10 | 8 | 0% | 2021-01-25 | 2021-01-25 |  | 2021-02-08 | 2021-02-08
106-024 | Revisions | 10 | 10 | 8 | 0% | 2021-02-08 | 2021-02-08 |  | 2021-02-22 | 2021-02-22
106-025 | Reclamation Distributes to SHPO and Invited Consulting Parties | 5 | 5 | 19 | 0% | 2021-02-22 | 2021-02-22 |  | 2021-03-01 | 2021-03-01
106-026 | Parties Accept Invitation for Consulting Party Status | 30 | 30 | 39 | 0% | 2021-03-02 | 2021-03-02 |  | 2021-03-31 | 2021-03-31
106-032 | Arrange Meeting Logistics and Prepare Materials | 20 | 20 | 8 | 0% | 2021-02-22 | 2021-02-22 |  | 2021-03-22 | 2021-03-22
106-033 | Conduct Meetings | 10 | 10 | 19 | 0% | 2021-03-01 | 2021-03-01 |  | 2021-03-15 | 2021-03-15
106-042 | Authority/Reclamation/Integration Reviews | 10 | 10 | 8 | 0% | 2021-03-30 | 2021-03-30 |  | 2021-04-13 | 2021-04-13
106-043 | Management/Work Group Reviews | 10 | 10 | 8 | 0% | 2021-04-13 | 2021-04-13 |  | 2021-04-27 | 2021-04-27
106-044 | Revisions | 10 | 10 | 24 | 0% | 2021-04-27 | 2021-04-27 |  | 2021-05-11 | 2021-05-11
106-052 | Circulate Draft PA to SHPO and Consulting Parties | 5 | 5 | 8 | 0% | 2021-04-27 | 2021-04-27 |  | 2021-05-04 | 2021-05-04
106-053 | Deadline for Comments on Draft PA | 30 | 30 | 12 | 0% | 2021-05-05 | 2021-05-05 |  | 2021-06-03 | 2021-06-03
106-061 | Prepare Draft Final PA | 20 | 20 | 8 | 0% | 2021-06-03 | 2021-06-03 |  | 2021-07-01 | 2021-07-01
106-062 | Authority/Reclamation/Integration Reviews | 10 | 10 | 8 | 0% | 2021-07-01 | 2021-07-01 |  | 2021-07-16 | 2021-07-16
106-063 | Management/Work Group Reviews | 10 | 10 | 8 | 0% | 2021-07-16 | 2021-07-16 |  | 2021-07-30 | 2021-07-30
106-064 | Revisions | 10 | 10 | 8 | 0% | 2021-07-30 | 2021-07-30 |  | 2021-08-13 | 2021-08-13
106-072 | Circulate Draft Final PA to SHPO and Consulting Parties | 5 | 5 | 8 | 0% | 2021-08-13 | 2021-08-13 |  | 2021-08-20 | 2021-08-20
106-073 | Deadline for Comments on Draft Final PA | 30 | 30 | 12 | 0% | 2021-08-21 | 2021-08-21 |  | 2021-09-19 | 2021-09-19
106-081 | Prepare Final PA | 15 | 15 | 10 | 0% | 2021-09-20 | 2021-09-20 |  | 2021-10-08 | 2021-10-08
106-082 | Authority/Reclamation/Integration Reviews | 10 | 10 | 10 | 0% | 2021-10-11 | 2021-10-11 |  | 2021-10-22 | 2021-10-22
106-083 | Management/Work Group Reviews | 10 | 10 | 10 | 0% | 2021-10-25 | 2021-10-25 |  | 2021-11-05 | 2021-11-05
106-084 | Revisions | 10 | 10 | 10 | 0% | 2021-11-08 | 2021-11-08 |  | 2021-11-19 | 2021-11-19
106-091 | Consult with SHPO and Consulting Parties on Final PA | 5 | 5 | 11 | 0% | 2021-11-22 | 2021-11-22 |  | 2021-11-30 | 2021-11-30
106-092 | Circulate Final PA to SHPO and Consulting Parties for Signatures | 5 | 5 | 10 | 0% | 2021-11-22 | 2021-11-22 |  | 2021-11-30 | 2021-11-30
106-093 | Deadline for Signatures on Final PA | 0 | 0 | 14 | 0% |  |  |  | 2021-12-02 | 2021-12-02
Water Rights |  | 685 | 685 | 0 |  | 2020-09-01 | 2020-09-01 |  | 2023-05-09 | 2023-05-12
WR-00-00 | Water Rights | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
WR-005 | Water Availability Analysis & Planning/Coordination with SWRCB | 210 | 210 | 11 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-06-29 | 2021-06-29
WR-025 | Prepare Water Right Application | 121 | 121 | 0 | 0% | 2021-07-15 | 2021-07-16 |  | 2022-01-06 | 2022-01-07
WR-035 | QA/QC and Legal Review of Draft Water Right Application | 15 | 15 | 0 | 0% | 2022-01-07 | 2022-01-10 |  | 2022-01-27 | 2022-01-28
WR-045 | Revise Draft Water Right Application | 25 | 25 | 0 | 0% | 2022-01-28 | 2022-01-31 |  | 2022-03-03 | 2022-03-04
WR-055 | Work Group Review of Draft Water Right Application | 10 | 10 | 0 | 0% | 2022-03-04 | 2022-03-07 |  | 2022-03-17 | 2022-03-18
WR-065 | Resolve Work Group Comments | 10 | 10 | 0 | 0% | 2022-03-18 | 2022-03-21 |  | 2022-03-31 | 2022-04-01
WR-075 | Authority Approval of Water Right Application, Submit to SWRCB | 1 | 1 | 0 | 0% | 2022-04-01 | 2022-04-04 |  | 2022-04-01 | 2022-04-04
WR-085 | Submit Water Right Application | 0 | 0 | 0 | 0% |  |  |  | 2022-04-01 | 2022-04-04
WR-095 | SWRCB Review of Water Right Application | 60 | 60 | 0 | 0% | 2022-04-02 | 2022-04-05 |  | 2022-05-31 | 2022-06-03
WR-105 | Receive Protests to Application | 44 | 44 | 0 | 0% | 2022-05-31 | 2022-06-03 |  | 2022-08-02 | 2022-08-05
WR-115 | Resolve Protests and Schedule Protest Hearing | 80 | 80 | 0 | 0% | 2022-08-02 | 2022-08-05 |  | 2022-11-23 | 2022-11-30
WR-125 | Notice Water Rights Hearing | 22 | 22 | 0 | 0% | 2022-11-23 | 2022-11-30 |  | 2022-12-28 | 2023-01-03
WR-135 | Conduct In-House Mock Water Right Hearing | 15 | 15 | 7 | 0% | 2022-12-28 | 2023-01-03 |  | 2023-01-19 | 2023-01-24
WR-145 | Conduct Water Right Hearing | 1 | 1 | 0 | 0% | 2023-01-30 | 2023-02-02 |  | 2023-01-31 | 2023-02-03
WR-155 | Negotiate Permit Terms | 44 | 44 | 0 | 0% | 2023-01-31 | 2023-02-03 |  | 2023-04-03 | 2023-04-06
WR-165 | SWRCB Prepare Draft Permit and CEQA Findings | 21 | 21 | 0 | 0% | 2023-04-03 | 2023-04-06 |  | 2023-05-02 | 2023-05-05
WR-175 | SWRCB Issue Water Right Permit | 5 | 5 | 0 | 0% | 2023-05-02 | 2023-05-05 |  | 2023-05-09 | 2023-05-12
WR-185 | Water Right Permit | 0 | 0 | 0 | 0% |  |  |  | 2023-05-09 | 2023-05-12
Section 404 |  | 419 | 419 | 364 |  | 2020-04-14 | 2020-04-14 |  | 2021-12-07 | 2021-12-07
404-00-00 | Section 404 Application | 300 | 300 | 364 | 0% | 2020-10-01 | 2020-10-01 |  | 2021-12-07 | 2021-12-07
404-001 | Agreement with Reclamation for LEDPA Analysis | 15 | 15 | 22 | 0% | 2020-04-14 | 2020-04-14 |  | 2020-05-04 | 2020-05-04
404-003 | USACE LEDPA & NEPA , 404/408 and WD Approach on Secion 404 Application | 88 | 88 | 22 | 0% | 2020-05-05 | 2020-05-05 |  | 2020-09-08 | 2020-09-08
404-010 | Desktop Wetland Delineation Analysis (includes Waters of the State) | 150 | 150 | 11 | 0% | 2020-10-01 | 2020-10-01 |  | 2021-05-04 | 2021-05-04
404-020 | Submit Delineation to USACE | 0 | 0 | 11 | 0% |  |  |  | 2021-05-05 | 2021-05-05
404-025 | Pre-Application Meeting | 1 | 1 | 54 | 0% | 2021-06-01 | 2021-06-01 |  | 2021-06-02 | 2021-06-02
404-030 | Preliminary Wetland Delineation Acceptance | 90 | 90 | 15 | 0% | 2021-05-06 | 2021-05-06 |  | 2021-08-03 | 2021-08-03
404-035 | Prepare Compensatory Mitigation Plan | 161 | 161 | 6 | 0% | 2021-02-23 | 2021-02-23 |  | 2021-10-08 | 2021-10-08
404-050 | Prepare Draft 404 Application | 42 | 42 | 11 | 0% | 2021-08-03 | 2021-08-03 |  | 2021-10-01 | 2021-10-01
404-060 | Authority/Integration/Work Group Review of Draft 404 Application | 20 | 20 | 6 | 0% | 2021-10-11 | 2021-10-11 |  | 2021-11-05 | 2021-11-05
404-070 | Prepare Final 404 Application | 20 | 20 | 6 | 0% | 2021-11-08 | 2021-11-08 |  | 2021-12-07 | 2021-12-07
404-120 | Submit 404 Application | 0 | 0 | 6 | 0% |  |  |  | 2021-12-07 | 2021-12-07
Section 408 |  | 505 | 505 | 180 |  | 2020-09-01 | 2020-09-01 |  | 2022-08-26 | 2022-08-26
408-00-00 | Section 408/Encroachment Permit | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
408-005 | Coordinate with CVFPB and USACE on Section 408/Encroachment Permit | 20 | 20 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-09-29 | 2020-09-29
408-010 | Assume Start of 50% Design of 408 Jurisdictional Features | 0 | 0 | 180 | 0% |  |  |  | 2021-07-01 | 2021-07-01
408-130 | Prepare Draft Encroachment Permit/408 Request w/Engineering Team | 129 | 129 | 180 | 0% | 2021-07-05 | 2021-07-05 |  | 2022-01-06 | 2022-01-06
408-135 | Continue Draft Encroachment Permit/408 Request w/Engineering Team | 124 | 124 | 180 | 0% | 2022-01-07 | 2022-01-07 |  | 2022-06-30 | 2022-06-30
408-140 | Authority/Integration/Work Group Review of Draft | 20 | 20 | 180 | 0% | 2022-07-01 | 2022-07-01 |  | 2022-07-29 | 2022-07-29
408-150 | Prepare Encroachment Permit/408 Request | 20 | 20 | 180 | 0% | 2022-08-01 | 2022-08-01 |  | 2022-08-26 | 2022-08-26
408-160 | Submit Encroachment Permit/408 Request | 0 | 0 | 180 | 0% |  |  |  | 2022-08-26 | 2022-08-26
Section 401 Water Quality |  | 311 | 311 | 11 |  | 2020-09-09 | 2020-09-09 |  | 2021-11-30 | 2021-11-30
401-00-00 | Section 401 Water Quality | 311 | 311 | 11 | 0% | 2020-09-09 | 2020-09-09 |  | 2021-11-30 | 2021-11-30
401-120 | Coordinate with RWQCB and SWRCB | 84 | 84 | 156 | 0% | 2020-09-09 | 2020-09-09 |  | 2021-01-08 | 2021-01-08
401-130 | Prepare Draft 401 Application | 42 | 42 | 11 | 0% | 2021-08-03 | 2021-08-03 |  | 2021-10-01 | 2021-10-01
401-140 | Authority/Integration/Work Group Review of Draft 401 | 20 | 20 | 11 | 0% | 2021-10-01 | 2021-10-01 |  | 2021-10-29 | 2021-10-29
401-150 | Prepare Final 401 Application | 20 | 20 | 11 | 0% | 2021-10-29 | 2021-10-29 |  | 2021-11-30 | 2021-11-30
401-160 | Submit 401 Application | 0 | 0 | 11 | 0% |  |  |  | 2021-11-30 | 2021-11-30
FEASIBILITY-LEVEL GEOTECH |  | 449 | 449 | 348 |  | 2020-03-25 | 2020-03-25 |  | 2021-12-30 | 2021-12-30
GPP-00-00 | Geotech Permitting & Planning -1B | 112 | 112 | 685 | 0% | 2020-03-25 | 2020-03-25 |  | 2020-08-31 | 2020-08-31
Geotechnical Permitting & Planning |  | 173 | 173 | 11 |  | 2020-03-25 | 2020-03-25 |  | 2020-11-25 | 2020-11-25
GSR-000 | Identify near-term Geotechnical Needs | 112 | 112 | 11 | 0% | 2020-03-25 | 2020-03-25 |  | 2020-08-31 | 2020-08-31
GSR-010 | Geotechnical Permitting & Planning, Right of Access | 61 | 61 | 11 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-11-25 | 2020-11-25
Field Investigation |  | 85 | 85 | 539 |  | 2020-11-30 | 2020-11-30 |  | 2021-03-30 | 2021-03-30
GSR-015 | Geotechnical Field Monitoring | 85 | 85 | 539 | 0% | 2020-11-30 | 2020-11-30 |  | 2021-03-30 | 2021-03-30
GSR-020 | Conduct Geotechnical Field Investigation | 85 | 85 | 11 | 0% | 2020-11-30 | 2020-11-30 |  | 2021-03-30 | 2021-03-30
Data Evaluation and Reporting |  | 234 | 234 | 348 |  | 2021-01-29 | 2021-01-29 |  | 2021-12-30 | 2021-12-30
GSR-030 | Data Evaluation and Prepare Geotechnical Data Reports | 107 | 107 | 11 | 0% | 2021-01-29 | 2021-01-29 |  | 2021-06-29 | 2021-06-29
GSR-040 | Data Gap Assessment and Preliminary Planning for Design Level Inv for Preferred Alt | 149 | 149 | 348 | 0% | 2021-05-28 | 2021-05-28 |  | 2021-12-30 | 2021-12-30
ENGINEERING |  | 536 | 536 | 261 |  | 2020-03-24 | 2020-03-24 |  | 2022-05-03 | 2022-05-03
Support of Project Description |  | 449 | 449 | 348 |  | 2020-03-24 | 2020-03-24 |  | 2021-12-30 | 2021-12-30
ENG-110 | Engineering Consultants Brought On Board (complete prior to Sept 1) | 0 | 0 | 11 | 0% |  |  |  | 2020-03-24 | 2020-03-24
ENG-120 | Coordination of CADD and GIS Standards | 5 | 5 | 11 | 0% | 2020-03-25 | 2020-03-25 |  | 2020-03-31 | 2020-03-31
ENG-130 | Coordination to Identify Alternatives for EIR/EIS & Related Studies | 5 | 5 | 9 | 0% | 2020-03-25 | 2020-03-25 |  | 2020-03-31 | 2020-03-31
ENG-140 | Coordination to Finalize Storage & Conveyance Capacities | 5 | 5 | 22 | 0% | 2020-03-25 | 2020-03-25 |  | 2020-03-31 | 2020-03-31
ENG-145 | Coordination with Reclamantion on Approach | 5 | 5 | 0 | 0% | 2020-03-25 | 2020-03-25 |  | 2020-03-31 | 2020-03-31
ENG-150 | Gather Data from Prior Draft EIR/EIS | 10 | 10 | 15 | 0% | 2020-03-25 | 2020-03-25 |  | 2020-04-07 | 2020-04-07
ENG-160 | Prepare Project Base Map | 20 | 20 | 0 | 0% | 2020-04-01 | 2020-04-01 |  | 2020-04-28 | 2020-04-28
ENG-170 | Prepare Basis of Feasibility Design | 22 | 22 | 0 | 0% | 2020-04-01 | 2020-04-01 |  | 2020-04-30 | 2020-04-30
ENG-180 | Conduct Field Reviews (as needed) | 5 | 5 | 17 | 0% | 2020-04-01 | 2020-04-01 |  | 2020-04-07 | 2020-04-07
ENG-190 | Prepare Preliminary Feasibility Level Design | 55 | 55 | 0 | 0% | 2020-05-01 | 2020-05-01 |  | 2020-07-20 | 2020-07-20
ENG-193 | Develop Hydaulic Model | 30 | 30 | 25 | 0% | 2020-05-01 | 2020-05-01 |  | 2020-06-12 | 2020-06-12
ENG-195 | Prepare Final Feasibility Level Design | 30 | 30 | 0 | 0% | 2020-07-21 | 2020-07-21 |  | 2020-08-31 | 2020-08-31
ENG-200 | Develop CADD Drawings of Key Features | 85 | 85 | 0 | 0% | 2020-05-01 | 2020-05-01 |  | 2020-08-31 | 2020-08-31
ENG-210 | Provide Information on Key Project Features & Facilities | 21 | 21 | 80 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-09-30 | 2020-09-30
ENG-220 | Convert Drawings to GIS Geodatabase File Format to Support Environmental & Permitting | 21 | 21 | 7 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-09-30 | 2020-09-30
ENG-230 | Support to Environmental and Permitting Team | 316 | 316 | 348 | 0% | 2020-10-01 | 2020-10-01 |  | 2021-12-30 | 2021-12-30
ENG-233 | Engineering Support for Alternative A | 46 | 46 | 639 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-11-04 | 2020-11-04
ENG-236 | Engineering Support for Modified Alternative A | 46 | 46 | 639 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-11-04 | 2020-11-04
Cost Estimate, Feasibility, Constructability |  | 424 | 424 | 261 |  | 2020-09-01 | 2020-09-01 |  | 2022-05-03 | 2022-05-03
ENG-240 | Identify Project Objectives | 11 | 11 | 80 | 0% | 2020-10-01 | 2020-10-01 |  | 2020-10-15 | 2020-10-15
ENG-250 | Feasibility Project Description | 0 | 0 | 80 | 0% |  |  |  | 2020-10-15 | 2020-10-15
ENG-260 | Obtain Operations Simulation Results of Preferred Option | 0 | 0 | 88 | 0% |  |  |  | 2020-11-16 | 2020-11-16
ENG-270 | Develop Costs Associated with Mitigation Measures | 15 | 15 | 80 | 0% | 2020-10-16 | 2020-10-16 |  | 2020-11-05 | 2020-11-05
ENG-280 | Develop Class 4 Cost Estimate | 25 | 25 | 108 | 0% | 2020-11-17 | 2020-11-17 |  | 2020-12-23 | 2020-12-23
ENG-290 | Risk and Uncertainty Assessment | 20 | 20 | 80 | 0% | 2020-11-06 | 2020-11-06 |  | 2020-12-07 | 2020-12-07
ENG-300 | Coordinate with Operations to Confirm Project Benefits | 45 | 45 | 88 | 0% | 2020-11-17 | 2020-11-17 |  | 2021-01-22 | 2021-01-22
ENG-310 | Project Benefits Consist with the Ops Plan | 40 | 40 | 80 | 0% | 2020-12-08 | 2020-12-08 |  | 2021-02-03 | 2021-02-03
ENG-320 | Cost Allocation | 20 | 20 | 80 | 0% | 2021-02-04 | 2021-02-04 |  | 2021-03-03 | 2021-03-03
ENG-330 | Technical Feasibility | 20 | 20 | 100 | 0% | 2021-02-04 | 2021-02-04 |  | 2021-03-03 | 2021-03-03
ENG-340 | Obtain the Finding of Env Feasibility with Mitigation | 5 | 5 | 82 | 0% | 2021-05-04 | 2021-05-04 |  | 2021-05-10 | 2021-05-10
ENG-370 | Constructability | 20 | 20 | 80 | 0% | 2021-03-04 | 2021-03-04 |  | 2021-03-31 | 2021-03-31
ENG-400 | Develop DSOD Engagement Plan | 96 | 96 | 11 | 0% | 2021-07-15 | 2021-07-15 |  | 2021-11-30 | 2021-11-30
ENG-404 | Coordinate on a Geotechnical Investigation Plan | 96 | 96 | 11 | 0% | 2021-07-15 | 2021-07-15 |  | 2021-11-30 | 2021-11-30
ENG-406 | Coordinate to Develop Geotechnical Permitting Plan | 96 | 96 | 11 | 0% | 2021-07-15 | 2021-07-15 |  | 2021-11-30 | 2021-11-30
ENG-410 | Develop Program Design/Construction/Permit Implementation Plan | 96 | 96 | 11 | 0% | 2021-07-15 | 2021-07-15 |  | 2021-11-30 | 2021-11-30
ENG-430 | Engineering Project Coordination and Project Management | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
ENG-450 | Project Level Survey/Mapping | 86 | 86 | 261 | 0% | 2022-01-04 | 2022-01-04 |  | 2022-05-03 | 2022-05-03
ENG-460 | Update Project Seimicity | 86 | 86 | 261 | 0% | 2022-01-04 | 2022-01-04 |  | 2022-05-03 | 2022-05-03
Economics and Financial |  | 20 | 20 | 80 |  | 2021-03-04 | 2021-03-04 |  | 2021-03-31 | 2021-03-31
Feasibility Report |  | 20 | 20 | 80 |  | 2021-03-04 | 2021-03-04 |  | 2021-03-31 | 2021-03-31
ENG-350 | Economic Feasibility | 5 | 5 | 95 | 0% | 2021-03-04 | 2021-03-04 |  | 2021-03-10 | 2021-03-10
ENG-360 | Financial Feasibility | 20 | 20 | 80 | 0% | 2021-03-04 | 2021-03-04 |  | 2021-03-31 | 2021-03-31
Authority Feasibility Report |  | 70 | 70 | 80 |  | 2021-04-01 | 2021-04-01 |  | 2021-07-09 | 2021-07-09
Feasibility Report |  | 70 | 70 | 80 |  | 2021-04-01 | 2021-04-01 |  | 2021-07-09 | 2021-07-09
ENG-380 | Prepare Draft Feasibility Report | 30 | 30 | 80 | 0% | 2021-04-01 | 2021-04-01 |  | 2021-05-12 | 2021-05-12
ENG-382 | Executive Summary (Storyboard) | 5 | 5 | 105 | 0% | 2021-04-01 | 2021-04-01 |  | 2021-04-07 | 2021-04-07
ENG-384 | Executive Summary Final | 5 | 5 | 85 | 0% | 2021-05-06 | 2021-05-06 |  | 2021-05-12 | 2021-05-12
ENG-385 | Work Group Review | 5 | 5 | 80 | 0% | 2021-05-13 | 2021-05-13 |  | 2021-05-19 | 2021-05-19
ENG-390 | Prepare Final Feasibility Report | 30 | 30 | 80 | 0% | 2021-05-20 | 2021-05-20 |  | 2021-07-01 | 2021-07-01
ENG-392 | Reservoir Committee and Board Approval | 5 | 5 | 80 | 0% | 2021-07-05 | 2021-07-05 |  | 2021-07-09 | 2021-07-09
Hydraulics Model |  | 63 | 63 | 82 |  | 2021-05-20 | 2021-05-20 |  | 2021-08-18 | 2021-08-18
ENG-420 | Advance Preliminary Hydraulics Model | 40 | 40 | 82 | 0% | 2021-05-20 | 2021-05-20 |  | 2021-07-16 | 2021-07-16
ENG-440 | Final Hydraulics Model | 23 | 23 | 82 | 0% | 2021-07-19 | 2021-07-19 |  | 2021-08-18 | 2021-08-18
PROP 1 |  | 289 | 289 | 0 |  | 2020-10-23 | 2020-10-23 |  | 2021-12-15 | 2021-12-15
CWC Feasibility Review |  | 180 | 180 | 0 |  | 2021-03-31 | 2021-03-31 |  | 2021-12-15 | 2021-12-15
CWC-391 | Release for CWC Review Pkg 1: Engineering | 0 | 0 | 80 | 0% |  |  |  | 2021-07-09 | 2021-07-09
CWC-393 | Release for CWC Review Pkg 2: Economic and Finance | 0 | 0 | 150 | 0% |  |  |  | 2021-03-31 | 2021-03-31
CWC-396 | Release for CWC Review Pkg 3: Environmental with Res Ops | 0 | 0 | 0 | 0% |  |  |  | 2021-12-03 | 2021-12-03
CWC-397 | CWC Review Pkg 1: Engineering | 30 | 30 | 80 | 0% | 2021-07-12 | 2021-07-12 |  | 2021-08-20 | 2021-08-20
CWC-407 | CWC Review Pkg 2: Economic and Finance | 30 | 30 | 150 | 0% | 2021-04-01 | 2021-04-01 |  | 2021-05-12 | 2021-05-12
CWC-417 | CWC Review Pkg 3: Environmental with Res Ops | 8 | 8 | 0 | 0% | 2021-12-06 | 2021-12-06 |  | 2021-12-15 | 2021-12-15
Revised Public Benefits |  | 0 | 0 | 259 |  | 2020-10-23 | 2020-10-23 |  | 2020-10-23 | 2020-10-23
CWC-420 | Provide CWC with Revised Public Benefits | 0 | 0 | 259 | 0% |  |  |  | 2020-10-23 | 2020-10-23
CWC Review of Public Draft EIR/EIS |  | 30 | 30 | 1 |  | 2021-07-15 | 2021-07-16 |  | 2021-08-25 | 2021-08-26
CWC-450 | CWC Public Review Draft EIR/EIS | 30 | 30 | 1 | 0% | 2021-07-15 | 2021-07-16 |  | 2021-08-25 | 2021-08-26
CWC Determination |  | 0 | 0 | 0 |  | 2021-12-15 | 2021-12-15 |  | 2021-12-15 | 2021-12-15
CWC-500 | State Determination of Feasibility | 0 | 0 | 0 | 0% |  |  |  | 2021-12-15 | 15-Dec-21*
PROJECT OPERATIONS AND FINANCES |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
REP-005 | Quarterly Reporting Amend 1B | 171 | 171 | 347 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-08-31 | 2020-08-31
REAL ESTATE |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
RE-200 | Real Estate Landowner Coordination | 171 | 171 | 347 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-08-31 | 2020-08-31
RE-210 | Real Estate Landowner Coordination | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
Real Estate Landowner Coordination |  | 0 | 0 | 0
COMMUNICATIONS & GOVERNMENT AFFAIRS |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
CG-000 | Communication & Government Affairs | 171 | 171 | 347 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-08-31 | 2020-08-31
CG-10 | Communication | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
GS-20 | Government Affairs Work Plan 2020 | 84 | 84 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-12-31 | 2020-12-31
GS-30 | Government Affairs Work Plan 2021 | 254 | 254 | 347 | 0% | 2021-01-04 | 2021-01-04 |  | 2021-12-31 | 2021-12-31
Organizational Assessment |  | 255 | 255 | 601 |  | 2020-01-02 | 2020-01-02 |  | 2020-12-31 | 2020-12-31
ORA-000 | Organizational Assessment Direction | 171 | 171 | 685 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-08-31 | 2020-08-31
ORA-010 | Organizational Assessment | 84 | 84 | 601 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-12-31 | 2020-12-31
Executive Director |  | 338 | 338 | 347 |  | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
EXD-010 | Executive Director | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
Contract Amendments |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
CON-00-20 | Contract Amendments | 20 | 20 | 836 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-01-29 | 2020-01-29
CON-010 | Contract Management | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
CON-022 | Revise Service Area Task Orders for Approval | 20 | 20 | 9 | 0% | 2020-02-04 | 2020-02-04 |  | 2020-03-02 | 2020-03-02
Accounts Payable & Receivable |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
AP-010 | Accounts Payable & Accounts Receivable | 171 | 171 | 347 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-08-31 | 2020-08-31
AP-012 | Accounts Payable & Accounts Receivable | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
Invoicing & Reporting |  | 499 | 499 | 347 |  | 2020-01-16 | 2020-01-16 |  | 2021-12-31 | 2021-12-31
INV-00-30 | CWC Invoicing Amend 1B | 161 | 161 | 685 | 0% | 2020-01-16 | 2020-01-16 |  | 2020-08-31 | 2020-08-31
INV-010 | CWC Invoicing Amend 2 | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
INV-032 | Prepare 4Q2019 CWC invoice | 17 | 17 | 685 | 0% | 2020-01-16 | 16-Jan-20* |  | 2020-02-07 | 2020-02-07
INV-033 | Prepare Q12020 CWC invoice | 18 | 18 | 828 | 0% | 2020-01-16 | 16-Jan-20* |  | 2020-02-10 | 2020-02-10
REP-010 | Quarterly Reporting Amend 2 | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
REP-020 | Annual Reporting | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
Project Scheduling |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
PS-010 | Project Scheduling | 171 | 171 | 347 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-08-31 | 2020-08-31
PS-020 | Project Scheduling | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
Monthly Board/Res Comm Support |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
MB-000 | Monthly Board/Res Comm Support | 171 | 171 | 347 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-08-31 | 2020-08-31
MB-010 | Monthly Board/Res Comm Support | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
Financial Assistance Agreement |  | 79 | 79 | 11 |  | 2020-01-14 | 2020-01-14 |  | 2020-05-01 | 2020-05-01
FAA-005 | Prepare Draft FA Scope and Form 424 | 15 | 15 | 11 | 0% | 2020-01-14 | 2020-01-14 |  | 2020-02-03 | 2020-02-03
FAA-010 | Review Scope with USBR | 5 | 5 | 11 | 0% | 2020-02-04 | 2020-02-04 |  | 2020-02-10 | 2020-02-10
FAA-015 | Prepare Budget Estimates, Narrative and Form 424A/B, SFLLL | 44 | 44 | 11 | 0% | 2020-02-11 | 2020-02-11 |  | 2020-04-10 | 2020-04-10
FAA-020 | Review with USBR | 5 | 5 | 11 | 0% | 2020-04-13 | 2020-04-13 |  | 2020-04-17 | 2020-04-17
FAA-025 | Finalize Draft FA | 10 | 10 | 11 | 0% | 2020-04-20 | 2020-04-20 |  | 2020-05-01 | 2020-05-01
Plan of Finance |  | 319 | 319 | 452 |  | 2020-04-30 | 2020-04-30 |  | 2021-08-02 | 2021-08-02
POF-00-00 | Plan of Finance | 109 | 109 | 452 | 0% | 2021-03-01 | 2021-03-01 |  | 2021-08-02 | 2021-08-02
POF-005 | Plan of Finance Update 1 (Update Affordability) | 0 | 0 | 771 | 0% | 2020-04-30 | 30-Apr-20*
POF-010 | Plan of Finance (Fin Feas) | 0 | 0 | 452 | 0% | 2021-03-01 | 01-Mar-21*
POF-015 | Plan of Finance (WIFIA Loan) | 0 | 0 | 538 | 0% | 2021-04-01 | 01-Apr-21*
POF-020 | WIFIA/LOI | 0 | 0 | 475 | 0% | 2021-06-30 | 30-Jun-21*
POF-025 | Plan of Finance (Home Board Pkg) | 0 | 0 | 452 | 0% |  |  |  | 2021-08-02 | 02-Aug-21*
WIFIA Loan Application |  | 381 | 381 | 475 |  | 2020-01-02 | 2020-01-02 |  | 2021-06-29 | 2021-06-29
WL-00-00 | WIFIA Loan Application Prep | 171 | 171 | 685 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-08-31 | 2020-08-31
WL-00-010 | WIFIA Loan Application | 125 | 125 | 475 | 0% | 2021-01-05 | 2021-01-05 |  | 2021-06-29 | 2021-06-29
WL-005 | Prepare Initial Loan Application | 60 | 60 | 475 | 0% | 2021-01-05 | 2021-01-05 |  | 2021-03-29 | 2021-03-29
WL-010 | Review Loan Application | 35 | 35 | 475 | 0% | 2021-03-30 | 2021-03-30 |  | 2021-05-17 | 2021-05-17
WL-015 | Prepare Loan Application for Facilities | 30 | 30 | 475 | 0% | 2021-05-18 | 2021-05-18 |  | 2021-06-29 | 2021-06-29
Risk Assessment |  | 217 | 217 | 601 |  | 2020-02-25 | 2020-02-25 |  | 2020-12-31 | 2020-12-31
RA-00-1B | Update Risk Assessment | 50 | 50 | 768 | 0% | 2020-02-25 | 2020-02-25 |  | 2020-05-04 | 2020-05-04
RA-00-2A | Risk Assessment | 84 | 84 | 601 | 0% | 2020-09-01 | 2020-09-01 |  | 2020-12-31 | 2020-12-31
RA-005 | Risk Analysis of Recommend Option Meeting | 40 | 40 | 768 | 0% | 2020-02-25 | 2020-02-25 |  | 2020-04-20 | 2020-04-20
RA-010 | Prepare Cost Risk Update | 10 | 10 | 768 | 0% | 2020-04-21 | 2020-04-21 |  | 2020-05-04 | 2020-05-04
RA-020 | Prepare RA | 66 | 66 | 623 | 0% | 2020-08-26 | 2020-08-26 |  | 2020-11-30 | 30-Nov-20*
RA-030 | Submit Admin Final RA | 0 | 0 | 623 | 0% |  |  |  | 2020-11-30 | 30-Nov-20*
General Counsel |  | 509 | 509 | 347 |  | 2020-01-02 | 2020-01-02 |  | 2021-12-31 | 2021-12-31
GC-010 | General Counsel | 171 | 171 | 347 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-08-31 | 2020-08-31
GC-020 | General Counsel | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
Legal Counsel |  | 0 | 0 | 0
Cost of Year Deliveries |  | 51 | 51 | 1 |  | 2020-01-02 | 2020-01-02 |  | 2020-03-12 | 2020-03-12
CYD-005 | Prepare Progress Report | 30 | 30 | 1 | 0% | 2020-01-02 | 2020-01-02 |  | 2020-02-12 | 2020-02-12
CYD-010 | In-progress Briefing | 1 | 1 | 3 | 0% | 2020-02-13 | 2020-02-13 |  | 2020-02-13 | 2020-02-13
CYD-015 | Prepare Final Report | 20 | 20 | 1 | 0% | 2020-02-13 | 2020-02-13 |  | 2020-03-11 | 2020-03-11
CYD-020 | In-progress Briefing | 1 | 1 | 1 | 0% | 2020-03-12 | 2020-03-12 |  | 2020-03-12 | 2020-03-12
Strategic Planner |  | 338 | 338 | 347 |  | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
STP-010 | Strategic Planner | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
Program Management |  | 338 | 338 | 347 |  | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
BUS-00-00 | Business Management | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
MGT-070 | Project Management | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
Misc Expenses |  | 338 | 338 | 347 |  | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
MGT-030 | Rent | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
MGT-040 | Misc Vendors | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
MGT-050 | IT/GIS Support | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
MGT-060 | Document Management | 338 | 338 | 347 | 0% | 2020-09-01 | 2020-09-01 |  | 2021-12-31 | 2021-12-31
Res Comm/Authority Board |  | 0 | 0 | 0
Reservoir Committee/Board Materials DUE |  | 0 | 0 | 0
Reservoir Committee Meetings |  | 0 | 0 | 0
Authority Board Meetings |  | 0 | 0 | 0