## Guide
Guide - This page serves as a step-by-step procedure for processing monthly progress reporting submittals
| Doc Type | Purpose | Due |  | Steps
| Invoice Cover | Excel template to capture key figures for transfer into reporting database. | Due with invoice (beginning first Monday of each month until the 15th) |  | Due with invoice (due beginning first Monday of each month until the 15th)
Open Invoice-Cover worksheet
Fill in the white cells $ Billed Amount (Current), % Work Completed to date
Upload into SharePoint by using button on top right of Invoice cover worksheet (opens Sites Sharepoint - Project Controls -> A/P invoices)
Find Pre-existing record for this submittal. Filter Columns by:
Vendor - Pick your Company
Document Type - INV Cover
Work Period - Current Work/Billing period
Locate and Select Record for editing
Load file as an Attachment (use edit window on right)
Note: At mid-month, you will receive an updated version of this Invoice Cover template for next period's invoice
| Invoice | Submit Vendor/Consultant Periodic Billing | Beginning first Monday of each month until the 15th. |  | Prepare Monthly Invoice Document
Combine multiple files into one pdf file
Navigate into Sites Sharepoint - Project Controls -> A/P invoices
Find Pre-existing record for this submittal. Filter Columns by:
Vendor - Pick your Company
Document Type - INV Consultant
Work Period - Current Work Period
Locate and Select Record for editing
Load file as an Attachment (use edit window on right)
| Monthly Progress Report | Key device to measuring progress and backup documentation for invoice authorization | Consultants are to prepare a Monthly Progress Report Template (MPR) for a work period and submit it to Sharepoint by the first Monday of each month. |  | Select a) Deliverables Progress worksheet and enter… (Note: if your list is inaccurate, contact Project Controls)
% Work Complete figure per Deliverable (see table below sheet for reference on determining ratios)
A Proposed Completion Date only if it differs from current completion date (current date will be updated monthly)
A concise Justification for an Extension if you are proposing a new Completion date
A concise description of progress (Progress made during Work Period)
If there is an issue affecting timely completion of a deliverable, mark it with a "1" in column L and describe matters on General Issues page
Select b) Task Work Progress Worksheet and…
Enter a % Work Complete figure per Task
Describe progress for the work period per Task (Key Work Highlights for Current Work Period)
Describe upcoming key items per task during next work period (Key Work to be Performed Next Period)
Note: On the initial round only
Consultant will fill in the deliverables table assigning each deliverable to the proper task
Project Controls will fill in Deliverable ID's, lock down the list and return updated template.
Consultant will request changes to the deliverables list through a separate process.
Select c) General Issues worksheet and…
Enter into Issues / Challenges per row any issues / challenges / risks / opportunities you foresee affecting ability to deliver your project
Enter Approach to Resolving Mitigating Issues per each row that issues are identified
For Potential Impacts (budget, schedule, etc…), Enter a "1" into cells to serve as indicators
For Completed column, Enter a "1" into cells to serve as indicator the issue has been resolved or is no longer in play
Update a new template provided to you monthly, previous entries will be carried forward
Navigate into Sites Sharepoint - Project Controls -> A/P invoices
Find Pre-existing record for this submittal. Filter Columns by:
Vendor - Pick your Company
Document Type - MPR Monthy Progress
Work Period - Current Work Period
Locate and Select Record for editing
Load file as an Attachment (use edit window on right)
| Monthly Project Analysis | Method for identifying key items in project performance and initiating | Project controls will prepare a Progress Analysis (as needed) for a work period and submit it to Sharepoint. |  | A Monthly Progress Report Analysis is prepared as needed.
For users to locate, Navigate into Sites Sharepoint - Project Controls -> A/P invoices
Find Pre-existing record for this submittal. Filter Columns by:
Vendor - Pick your Company
Document Type - Monthy Progress Analysis
Work Period - Current Work Period
or set alerts to be notified of incoming Analysis files
Locate and Select Record
Respond by entering comments and attaching files
Guide on assigning % Completion values
| Deliverable Type | Phase |  | % Work Complete
| Meeting / Workshop | Scheduled |  | 10%
|  | Agenda & Advance Materials Sent |  | 30%
|  | Meeting Held |  | 60%
|  | Final Minutes Issued |  | 100%
| Memo/Tech Memo/Report (1) | Outline Complete |  | 10%
|  | Investigations, Testing, Document |  | 10% -> 80%
Text/Tables/Graphics Underway
|  | 1st Draft Ready for Internal Review |  | 80%
|  | Final Draft Ready for Client Review |  | 90%
|  | Document Finalized |  | 100%

## a) Deliverables
Monthly Progress Template HDR 2020-05 Jun 01, 2020
|  | HDR Deliverables Progress for 2020-05 Work Period | [8 empty] | HDR Deliverables Progress for 2020-05 Work Period
| Phase | Task ID | Your Task # | Deliverable ID | Deliverable Name | Status | Current Completion Date | % Complete | Proposed Completion Date | Justification for Extension | Progress made during Work Period | Issue
1 | 2 | A02 | A02 | PLN04 | Draft Operations Plan | Active | 0 | 40% |  |  | Developed strategy and schedue for discussions with Reclamation and DWR.
2 | 2 | A08 | A08 | APP01 | Application for Financial Assistance to Reclamation | Active | 0 | 90% |  |  | Finished resolution of project passed by the Reservoir Committee and Authority Board. Submitted additional materials/backup to Reclamation for inclusion in application.
3 | 2 | A08 | A08 | PLN05 | Amendment 1B work Plan | Active | 0 | 100% |  |  | Complete.
4 | 2 | A08 | A08 | PLN06 | Amendment 2 work plan | Active | 0 | 100% |  |  | Complete.
5 | 2 | A08 | A08 | TMS16 | WIFIA Letter of Interest Strategy Memo | Active | 0 | 20% |  |  | Continued development of letter.
6 | 2 | A13 | A13 | TMS15 | Risk Workshop Outcomes TM | Active | 0 | 10% |  |  | Began review of risk register and identified new risks based on updated project (VP7).
7 | 2 | A03 | A03 | SYS01 | Environmental Tracking Tool | Completed | 0
8 | 2 | A03 | A03 | TMS11 | Environmental QA/QC process | Completed | 0
9 | 2 | A04 | A04 | SCH01 | Permitting Schedule | Completed | 2019-07-01
10 | 2 | A08 | A08 | SCH02 | Governance Meetings calendar | Completed | 2019-05-01
11 | 2 | A08 | A08 | SYS02 | Smartsheet for Res Committee and Board Items | Completed | 2019-05-01
12 | 2 | A11 | A11 | TMS14 | Field Trip Safety TM | Completed | 2019-07-01
13 | 2 | A14 | A14 | SYS03 | GIS ROW Tool - Desktop and Mobile Apps | Completed | 2019-06-12
14 | 2 | A15 | A15 | PLN02 | GIS Plan | Completed | 2019-07-01
15 | 2 | A15 | A15 | SYS04 | GIS Database | Completed | 2019-06-01
16 | 2 | A15 | A15 | SYS06 | GIS Map Templates | Completed | 2019-06-30
17 | 2 | A16 | A16 | SYS07 | TO2 Deliverables Documents Library | Completed | 2019-06-14
18 | 2 | A06 | A06 | TMS12 | Procurement Approach TM | Obsolete | 2019-09-01
19 | 2 | A07 | A07 | TMS13 | Review comments on 2019 GIWP | Obsolete | 2019-07-31
20 | 2 | A14 | A14 | PLN01 | 2019 IT Plan | Paused | 2019-07-01
21 | 2 | A15 | A15 | SYS05 | Project GIS web-viewer | Paused | 2019-06-21
22 | 2 | A16 | A16 | PLN03 | Document Management Plan (final) | Paused | 2019-06-14
23 | 2
24 | 2
25 | 2
26 | 2
27 | 2
28 | 2
29 | 2
30 | 2
31 | 2
32 | 2
33 | 2
34 | 2
35 | 2 | [11 empty] | GIS | 36616
36 | 2
37 | 2
38 | 2
39 | 2
40 | 2
41 | 2
42 | 2
43 | 2
44 | 2
[13 empty] | Expenses | 19000
[13 empty] | Local/Landowner Outreach | 62940
[13 empty] | Statewide Outreach | 43920
[13 empty] | NGO Outreach | 37620
[13 empty] | Strategic Communications | 31920
[13 empty] | Message Development/Training | 18620
[13 empty] | Informational Materials Distribution | 95430
[13 empty] | Website Modifications and Management | 37650
[13 empty] | Video & Photography | 27645
[13 empty] | Authority/Reservoir Committee Public Affairs Support | 39920
[13 empty] | Media Relations | 24310
[13 empty] | Social Media | 22725
[13 empty] | Project Management | 97165
[13 empty] | Expenses | 85500
[13 empty] | Permitting and Resource Agency Technical Support | 295582.33
[13 empty] | Environmental Document Support | 363683.96
[13 empty] | Total Operations Technical Support | 358822.22
[13 empty] | Project Management | 118345.66
[13 empty] | Subs and ODCS | 135166
[13 empty] | Fugro PMP | 67220
[13 empty] | Data Review, Initial Site Visit,s and Develop 2019 Field Investigation Work Plan | 129310
[13 empty] | 2019 Site Investigation | 525325
[13 empty] | Future Site Investigation Work Plan for Design | 127815
[13 empty] | Project Management | 194177
[13 empty] | Expenses | 1255000
[13 empty] | Draft EIS/EIR Review and Strategic Consultation | 183585
[13 empty] | Prepare Admin Final Responses to Comments | 706108
[13 empty] | Prepare Administrative Final EIR/EIS | 715087
[13 empty] | Begin Preparation of Administrative Record for Final EIR/EIS | 39838
[13 empty] | Engagement | 84620
[13 empty] | Geotechnical Environmental Document | 100374
[13 empty] | Project Management | 118736
[13 empty] | Expenses | 4500
[13 empty] | Finalize Joint Biological Assessment | 1587973
[13 empty] | Finalize Geotechnical Permits and Fieldwork | 210858
[13 empty] | Prepare Section 106 Documents | 550076
[13 empty] | Begin Preperation of Permits and Agreements | 449881
[13 empty] | Prepare for 2020 Field Work Studies | 10669
[13 empty] | Strategize on Mitigation and Adaptive Management Planning | 157261
[13 empty] | Project Management | 178987
[13 empty] | Expenses | 217000
Formulas:
Current Completion Date = IF(A7<=DeliverableCount,INDEX(vw_Deliverables_wVendorTaskId[#All],MATCH(ConsultantChoice,vw_Deliverables_wVendorTaskId[Vendor_Alpha],0)+A7,11),"")
Monthly Progress Template
Cover Page
Monthly Progress Template
Invoice Data
Consultant Monthly Progress Template
Deliverables Progress
 Consultant's data entry is restricted to white shaded cells.
 Submit weekly to Sites Sharepoint (use link button below)
 In case you have trouble, email KStubblefield@brwncald.com
Link to Sites Sharepoint Project Controls - (A/P) Invoices
Note on M6: Enter a "1" to mark the deliverable encountering an issue identified on the General Issues page.

## b) Task Work
Monthly Progress Template HDR 2020-05 Jun 01, 2020
HDR Work Progress for 2020-05 Period
Row | Consultant | Phase | Task # | Task Name | % Work Complete |  | Key Work Highlights for Current Work Period |  | Key Upcoming Work for Period 2020-06
1 | HDR | 2 | A01 | Communications Int. |  | 1 | No work authorized under Task Order. | 1 | No work authorized under Task Order.
2 | HDR | 2 | A01 | Communications Int. |  | 2 |  | 2
3 | HDR | 2 | A01 | Communications Int. |  | 3 |  | 3
4 | HDR | 2 | A01 | Communications Int. |  | 4 |  | 4
5 | HDR | 2 | A01 | Communications Int. |  | 5 |  | 5
6 | HDR | 2 | A02 | Ops Modeling Int. | 40% | 1 | Worked with Operations consultant on development of operations criteria, including selection of baseline, diversion criteria, and Shasta Exchanges. | 1 | Continue to work with Operations consultant to advance operating criteria, including selection of baseline and other operating criteria. Take criteiria to Workgroup for review.
7 | HDR | 2 | A02 | Ops Modeling Int. |  | 2 | Led ad hoc Operations & Engineering Workgroup preparation and presentation. Hosted Workgroup meeting on Webex. | 2 | Continue to support Authority Agents and Workgroup Chair and Vice-Chair for ad hoc meetings.
8 | HDR | 2 | A02 | Ops Modeling Int. |  | 3 | Supported permitting lead on development of water rights application and Place of Use memorandum. | 3 | Continue to support permitting lead on water rights from an operational standpoint.
9 | HDR | 2 | A02 | Ops Modeling Int. |  | 4 | Supported the development of the project description and worked with the environmental planning and permitting team to provide operations data when available. | 4 | Continue to provide project integration for operations related to the project description, particularly in relation to modeling for the EIR/EIS.
10 | HDR | 2 | A02 | Ops Modeling Int. |  | 5 |  | 5
11 | HDR | 2 | A03 | Env. Planning Int. | 55.56% | 1 | Worked to develop the approach to the next phase of the EIR/EIS including development of the project description and EIR/EIS alternatives. | 1 | Continue development of EIR/EIS alternatives; take recommended alternatives to ad hoc Workgroup.
12 | HDR | 2 | A03 | Env. Planning Int. |  | 2 | Coordinated with Reclamation on the NEPA process and Reclamation's feasibility report. | 2 | Continue to coordinate with Reclamation on the NEPA process.
13 | HDR | 2 | A03 | Env. Planning Int. |  | 3 | Prepped for and presented at the ad hoc Environmental Planning & Permitting Workgroup. | 3 | Continue to support the ad hoc Workgroup.
14 | HDR | 2 | A03 | Env. Planning Int. |  | 4 |  | 4 | Review Reclamation's final draft feasibility study from ane environmental planning perspective.
15 | HDR | 2 | A03 | Env. Planning Int. |  | 5 |  | 5
16 | HDR | 2 | A04 | Permitting Int. | 55.56% | 1 | Worked with water rights consultant on Place of Use strategy. | 1 | Continue data needs coordination with engineering and geotechnical teams, along with envrironmental planning and operations.
17 | HDR | 2 | A04 | Permitting Int. |  | 2 | Began work on permitting project description. | 2 | Begin planning for project mitigation based on analysis provided by operations, environmental planning, and permitting.
18 | HDR | 2 | A04 | Permitting Int. |  | 3 | Led discussions on the continuation of the diversion criteria, baseline, and other permitting-related topics. | 3 | Provide a regulatory update with staff from regulatory agencies on new project (VP7).
19 | HDR | 2 | A04 | Permitting Int. |  | 4 | Coordinated on data needs for geotechnical and engineering, includign feasibility-level geotechnical exploration. | 4 | Work with permitting team to begin permit applications for feasibility study geotechnical explorations.
20 | HDR | 2 | A04 | Permitting Int. |  | 5 |  | 5
21 | HDR | 2 | A05 | Real Estate Int. | 35% | 1 | Developed parcel list of parcel owners in the area of VP7. | 1 | Continue landowner coordination and outreach, particularly in Yolo County along the Dunnigan pipeline.
22 | HDR | 2 | A05 | Real Estate Int. |  | 2 | Began to work with Yolo county on landowner outreach. | 2 | Continue updates on ROW tool (mobile and desktop versions).
23 | HDR | 2 | A05 | Real Estate Int. |  | 3 | Worked with engineering team on conveyance system alignment from a real estate perspective. | 3
24 | HDR | 2 | A05 | Real Estate Int. |  | 4 | Began to update the desktop and mobile ROW tools with newly impacted properties. | 4
25 | HDR | 2 | A05 | Real Estate Int. |  | 5 |  | 5
26 | HDR | 2 | A06 | Engineering Int. | 55.56% | 1 | Led schedule updates for the engineering team based on contract start changes. | 1 | Begin feasibility-level design for VP7.
27 | HDR | 2 | A06 | Engineering Int. |  | 2 | Reviewed available data and began determining geotechnical exploration locations for feasibility. | 2 | Provide data, as needed, to environmental planning and permitting teams.
28 | HDR | 2 | A06 | Engineering Int. |  | 3 | Worked with environmental planning and permitting on data needs for EIR/EIS and Biological Assessment. | 3 | Provide draft list of geotechnical exploration locations for Amendment 2.
29 | HDR | 2 | A06 | Engineering Int. |  | 4 |  | 4
30 | HDR | 2 | A06 | Engineering Int. |  | 5 |  | 5
31 | HDR | 2 | A07 | Geotech Int. | 100% | 1 | No work authorized under Task Order. | 1 | No work authorized under Task Order.
32 | HDR | 2 | A07 | Geotech Int. |  | 2 |  | 2
33 | HDR | 2 | A07 | Geotech Int. |  | 3 |  | 3
34 | HDR | 2 | A07 | Geotech Int. |  | 4 |  | 4
35 | HDR | 2 | A07 | Geotech Int. |  | 5 |  | 5
36 | HDR | 2 | A08 | Controls Int. | 55.56% | 1 | Provided updates to P6 project schedule an associated cash flow. | 1 | Continue to provide information for Financial Assistance Application, as requested by Reclamation.
37 | HDR | 2 | A08 | Controls Int. |  | 2 | Updated Financial Assistance Agreement application for WIIN Act funding. | 2 | Continue to provide updates and analysis to P6 project schedule.
38 | HDR | 2 | A08 | Controls Int. |  | 3 | Reviewed CWC invoice for submittal. | 3 | Continue to assist in development of TO templates and troubleshooting.
39 | HDR | 2 | A08 | Controls Int. |  | 4 | Assisted in developing task order templates and schedule-task order linkages. | 4
40 | HDR | 2 | A08 | Controls Int. |  | 5 |  | 5
41 | HDR | 2 | A09 | General Int. | 60% | 1 | Supported the Authority in implementing actions from the Organizational Assessment. | 1 | Continue to support the Authority in implementing actions from the Organizational Assessment.
42 | HDR | 2 | A09 | General Int. |  | 2 | Provided day-to-day coordination with Reclamation. | 2 | Continue to provide day-to-day coordination with Reclamation.
43 | HDR | 2 | A09 | General Int. |  | 3 |  | 3 | Review Reclamation's final draft feasibility study.
44 | HDR | 2 | A09 | General Int. |  | 4 |  | 4
45 | HDR | 2 | A09 | General Int. |  | 5 |  | 5
46 | HDR | 2 | A10 | Authority's Engineer | 100% | 1 | No work authorized under Task Order. | 1 | No work authorized under Task Order.
47 | HDR | 2 | A10 | Authority's Engineer |  | 2 |  | 2
48 | HDR | 2 | A10 | Authority's Engineer |  | 3 |  | 3
49 | HDR | 2 | A10 | Authority's Engineer |  | 4 |  | 4
50 | HDR | 2 | A10 | Authority's Engineer |  | 5 |  | 5
51 | HDR | 2 | A11 | Health, Safety & Loss Prevention | 100% | 1 | No work authorized under Task Order. | 1 | No work authorized under Task Order.
52 | HDR | 2 | A11 | Health, Safety & Loss Prevention |  | 2 |  | 2
53 | HDR | 2 | A11 | Health, Safety & Loss Prevention |  | 3 |  | 3
54 | HDR | 2 | A11 | Health, Safety & Loss Prevention |  | 4 |  | 4
55 | HDR | 2 | A11 | Health, Safety & Loss Prevention |  | 5 |  | 5
56 | HDR | 2 | A12 | Quality Management | 100% | 1 | No work authorized under Task Order. | 1 | No work authorized under Task Order.
57 | HDR | 2 | A12 | Quality Management |  | 2 |  | 2
58 | HDR | 2 | A12 | Quality Management |  | 3 |  | 3
59 | HDR | 2 | A12 | Quality Management |  | 4 |  | 4
60 | HDR | 2 | A12 | Quality Management |  | 5 |  | 5
61 | HDR | 2 | A13 | Risk Management | 20% | 1 | Began to update risk assessment based on new project (VP7). | 1 | Continue review of risk assessment and begin draft of Risk Assessment TM.
62 | HDR | 2 | A13 | Risk Management |  | 2 |  | 2
63 | HDR | 2 | A13 | Risk Management |  | 3 |  | 3
64 | HDR | 2 | A13 | Risk Management |  | 4 |  | 4
65 | HDR | 2 | A13 | Risk Management |  | 5 |  | 5
66 | HDR | 2 | A14 | IT | 55.56% | 1 | Provided Webex hosting for ad hoc Workgroup, Authority Board, and Reservoir Committee meetings. | 1 | Continue to provide Webex hosting for ad hoc Workgroup, Authority Board, and Reservoir Committee meetings.
67 | HDR | 2 | A14 | IT |  | 2 | Provided SharePoint support and onboarding. | 2 | Continue to provide SharePoint, Azure, and SQL server support as needed.
68 | HDR | 2 | A14 | IT |  | 3 |  | 3
69 | HDR | 2 | A14 | IT |  | 4 |  | 4
70 | HDR | 2 | A14 | IT |  | 5 |  | 5
71 | HDR | 2 | A15 | GIS | 100% | 1 | No work authorized under Task Order. | 1 | No work authorized under Task Order.
72 | HDR | 2 | A15 | GIS |  | 2 |  | 2
73 | HDR | 2 | A15 | GIS |  | 3 |  | 3
74 | HDR | 2 | A15 | GIS |  | 4 |  | 4
75 | HDR | 2 | A15 | GIS |  | 5 |  | 5
76 | HDR | 2 | A16 | Document Management | 55.56% | 1 | Provided technical editing for reports and presentations. | 1 | Provide as-needed technical edfiting and document management.
77 | HDR | 2 | A16 | Document Management |  | 2 |  | 2
78 | HDR | 2 | A16 | Document Management |  | 3 |  | 3
79 | HDR | 2 | A16 | Document Management |  | 4 |  | 4
80 | HDR | 2 | A16 | Document Management |  | 5 |  | 5
81 | HDR | 2 | A17 | Staff Support | 55.56% | 1 | No work performed. | 1 | Provide as-needed graphics support and figure/maps creation.
82 | HDR | 2 | A17 | Staff Support |  | 2 |  | 2
83 | HDR | 2 | A17 | Staff Support |  | 3 |  | 3
84 | HDR | 2 | A17 | Staff Support |  | 4 |  | 4
85 | HDR | 2 | A17 | Staff Support |  | 5 |  | 5
86 | HDR | 2 | A18 | Satellite Project Office | 100% | 1 | No work authorized under Task Order. | 1 | No work authorized under Task Order.
87 | HDR | 2 | A18 | Satellite Project Office |  | 2 |  | 2
88 | HDR | 2 | A18 | Satellite Project Office |  | 3 |  | 3
89 | HDR | 2 | A18 | Satellite Project Office |  | 4 |  | 4
90 | HDR | 2 | A18 | Satellite Project Office |  | 5 |  | 5
91 | HDR | 2 | A19 | Land Conservation Approach | 100% | 1 | No work authorized under Task Order. | 1 | No work authorized under Task Order.
92 | HDR | 2 | A19 | Land Conservation Approach |  | 2 |  | 2
93 | HDR | 2 | A19 | Land Conservation Approach |  | 3 |  | 3
94 | HDR | 2 | A19 | Land Conservation Approach |  | 4 |  | 4
95 | HDR | 2 | A19 | Land Conservation Approach |  | 5 |  | 5
96 | HDR | 2 | A98 | HDR Project Management | 55.56% | 1 | Prepared monthly invoice and MPR. | 1 | Continue with all project management activities.
97 | HDR | 2 | A98 | HDR Project Management |  | 2 | Submitted weekly burn rate data to controls and monitored burn rate with team leads. | 2
98 | HDR | 2 | A98 | HDR Project Management |  | 3 |  | 3
99 | HDR | 2 | A98 | HDR Project Management |  | 4 |  | 4
100 | HDR | 2 | A98 | HDR Project Management |  | 5 |  | 5
101 | HDR | 2 | A99 | Expenses | 55.56% | 1 | Submitted typical project expenses. | 1 | Continue to submit expenses.
102 | HDR | 2 | A99 | Expenses |  | 2 |  | 2
103 | HDR | 2 | A99 | Expenses |  | 3 |  | 3
104 | HDR | 2 | A99 |  |  | 4 |  | 4
105 | HDR | 2 | A99 |  |  | 5 |  | 5
Note on G5: Use filter to control # bullet lines
Note on H5: Fill in bullet points to explain items completed during current work period.
Monthly Progress Template
Cover Page
Monthly Progress Template
Invoice Data
Consultant Progress Template
Task Work Progress
 Consultant's data entry restricted to white cells.
 Make sure all % complete cells are updated.
 You can hide empty rows if you wish
Link to Sites Sharepoint Project Controls - (A/P) Invoices
 Submit weekly to Sharepoint (use link button below)
 In case you have trouble, email KStubblefield@brwncald.com
Monthly Progress Template
Invoice Data
Monthly Progress Template
Invoice Data

## c) General Issues
Monthly Progress Template HDR 2020-05 Jun 01, 2020
Possible Impacts
Check all that apply
# | Issues / Challenges | Approach to Resolving or Mitigating Issues | Budget | Schedule | Scope | Completed | Comments
1 | The 2020-2021 Work Plan has required significant effort that was not budgeted for. | Monitor overall weekly HDR burn rate. Determine if existing budget within HDR's contract can be transferred to this task. | 1 |  | 1 | 1 | No longer applicable.
2 | Assembling pieces of existing CAD/GIS data from various sources and incorporating in to master dataset. | Tracking data collection efforts and prioritizing important data for conversion to GIS (from CAD). | 1 | 1 | 1 | 1 | Sent ICF facilities footprint layer for permanent impacts
3 | Lack of clarity among all parties involved in Affordability Analysis (e.g., what scenarios are needed, who is responsible for which pieces). | Establish a schedule for the effort and a single source of responsibility (Lee Frederiksen). | 1 |  | 1 | 1 | This effort is nearing completion
4 | Work requested for coordination with USBR regarding 2019 geotechnical work was not anticipated. | Propose removing work associated with Fugro's 2019 GIWP development and re-purposing for USBR coordination. | 1 |  | 1 | 1 | No longer applicable.
5 | The percent of work complete was not updated for October due to changing scope and budgets. | It is expected that task orders will be revised before the end of the year, at which time HDR can rebaseline. | 1 | 1 | 1 | 1 | No longer applicable.
6
7
8
9
10
11
Monthly Progress Template
Cover Page
Monthly Progress Template
Invoice Data
Monthly Progress Template
General Issues
 Consultant's data entry restricted to white cells.
 Make sure all white cells are completed per row
 Add closure comments to indicate item has been remedied.
Link to Sites Sharepoint Project Controls - (A/P) Invoices
 Sharepoint account needed
 Submit weekly to Sharepoint (use link button below)
 In case you have trouble, email KStubblefield@brwncald.com
Note on C4: If you copy content from another source, please paste in as values
Note on D5: enter a "1" in cells that apply
Note on G5: Select a "1" to indicate Issue has been closed
Note on H6: Fill in comments only when the challenge has been met

## Output-Deliverables (hidden)
Firm | Phase | Work Period | Task ID | Your Task # | Deliverable ID | Deliverable Name | Status | Current Completion Date | % Complete | Proposed Completion Date | Justification for Extension | Progress made during Work Period | Issue
HDR | 2 | 2020-05 | A02 | A02 | PLN04 | Draft Operations Plan | Active |  | 40% |  | 0 | Developed strategy and schedue for discussions with Reclamation and DWR. | 0
HDR | 2 | 2020-05 | A08 | A08 | APP01 | Application for Financial Assistance to Reclamation | Active |  | 90% |  | 0 | Finished resolution of project passed by the Reservoir Committee and Authority Board. Submitted additional materials/backup to Reclamation for inclusion in application. | 0
HDR | 2 | 2020-05 | A08 | A08 | PLN05 | Amendment 1B work Plan | Active |  | 100% |  | 0 | Complete. | 0
HDR | 2 | 2020-05 | A08 | A08 | PLN06 | Amendment 2 work plan | Active |  | 100% |  | 0 | Complete. | 0
HDR | 2 | 2020-05 | A08 | A08 | TMS16 | WIFIA Letter of Interest Strategy Memo | Active |  | 20% |  | 0 | Continued development of letter. | 0
HDR | 2 | 2020-05 | A13 | A13 | TMS15 | Risk Workshop Outcomes TM | Active |  | 10% |  | 0 | Began review of risk register and identified new risks based on updated project (VP7). | 0
HDR | 2 | 2020-05 | A03 | A03 | SYS01 | Environmental Tracking Tool | Completed |  | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | A03 | A03 | TMS11 | Environmental QA/QC process | Completed |  | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | A04 | A04 | SCH01 | Permitting Schedule | Completed | 2019-07-01 | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | A08 | A08 | SCH02 | Governance Meetings calendar | Completed | 2019-05-01 | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | A08 | A08 | SYS02 | Smartsheet for Res Committee and Board Items | Completed | 2019-05-01 | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | A11 | A11 | TMS14 | Field Trip Safety TM | Completed | 2019-07-01 | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | A14 | A14 | SYS03 | GIS ROW Tool - Desktop and Mobile Apps | Completed | 2019-06-12 | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | A15 | A15 | PLN02 | GIS Plan | Completed | 2019-07-01 | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | A15 | A15 | SYS04 | GIS Database | Completed | 2019-06-01 | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | A15 | A15 | SYS06 | GIS Map Templates | Completed | 2019-06-30 | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | A16 | A16 | SYS07 | TO2 Deliverables Documents Library | Completed | 2019-06-14 | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | A06 | A06 | TMS12 | Procurement Approach TM | Obsolete | 2019-09-01 | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | A07 | A07 | TMS13 | Review comments on 2019 GIWP | Obsolete | 2019-07-31 | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | A14 | A14 | PLN01 | 2019 IT Plan | Paused | 2019-07-01 | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | A15 | A15 | SYS05 | Project GIS web-viewer | Paused | 2019-06-21 | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | A16 | A16 | PLN03 | Document Management Plan (final) | Paused | 2019-06-14 | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | [6 empty] | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | [6 empty] | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | [6 empty] | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | [6 empty] | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | [6 empty] | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | [6 empty] | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | [6 empty] | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | [6 empty] | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | [6 empty] | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | [6 empty] | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | [6 empty] | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | [6 empty] | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | [6 empty] | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | [6 empty] | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | [6 empty] | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | [6 empty] | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | [6 empty] | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | [6 empty] | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | [6 empty] | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | [6 empty] | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | [6 empty] | 0% |  | 0 | 0 | 0
HDR | 2 | 2020-05 | [6 empty] | 0% |  | 0 | 0 | 0

## Output-Tasks (hidden)
Consultant | Phase | WorkPeriod | TaskID | Task_Name | PercentComplete | Item | Work Performed_Current | Item_M1 | Worktodo_M1
HDR | 2 | 2020-05 | A01 | Communications Int. | 0% | 1 | No work authorized under Task Order. | 1 | No work authorized under Task Order.
HDR | 2 | 2020-05 | A01 | Communications Int. | 0% | 2 | 0 | 2 | 0
HDR | 2 | 2020-05 | A01 | Communications Int. | 0% | 3 | 0 | 3 | 0
HDR | 2 | 2020-05 | A01 | Communications Int. | 0% | 4 | 0 | 4 | 0
HDR | 2 | 2020-05 | A01 | Communications Int. | 0% | 5 | 0 | 5 | 0
HDR | 2 | 2020-05 | A02 | Ops Modeling Int. | 40% | 1 | Worked with Operations consultant on development of operations criteria, including selection of baseline, diversion criteria, and Shasta Exchanges. | 1 | Continue to work with Operations consultant to advance operating criteria, including selection of baseline and other operating criteria. Take criteiria to Workgroup for review.
HDR | 2 | 2020-05 | A02 | Ops Modeling Int. | 0% | 2 | Led ad hoc Operations & Engineering Workgroup preparation and presentation. Hosted Workgroup meeting on Webex. | 2 | Continue to support Authority Agents and Workgroup Chair and Vice-Chair for ad hoc meetings.
HDR | 2 | 2020-05 | A02 | Ops Modeling Int. | 0% | 3 | Supported permitting lead on development of water rights application and Place of Use memorandum. | 3 | Continue to support permitting lead on water rights from an operational standpoint.
HDR | 2 | 2020-05 | A02 | Ops Modeling Int. | 0% | 4 | Supported the development of the project description and worked with the environmental planning and permitting team to provide operations data when available. | 4 | Continue to provide project integration for operations related to the project description, particularly in relation to modeling for the EIR/EIS.
HDR | 2 | 2020-05 | A02 | Ops Modeling Int. | 0% | 5 | 0 | 5 | 0
HDR | 2 | 2020-05 | A03 | Env. Planning Int. | 55.56% | 1 | Worked to develop the approach to the next phase of the EIR/EIS including development of the project description and EIR/EIS alternatives. | 1 | Continue development of EIR/EIS alternatives; take recommended alternatives to ad hoc Workgroup.
HDR | 2 | 2020-05 | A03 | Env. Planning Int. | 0% | 2 | Coordinated with Reclamation on the NEPA process and Reclamation's feasibility report. | 2 | Continue to coordinate with Reclamation on the NEPA process.
HDR | 2 | 2020-05 | A03 | Env. Planning Int. | 0% | 3 | Prepped for and presented at the ad hoc Environmental Planning & Permitting Workgroup. | 3 | Continue to support the ad hoc Workgroup.
HDR | 2 | 2020-05 | A03 | Env. Planning Int. | 0% | 4 | 0 | 4 | Review Reclamation's final draft feasibility study from ane environmental planning perspective.
HDR | 2 | 2020-05 | A03 | Env. Planning Int. | 0% | 5 | 0 | 5 | 0
HDR | 2 | 2020-05 | A04 | Permitting Int. | 55.56% | 1 | Worked with water rights consultant on Place of Use strategy. | 1 | Continue data needs coordination with engineering and geotechnical teams, along with envrironmental planning and operations.
HDR | 2 | 2020-05 | A04 | Permitting Int. | 0% | 2 | Began work on permitting project description. | 2 | Begin planning for project mitigation based on analysis provided by operations, environmental planning, and permitting.
HDR | 2 | 2020-05 | A04 | Permitting Int. | 0% | 3 | Led discussions on the continuation of the diversion criteria, baseline, and other permitting-related topics. | 3 | Provide a regulatory update with staff from regulatory agencies on new project (VP7).
HDR | 2 | 2020-05 | A04 | Permitting Int. | 0% | 4 | Coordinated on data needs for geotechnical and engineering, includign feasibility-level geotechnical exploration. | 4 | Work with permitting team to begin permit applications for feasibility study geotechnical explorations.
HDR | 2 | 2020-05 | A04 | Permitting Int. | 0% | 5 | 0 | 5 | 0
HDR | 2 | 2020-05 | A05 | Real Estate Int. | 35% | 1 | Developed parcel list of parcel owners in the area of VP7. | 1 | Continue landowner coordination and outreach, particularly in Yolo County along the Dunnigan pipeline.
HDR | 2 | 2020-05 | A05 | Real Estate Int. | 0% | 2 | Began to work with Yolo county on landowner outreach. | 2 | Continue updates on ROW tool (mobile and desktop versions).
HDR | 2 | 2020-05 | A05 | Real Estate Int. | 0% | 3 | Worked with engineering team on conveyance system alignment from a real estate perspective. | 3 | 0
HDR | 2 | 2020-05 | A05 | Real Estate Int. | 0% | 4 | Began to update the desktop and mobile ROW tools with newly impacted properties. | 4 | 0
HDR | 2 | 2020-05 | A05 | Real Estate Int. | 0% | 5 | 0 | 5 | 0
HDR | 2 | 2020-05 | A06 | Engineering Int. | 55.56% | 1 | Led schedule updates for the engineering team based on contract start changes. | 1 | Begin feasibility-level design for VP7.
HDR | 2 | 2020-05 | A06 | Engineering Int. | 0% | 2 | Reviewed available data and began determining geotechnical exploration locations for feasibility. | 2 | Provide data, as needed, to environmental planning and permitting teams.
HDR | 2 | 2020-05 | A06 | Engineering Int. | 0% | 3 | Worked with environmental planning and permitting on data needs for EIR/EIS and Biological Assessment. | 3 | Provide draft list of geotechnical exploration locations for Amendment 2.
HDR | 2 | 2020-05 | A06 | Engineering Int. | 0% | 4 | 0 | 4 | 0
HDR | 2 | 2020-05 | A06 | Engineering Int. | 0% | 5 | 0 | 5 | 0
HDR | 2 | 2020-05 | A07 | Geotech Int. | 100% | 1 | No work authorized under Task Order. | 1 | No work authorized under Task Order.
HDR | 2 | 2020-05 | A07 | Geotech Int. | 0% | 2 | 0 | 2 | 0
HDR | 2 | 2020-05 | A07 | Geotech Int. | 0% | 3 | 0 | 3 | 0
HDR | 2 | 2020-05 | A07 | Geotech Int. | 0% | 4 | 0 | 4 | 0
HDR | 2 | 2020-05 | A07 | Geotech Int. | 0% | 5 | 0 | 5 | 0
HDR | 2 | 2020-05 | A08 | Controls Int. | 55.56% | 1 | Provided updates to P6 project schedule an associated cash flow. | 1 | Continue to provide information for Financial Assistance Application, as requested by Reclamation.
HDR | 2 | 2020-05 | A08 | Controls Int. | 0% | 2 | Updated Financial Assistance Agreement application for WIIN Act funding. | 2 | Continue to provide updates and analysis to P6 project schedule.
HDR | 2 | 2020-05 | A08 | Controls Int. | 0% | 3 | Reviewed CWC invoice for submittal. | 3 | Continue to assist in development of TO templates and troubleshooting.
HDR | 2 | 2020-05 | A08 | Controls Int. | 0% | 4 | Assisted in developing task order templates and schedule-task order linkages. | 4 | 0
HDR | 2 | 2020-05 | A08 | Controls Int. | 0% | 5 | 0 | 5 | 0
HDR | 2 | 2020-05 | A09 | General Int. | 60% | 1 | Supported the Authority in implementing actions from the Organizational Assessment. | 1 | Continue to support the Authority in implementing actions from the Organizational Assessment.
HDR | 2 | 2020-05 | A09 | General Int. | 0% | 2 | Provided day-to-day coordination with Reclamation. | 2 | Continue to provide day-to-day coordination with Reclamation.
HDR | 2 | 2020-05 | A09 | General Int. | 0% | 3 | 0 | 3 | Review Reclamation's final draft feasibility study.
HDR | 2 | 2020-05 | A09 | General Int. | 0% | 4 | 0 | 4 | 0
HDR | 2 | 2020-05 | A09 | General Int. | 0% | 5 | 0 | 5 | 0
HDR | 2 | 2020-05 | A10 | Authority's Engineer | 100% | 1 | No work authorized under Task Order. | 1 | No work authorized under Task Order.
HDR | 2 | 2020-05 | A10 | Authority's Engineer | 0% | 2 | 0 | 2 | 0
HDR | 2 | 2020-05 | A10 | Authority's Engineer | 0% | 3 | 0 | 3 | 0
HDR | 2 | 2020-05 | A10 | Authority's Engineer | 0% | 4 | 0 | 4 | 0
HDR | 2 | 2020-05 | A10 | Authority's Engineer | 0% | 5 | 0 | 5 | 0
HDR | 2 | 2020-05 | A11 | Health, Safety & Loss Prevention | 100% | 1 | No work authorized under Task Order. | 1 | No work authorized under Task Order.
HDR | 2 | 2020-05 | A11 | Health, Safety & Loss Prevention | 0% | 2 | 0 | 2 | 0
HDR | 2 | 2020-05 | A11 | Health, Safety & Loss Prevention | 0% | 3 | 0 | 3 | 0
HDR | 2 | 2020-05 | A11 | Health, Safety & Loss Prevention | 0% | 4 | 0 | 4 | 0
HDR | 2 | 2020-05 | A11 | Health, Safety & Loss Prevention | 0% | 5 | 0 | 5 | 0
HDR | 2 | 2020-05 | A12 | Quality Management | 100% | 1 | No work authorized under Task Order. | 1 | No work authorized under Task Order.
HDR | 2 | 2020-05 | A12 | Quality Management | 0% | 2 | 0 | 2 | 0
HDR | 2 | 2020-05 | A12 | Quality Management | 0% | 3 | 0 | 3 | 0
HDR | 2 | 2020-05 | A12 | Quality Management | 0% | 4 | 0 | 4 | 0
HDR | 2 | 2020-05 | A12 | Quality Management | 0% | 5 | 0 | 5 | 0
HDR | 2 | 2020-05 | A13 | Risk Management | 20% | 1 | Began to update risk assessment based on new project (VP7). | 1 | Continue review of risk assessment and begin draft of Risk Assessment TM.
HDR | 2 | 2020-05 | A13 | Risk Management | 0% | 2 | 0 | 2 | 0
HDR | 2 | 2020-05 | A13 | Risk Management | 0% | 3 | 0 | 3 | 0
HDR | 2 | 2020-05 | A13 | Risk Management | 0% | 4 | 0 | 4 | 0
HDR | 2 | 2020-05 | A13 | Risk Management | 0% | 5 | 0 | 5 | 0
HDR | 2 | 2020-05 | A14 | IT | 55.56% | 1 | Provided Webex hosting for ad hoc Workgroup, Authority Board, and Reservoir Committee meetings. | 1 | Continue to provide Webex hosting for ad hoc Workgroup, Authority Board, and Reservoir Committee meetings.
HDR | 2 | 2020-05 | A14 | IT | 0% | 2 | Provided SharePoint support and onboarding. | 2 | Continue to provide SharePoint, Azure, and SQL server support as needed.
HDR | 2 | 2020-05 | A14 | IT | 0% | 3 | 0 | 3 | 0
HDR | 2 | 2020-05 | A14 | IT | 0% | 4 | 0 | 4 | 0
HDR | 2 | 2020-05 | A14 | IT | 0% | 5 | 0 | 5 | 0
HDR | 2 | 2020-05 | A15 | GIS | 100% | 1 | No work authorized under Task Order. | 1 | No work authorized under Task Order.
HDR | 2 | 2020-05 | A15 | GIS | 0% | 2 | 0 | 2 | 0
HDR | 2 | 2020-05 | A15 | GIS | 0% | 3 | 0 | 3 | 0
HDR | 2 | 2020-05 | A15 | GIS | 0% | 4 | 0 | 4 | 0
HDR | 2 | 2020-05 | A15 | GIS | 0% | 5 | 0 | 5 | 0
HDR | 2 | 2020-05 | A16 | Document Management | 55.56% | 1 | Provided technical editing for reports and presentations. | 1 | Provide as-needed technical edfiting and document management.
HDR | 2 | 2020-05 | A16 | Document Management | 0% | 2 | 0 | 2 | 0
HDR | 2 | 2020-05 | A16 | Document Management | 0% | 3 | 0 | 3 | 0
HDR | 2 | 2020-05 | A16 | Document Management | 0% | 4 | 0 | 4 | 0
HDR | 2 | 2020-05 | A16 | Document Management | 0% | 5 | 0 | 5 | 0
HDR | 2 | 2020-05 | A17 | Staff Support | 55.56% | 1 | No work performed. | 1 | Provide as-needed graphics support and figure/maps creation.
HDR | 2 | 2020-05 | A17 | Staff Support | 0% | 2 | 0 | 2 | 0
HDR | 2 | 2020-05 | A17 | Staff Support | 0% | 3 | 0 | 3 | 0
HDR | 2 | 2020-05 | A17 | Staff Support | 0% | 4 | 0 | 4 | 0
HDR | 2 | 2020-05 | A17 | Staff Support | 0% | 5 | 0 | 5 | 0
HDR | 2 | 2020-05 | A18 | Satellite Project Office | 100% | 1 | No work authorized under Task Order. | 1 | No work authorized under Task Order.
HDR | 2 | 2020-05 | A18 | Satellite Project Office | 0% | 2 | 0 | 2 | 0
HDR | 2 | 2020-05 | A18 | Satellite Project Office | 0% | 3 | 0 | 3 | 0
HDR | 2 | 2020-05 | A18 | Satellite Project Office | 0% | 4 | 0 | 4 | 0
HDR | 2 | 2020-05 | A18 | Satellite Project Office | 0% | 5 | 0 | 5 | 0
HDR | 2 | 2020-05 | A19 | Land Conservation Approach | 100% | 1 | No work authorized under Task Order. | 1 | No work authorized under Task Order.
HDR | 2 | 2020-05 | A19 | Land Conservation Approach | 0% | 2 | 0 | 2 | 0
HDR | 2 | 2020-05 | A19 | Land Conservation Approach | 0% | 3 | 0 | 3 | 0
HDR | 2 | 2020-05 | A19 | Land Conservation Approach | 0% | 4 | 0 | 4 | 0
HDR | 2 | 2020-05 | A19 | Land Conservation Approach | 0% | 5 | 0 | 5 | 0
HDR | 2 | 2020-05 | A98 | HDR Project Management | 55.56% | 1 | Prepared monthly invoice and MPR. | 1 | Continue with all project management activities.
HDR | 2 | 2020-05 | A98 | HDR Project Management | 0% | 2 | Submitted weekly burn rate data to controls and monitored burn rate with team leads. | 2 | 0
HDR | 2 | 2020-05 | A98 | HDR Project Management | 0% | 3 | 0 | 3 | 0
HDR | 2 | 2020-05 | A98 | HDR Project Management | 0% | 4 | 0 | 4 | 0
HDR | 2 | 2020-05 | A98 | HDR Project Management | 0% | 5 | 0 | 5 | 0
HDR | 2 | 2020-05 | A99 | Expenses | 55.56% | 1 | Submitted typical project expenses. | 1 | Continue to submit expenses.
HDR | 2 | 2020-05 | A99 | Expenses | 0% | 2 | 0 | 2 | 0
HDR | 2 | 2020-05 | A99 | Expenses | 0% | 3 | 0 | 3 | 0
HDR | 2 | 2020-05 | A99 |  | 0% | 4 | 0 | 4 | 0
HDR | 2 | 2020-05 | A99 |  | 0% | 5 | 0 | 5 | 0

## Output-Issues (hidden)
Firm | Phase | Period | # | Issues / Challenges | Approach to Resolving or Mitigating Issues | Budget | Schedule | Scope | Completed | Comments
HDR | 2 | 2020-05 | 1 | The 2020-2021 Work Plan has required significant effort that was not budgeted for. | Monitor overall weekly HDR burn rate. Determine if existing budget within HDR's contract can be transferred to this task. | 1 | 0 | 1 | 1 | No longer applicable.
HDR | 2 | 2020-05 | 2 | Assembling pieces of existing CAD/GIS data from various sources and incorporating in to master dataset. | Tracking data collection efforts and prioritizing important data for conversion to GIS (from CAD). | 1 | 1 | 1 | 1 | Sent ICF facilities footprint layer for permanent impacts
HDR | 2 | 2020-05 | 3 | Lack of clarity among all parties involved in Affordability Analysis (e.g., what scenarios are needed, who is responsible for which pieces). | Establish a schedule for the effort and a single source of responsibility (Lee Frederiksen). | 1 | 0 | 1 | 1 | This effort is nearing completion
HDR | 2 | 2020-05 | 4 | Work requested for coordination with USBR regarding 2019 geotechnical work was not anticipated. | Propose removing work associated with Fugro's 2019 GIWP development and re-purposing for USBR coordination. | 1 | 0 | 1 | 1 | No longer applicable.
HDR | 2 | 2020-05 | 5 | The percent of work complete was not updated for October due to changing scope and budgets. | It is expected that task orders will be revised before the end of the year, at which time HDR can rebaseline. | 1 | 1 | 1 | 1 | No longer applicable.
HDR | 2 | 2020-05 | 6 | 0 | 0 | 0 | 0 | 0 | 0
HDR | 2 | 2020-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HDR | 2 | 2020-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HDR | 2 | 2020-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HDR | 2 | 2020-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HDR | 2 | 2020-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HDR | 2 | 2020-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HDR | 2 | 2020-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HDR | 2 | 2020-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HDR | 2 | 2020-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HDR | 2 | 2020-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HDR | 2 | 2020-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HDR | 2 | 2020-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HDR | 2 | 2020-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HDR | 2 | 2020-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HDR | 2 | 2020-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Setup (hidden)
Service Areas
Service Area |  | Service_Areas | Service_ID | Service_Code | Firm_ID | Authority_Agent | PI_Lead
a) Project Integration |  | a) Project Integration | A | INT | HDR | Trapasso | John Buttz
|  | b) Project Controls | B | PCO | BC | Trapasso | Cathy Westcot
Consultant |  | c) Communications and Public Outreach | C | COM | K&A | Spesert | Kim Pallari
HDR | a-HDR | d) Operations Simulation Modeling | D | OPS | CH2-d | Rob Thomson | Steve Weaver
|  | e) Environmental Planning and Analysis | E | ENV | ICF-e | Rob Thomson | Laurie Warner Herson
Work Period |  | f) Permitting Agreeements | F | PER | ICF-f | Rob Thomson | John Spranza
2020-05 |  | g) Real Estate | G | ROW | BRI | Spesert | Erin Heydinger
|  | h) Engineering | H | ENG | TBD | TBD | Lee Frederiksen
Filename |  | i) Geotechnical Engineering | I | GEO | FUG | Jim Watson | Chris Krivanec
https://sitesreservoirproject.sharepoint.com/projectintegration/HDR Business Documents/Invoices and Monthly Reports/Task Order 2/2020-5 May/[Monthly Progress Template HDR 2020-05.xlsx]b) Task Work
Work / Billing Periods
2019-01
2019-02
2019-03
2019-04
2019-05
2019-06
2019-07
2019-08
2019-09
2019-10
2019-11
2019-12
2020-01
2020-02
2020-03
2020-04
2020-05
2020-06
2020-07
2020-08
2020-09
2020-10
2020-11
2020-12
TaskCount
21
Phase
2
DeliverableCount
22

## vw_Deliverables_wVendorTaskId (hidden)
ID | Phase | Vendor_Alpha | Service_Area | Task_Number | Vendor_TaskID | Type | Deliverable_ID | Name | Original_Completion | Current_Completion | Plan | Status
157 | 2 | HDR | A | A02 | A02 | PLN | PLN04 | Draft Operations Plan |  |  | Work Plan 1b | Active
163 | 2 | HDR | A | A08 | A08 | APP | APP01 | Application for Financial Assistance to Reclamation |  |  | Work Plan 1b | Active
161 | 2 | HDR | A | A08 | A08 | PLN | PLN05 | Amendment 1B work Plan |  |  | Work Plan 1b | Active
162 | 2 | HDR | A | A08 | A08 | PLN | PLN06 | Amendment 2 work plan |  |  | Work Plan 1b | Active
164 | 2 | HDR | A | A08 | A08 | TMS | TMS16 | WIFIA Letter of Interest Strategy Memo |  |  | Work Plan 1b | Active
274 | 2 | HDR | A | A13 | A13 | TMS | TMS15 | Risk Workshop Outcomes TM |  |  | Work Plan 1b | Active
2 | 2 | HDR | A | A03 | A03 | SYS | SYS01 | Environmental Tracking Tool |  |  |  | Completed
1 | 2 | HDR | A | A03 | A03 | TMS | TMS11 | Environmental QA/QC process |  |  |  | Completed
3 | 2 | HDR | A | A04 | A04 | SCH | SCH01 | Permitting Schedule | 2019-07-01 | 2019-07-01 |  | Completed
7 | 2 | HDR | A | A08 | A08 | SCH | SCH02 | Governance Meetings calendar | 2019-05-01 | 2019-05-01 |  | Completed
6 | 2 | HDR | A | A08 | A08 | SYS | SYS02 | Smartsheet for Res Committee and Board Items | 2019-05-01 | 2019-05-01 |  | Completed
8 | 2 | HDR | A | A11 | A11 | TMS | TMS14 | Field Trip Safety TM | 2019-06-01 | 2019-07-01 |  | Completed
10 | 2 | HDR | A | A14 | A14 | SYS | SYS03 | GIS ROW Tool - Desktop and Mobile Apps | 2019-06-12 | 2019-06-12 |  | Completed
11 | 2 | HDR | A | A15 | A15 | PLN | PLN02 | GIS Plan | 2019-07-01 | 2019-07-01 |  | Completed
12 | 2 | HDR | A | A15 | A15 | SYS | SYS04 | GIS Database | 2019-06-01 | 2019-06-01 |  | Completed
14 | 2 | HDR | A | A15 | A15 | SYS | SYS06 | GIS Map Templates | 2019-06-30 | 2019-06-30 |  | Completed
16 | 2 | HDR | A | A16 | A16 | SYS | SYS07 | TO2 Deliverables Documents Library | 2019-05-17 | 2019-06-14 |  | Completed
4 | 2 | HDR | A | A06 | A06 | TMS | TMS12 | Procurement Approach TM | 2019-09-01 | 2019-09-01 |  | Obsolete
5 | 2 | HDR | A | A07 | A07 | TMS | TMS13 | Review comments on 2019 GIWP | 2019-07-31 | 2019-07-31 |  | Obsolete
9 | 2 | HDR | A | A14 | A14 | PLN | PLN01 | 2019 IT Plan | 2019-07-01 | 2019-07-01 |  | Paused
13 | 2 | HDR | A | A15 | A15 | SYS | SYS05 | Project GIS web-viewer | 2019-06-01 | 2019-06-21 |  | Paused
15 | 2 | HDR | A | A16 | A16 | PLN | PLN03 | Document Management Plan (final) | 2019-04-30 | 2019-06-14 |  | Paused
136 | 1 | HDR | A |  |  | IMG | IMG01 | Quick Start Plan
130 | 1 | HDR | A |  |  | IMG | IMG02 | 2019 Committee and Work Group Structure
131 | 1 | HDR | A |  |  | IMG | IMG03 | Phase 2A Organization Chart
132 | 1 | HDR | A |  |  | IMG | IMG04 | Document Management Flowchart
133 | 1 | HDR | A |  |  | IMG | IMG05 | Staff Approval Process
134 | 1 | HDR | A |  |  | IMG | IMG06 | Monthly Reservoir Committee and Board Meeting Cycle
135 | 1 | HDR | A |  |  | IMG | IMG07 | New Staff Guide Outline
129 | 1 | HDR | A |  |  | MEM | MEM01 | File naming convention
117 | 1 | HDR | A |  |  | PMA | PMA02 | Matrix of Authority Draft
112 | 1 | HDR | A |  |  | PMA | PMA03 | Document Management Plan Draft
113 | 1 | HDR | A |  |  | PMA | PMA04 | Internal Communications Plan Outline Draft
114 | 1 | HDR | A |  |  | PMA | PMA05 | Engineering Management Section Outline Draft
118 | 1 | HDR | A |  |  | PMA | PMA12 | QMP for Environmental Planning and Permitting Draft
115 | 1 | HDR | A |  |  | PMA | PMA13 | Staff Approval Process Draft
116 | 1 | HDR | A |  |  | PMB | PMB04 | IT and GIS Plan Outline Draft
110 | 1 | HDR | A |  |  | PMP | PMP00
111 | 1 | HDR | A |  |  | PMA | PMP01 | Project Management Plan Outline
137 | 1 | HDR | A |  |  | PRE | PRE01 | Right-of-Way Process Draft
128 | 1 | HDR | A |  |  | TMS | TMS01
119 | 1 | HDR | A |  |  | TMS | TMS02 | Environmental Team Communication Protocols Draft
120 | 1 | HDR | A |  |  | TMS | TMS03 | Project Breakdown Structure Draft
121 | 1 | HDR | A |  |  | TMS | TMS04 | Special Studies Plan
122 | 1 | HDR | A |  |  | TMS | TMS05 | Initial IT and SharePoint Setup Draft
123 | 1 | HDR | A |  |  | TMS | TMS06 | Natomas Office Support Draft
124 | 1 | HDR | A |  |  | TMS | TMS10 | Staff Support Plan Draft
21 | 2 | BC | B | B01 | B1 | SYS | SYS03 | Board-Level MPR | 2019-06-12 | 2019-06-12 |  | Active
22 | 2 | BC | B | B01 | B1 | SYS | SYS04 | Commitments Worksheet | 2019-06-12 | 2019-06-12 |  | Active
275 | 2 | BC | B | B02 | B2 | INV | INV01 | CWC Invoice/Progress Report No 4 |  |  | Work Plan 1b | Active
276 | 2 | BC | B | B02 | B2 | INV | INV02 | CWC Invoice/Progress Report No 5 |  |  | Work Plan 1b | Active
30 | 2 | BC | B | B02 | B2 | PRO | PRO05 | Task Order Approval Process | 2019-07-31 | 2019-07-31 |  | Active
277 | 2 | BC | B | B02 | B2 | REP | REP01 | CWC Quarterly Report No 6 |  |  | Work Plan 1b | Active
278 | 2 | BC | B | B02 | B2 | REP | REP02 | CWC Quarterly Report No 7 |  |  | Work Plan 1b | Active
279 | 2 | BC | B | B02 | B2 | REP | REP03 | CWC Eligibility Memo |  |  | Work Plan 1b | Active
281 | 2 | BC | B | B02 | B2 | REP | REP04 | 2019 Sites Project Annual Status Report |  |  | Work Plan 1b | Active
282 | 2 | BC | B | B02 | B2 | REP | REP05 | 2019 Consultant Progress Report |  |  | Work Plan 1b | Active
280 | 2 | BC | B | B02 | B2 | TMS | TMS05 | Draft Dry Year Supply TM |  |  | Work Plan 1b | Active
285 | 2 | BC | B | B03 | B3 | PLN | PLN01 | Amendment 1B Work Plan |  |  | Work Plan 1b | Active
286 | 2 | BC | B | B03 | B3 | PLN | PLN02 | Amendment 2 Work Plan |  |  | Work Plan 1b | Active
23 | 2 | BC | B | B01 | B1 | PRO | PRO01 | Process Diagram for Data Entry | 2019-06-28 | 2019-06-28 |  | Completed
24 | 2 | BC | B | B01 | B1 | PRO | PRO02 | Process Map for Reporting Approval Workflow | 2019-07-26 | 2019-07-26 |  | Completed
17 | 2 | BC | B | B01 | B1 | SYS | SYS01 | Data Dictionary | 2019-12-31 | 2019-12-31 |  | Completed
20 | 2 | BC | B | B01 | B1 | SYS | SYS02 | Reporting Database | 2019-06-21 | 2019-06-21 |  | Completed
18 | 2 | BC | B | B01 | B1 | TEM | TEM01 | Consultant-Level MPR | 2019-05-15 | 2019-05-15 |  | Completed
19 | 2 | BC | B | B01 | B1 | TEM | TEM02 | Task Order Template | 2019-06-12 | 2019-06-12 |  | Completed
25 | 2 | BC | B | B01 | B1 | TMS | TMS11 | Initial Business Reports Set | 2019-06-12 | 2019-06-12 |  | Completed
31 | 2 | BC | B | B02 | B2 | PRO | PRO06 | Task Order Close Process | 2019-07-31 | 2019-07-31 |  | Completed
32 | 2 | BC | B | B02 | B2 | PRO | PRO07 | Staff Approval Process | 2019-07-31 | 2019-07-31 |  | Completed
34 | 2 | BC | B | B02 | B2 | TEM | TEM03 | Monthly templates for CWC | 2019-04-30 | 2019-04-30 |  | Completed
26 | 2 | BC | B | B01 | B1 | TMS | TMS03 | PMIS Selection Factor TM | 2019-07-15 | 2019-07-15 |  | Paused
27 | 2 | BC | B | B01 | B1 | TMS | TMS04 | PMIS Package Survey | 2019-07-15 | 2019-07-15 |  | Paused
28 | 2 | BC | B | B02 | B2 | PRO | PRO03 | Consultant Agreement Approval Process | 2019-07-31 | 2019-07-31 |  | Paused
29 | 2 | BC | B | B02 | B2 | PRO | PRO04 | Consulting Agreement Change Process | 2019-07-31 | 2019-07-31 |  | Paused
33 | 2 | BC | B | B02 | B2 | PRO | PRO08 | New Subconsultant Approval Process | 2019-07-31 | 2019-07-31 |  | Paused
35 | 2 | BC | B | B03 | B3 | SCH | SCH01 | Master program schedule and activity database (2019) | 2019-08-30 | 2019-08-30 |  | Paused
36 | 2 | BC | B | B03 | B3 | SCH | SCH02 | Master activity database (2019) | 2019-08-30 | 2019-08-30 |  | Paused
39 | 2 | BC | B | B05 | B5 | PMA | PMA01 | Contract Administration Plan - Process Flow Diagram/Short Narrative | 2019-07-31 | 2019-07-31 |  | Paused
38 | 2 | BC | B | B05 | B5 | PMA | PMA07 | Cost Management Plan - Process Flow Diagram/Short Narrative | 2019-07-31 | 2019-07-31 |  | Paused
138 | 1 | BC | B | B01 | B1 | TMS | TMS01 | PMIS Evaluation and Workplan Draft
145 | 1 | BC | B | B05 | B5 | PMA | PMA02 | Change Management Plan
37 | 2 | BC | B | B05 | B5 | PMA | PMA06 | Schedule Management Plan -Process Flow Diagram/Short Narrative | 2019-07-31 | 2019-07-31
287 |  | K&A | C | C01 | C1.1 | NWS | NWS05 | Landowner Newsletter 1 |  |  | Work Plan 1b | Active
288 |  | K&A | C | C01 | C1.1 | NWS | NWS06 | Landowner Newsletter 2 |  |  | Work Plan 1b | Active
41 | 2 | K&A | C | C01 | C1.1 | SYS | SYS02 | Database Update No. 2 (local) | 2019-12-01 | 2019-12-01 |  | Active
48 | 2 | K&A | C | C02 | C1.2 | SCH | SCH01 | Outreach Calendar | 2019-12-31 | 2019-12-31 |  | Active
46 | 2 | K&A | C | C02 | C1.2 | SYS | SYS04 | Database Update No. 2 (state) | 2019-12-01 | 2019-12-01 |  | Active
59 | 2 | K&A | C | C11 | C7.1 | REP | REP02 | Phase 2A Summary of Social Media Engagement | 2019-12-31 | 2019-12-31 |  | Active
43 | 2 | K&A | C | C01 | C1.1 | NWS | NWS01 | Newsletter No. 1 | 2019-07-01 | 2019-07-01 |  | Completed
44 | 2 | K&A | C | C01 | C1.1 | NWS | NWS02 | Newsletter No. 2 | 2019-10-01 | 2019-10-01 |  | Completed
40 | 2 | K&A | C | C01 | C1.1 | SYS | SYS01 | Database Update No. 1 (local) | 2019-08-01 | 2019-08-01 |  | Completed
45 | 2 | K&A | C | C02 | C1.2 | SYS | SYS03 | Database Update No. 1 (state) | 2019-08-01 | 2019-08-01 |  | Completed
47 | 2 | K&A | C | C02 | C1.2 | TEM | TEM01 | Stakeholder Toolkit | 2019-07-01 | 2019-07-01 |  | Completed
49 | 2 | K&A | C | C05 | C2.2 | PLN | PLN02 | Updated message platform No. 1 |  |  |  | Completed
50 | 2 | K&A | C | C05 | C2.2 | PLN | PLN03 | Updated message platform No. 2 |  |  |  | Completed
53 | 2 | K&A | C | C06 | C3.1 | NWS | NWS03 | Email Blast No. 1 | 2019-07-01 | 2019-07-01 |  | Completed
54 | 2 | K&A | C | C06 | C3.1 | NWS | NWS04 | Email Blast No. 2 | 2019-11-01 | 2019-11-01 |  | Completed
52 | 2 | K&A | C | C06 | C3.1 | TEM | TEM02 | Branding Templates | 2019-05-01 | 2019-05-01 |  | Completed
55 | 2 | K&A | C | C06 | C3.1 | TEM | TEM03 | PowerPoint Template - Programmatic | 2019-05-15 | 2019-05-15 |  | Completed
56 | 2 | K&A | C | C06 | C3.1 | TEM | TEM04 | PowerPoint Template - Topic-Specific | 2019-09-15 | 2019-09-15 |  | Completed
57 | 2 | K&A | C | C07 | C4.1 | SYS | SYS05 | Website Transitioned | 2019-06-01 | 2019-06-01 |  | Completed
58 | 2 | K&A | C | C09 | C5.1 | REP | REP01 | Media List | 2019-07-01 | 2019-07-01 |  | Completed
42 | 2 | K&A | C | C01 | C1.1 | PLN | PLN01 | Landowner Engagement Plan | 2019-09-01 | 2019-09-01 |  | Paused
51 | 2 | K&A | C | C05 | C2.2 | TRA | TRA01 | Speaker Training | 2019-08-01 | 2019-08-01 |  | Paused
61 | 2 | CH2-d | D | D01 | D1 | PER | PER01 | CalSim results for permits | 2019-08-23 | 2019-08-23 |  | Active
60 | 2 | CH2-d | D | D01 | D1 | TMS | TMS01 | Daily modeling analysis results and TM (permitting) | 2019-08-23 | 2019-08-23 |  | Active
217 | 2 | CH2-d | D | D02 | D2 | TMS | TMS07 | Modeling Methodology/Assumptions TM |  |  | Work Plan 1b | Active
219 | 2 | CH2-d | D | D03 | D3 | MOD | MOD02 | CE-Qual-W2 Modeling Files |  |  | Work Plan 1b | Active
218 | 2 | CH2-d | D | D03 | D3 | TMS | TMS08 | Reservoir Water Quality Modeling Development TM |  |  | Work Plan 1b | Active
221 | 2 | CH2-d | D | D03 | D3 | TMS | TMS09 | Operations Project Description TM |  |  | Work Plan 1b | Active
68 | 2 | CH2-d | D | D98 | D4 | PRE | PRE01 | Ops Work Group Presentation (ops rebalancing) | 2019-07-08 | 2019-07-08 |  | Active
70 | 2 | CH2-d | D | D98 | D4 | PRE | PRE02 | Ops Work Group Presentation (ops technical support) | 2019-07-08 | 2019-07-08 |  | Active
69 | 2 | CH2-d | D | D98 | D4 | TMS | TMS05 | Ops Rebalancing results and TM | 2019-07-08 | 2019-07-08 |  | Active
71 | 2 | CH2-d | D | D98 | D4 | TMS | TMS06 | Ops Technical Support TM | 2019-12-31 | 2019-12-31 |  | Active
62 | 2 | CH2-d | D | D01 | D1 | PER | PER02 | Side-channel habitat results for permits | 2019-08-23 | 2019-08-23 |  | Paused
64 | 2 | CH2-d | D | D02 | D2 | EIR | EIR01 | CalSim results for EIR/S | 2019-10-25 | 2019-10-25 |  | Paused
63 | 2 | CH2-d | D | D02 | D2 | TMS | TMS02 | Analytical Framework and Tools TM (environmental) | 2019-10-25 | 2019-10-25 |  | Paused
65 | 2 | CH2-d | D | D02 | D2 | TMS | TMS03 | Modeling analysis results and TM (environmental) | 2019-10-25 | 2019-10-25 |  | Paused
66 | 2 | CH2-d | D | D03 | D3 | MOD | MOD01 | CE-QUAL-W2 modeling files | 2019-08-02 | 2019-08-02 |  | Paused
67 | 2 | CH2-d | D | D03 | D3 | TMS | TMS04 | Water Quality Modeling results and TM | 2019-08-02 | 2019-08-02 |  | Paused
260 | 2 | ICF-e | E | E07 | E07 | EIR | EIR11 | Draft EIR/EIS Project Description Chapter |  |  | Work Plan 1b | Active
222 | 2 | ICF-e | E | E07 | E07 | PLN | PLN01 | EIR/EIS Work Plan |  |  | Work Plan 1b | Active
223 | 2 | ICF-e | E | E09 | E09 | EIR | EIR09 | Draft Annotated Outline for Recirculated Environmental document |  |  | Work Plan 1b | Active
224 | 2 | ICF-e | E | E09 | E09 | EIR | EIR10 | Draft Introductory Language Document for Recirculated Environmental document |  |  | Work Plan 1b | Active
77 | 2 | ICF-e | E | E03 | E3 | SYS | SYS01 | Comment Response Tracking Tool | 2019-05-31 | 2019-05-31 |  | Completed
81 | 2 | ICF-e | E | E06 | E6 | REP | EIR08 | Final EA/IS (Geotech) | 2019-08-28 | 2019-08-28 |  | Completed
79 | 2 | ICF-e | E | E06 | E6 | TMS | TMS01 | Cultural Resources TM | 2019-06-17 | 2019-06-17 |  | Completed
72 | 2 | ICF-e | E | E01 | E1 | EIR | EIR01 | EIR/EIS Strategy Meeting | 2019-06-28 | 2019-06-28 |  | Obsolete
73 | 2 | ICF-e | E | E02 | E2 | EIR | EIR02 | Admin Final EIR/EIS Master Responses | 2019-07-31 | 2019-07-31 |  | Obsolete
74 | 2 | ICF-e | E | E02 | E2 | EIR | EIR03 | Admin Final EIR/EIS Comment Response Table No. 1 | 2019-06-28 | 2019-06-28 |  | Obsolete
75 | 2 | ICF-e | E | E02 | E2 | EIR | EIR04 | Admin Final EIR/EIS Comment Response Table No. 2 | 2019-07-31 | 2019-07-31 |  | Obsolete
76 | 2 | ICF-e | E | E03 | E3 | REP | EIR05 | Admin Final EIR/EIS | 2019-12-31 | 2019-12-31 |  | Obsolete
78 | 2 | ICF-e | E | E04 | E4 | EIR | EIR06 | Admin Record for Final EIR/EIS | 2019-12-31 | 2019-12-31 |  | Obsolete
80 | 2 | ICF-e | E | E06 | E6 | EIR | EIR07 | Errata sheet for EA/IS | 2019-08-22 | 2019-08-22 |  | Obsolete
297 | 2 | ICF-f | F | F02 | F2 | REP | REP11 | Geotechnical Monitoring and required Reporting for Federal Feasibility Study |  |  | Work Plan 1b | Active
310 | 2 | ICF-f | F | F02 | F2 | REP | REP19 | Updated Terrestrial Temporary and Permanent Impact Acreage |  |  | Work Plan 1b | Active
298 | 2 | ICF-f | F | F07 | F07 | PER | PER08 | Clean water Act 404 and 401 Permit (Draft) |  |  | Work Plan 1b | Active
302 | 2 | ICF-f | F | F07 | F07 | PER | PER09 | Clean water Act 404 and 401 Permit (Final) |  |  | Work Plan 1b | Active
308 | 2 | ICF-f | F | F07 | F07 | PER | PER10 | Agreement with USACE on Approach for 404/408, wetland delineation and 404(b)(1) |  |  | Work Plan 1b | Active
307 | 2 | ICF-f | F | F07 | F07 | PLN | PLN04 | Draft and Final Preliminary Section 106 Action Plan |  |  | Work Plan 1b | Active
299 | 2 | ICF-f | F | F07 | F07 | REP | REP12 | CDFW Lake and Streambed Agreement-Standard (Draft) |  |  | Work Plan 1b | Active
300 | 2 | ICF-f | F | F07 | F07 | REP | REP13 | USFWS Amended Biological Assessment (Draft) |  |  | Work Plan 1b | Active
301 | 2 | ICF-f | F | F07 | F07 | REP | REP14 | Section 106 Historic Properties Identification and Assessment (Draft) |  |  | Work Plan 1b | Active
303 | 2 | ICF-f | F | F07 | F07 | REP | REP15 | CDFW Lake and Streambed Agreement-Standard (Final) |  |  | Work Plan 1b | Active
304 | 2 | ICF-f | F | F07 | F07 | REP | REP16 | USFWS Amended Biological Assessment (Final) |  |  | Work Plan 1b | Active
305 | 2 | ICF-f | F | F07 | F07 | REP | REP17 | Section 106 Historic Properties Identification and Assessment (Final) |  |  | Work Plan 1b | Active
309 | 2 | ICF-f | F | F07 | F07 | REP | REP18 | Updated BA Project Description |  |  | Work Plan 1b | Active
306 | 2 | ICF-f | F | F07 | F07 | TMS | TMS06 | Brief Memorandum detailing results of Task F07: Early coordination and Development of Key Permits. |  |  | Work Plan 1b | Active
82 | 2 | ICF-f | F | F01 | F1 | REP | REP01 | Draft Species Accounts for Project | 2019-06-30 | 2019-06-30 |  | Completed
148 | 2 | ICF-f | F | F02 | F2 | REP | REP05 | Geotech Section 106 Historic Properties Report (Final) |  |  |  | Completed
92 | 2 | ICF-f | F | F02 | F2 | REP | REP06 | Geotech Joint Biological Assessment for NMFS and USFWS | 2019-06-17 | 2019-06-17 |  | Completed
93 | 2 | ICF-f | F | F03 | F3 | PLN | PLN01 | Public Involvement & Tribal Consultation Plan (Preliminary Draft) | 2019-08-15 | 2019-08-15 |  | Completed
85 | 2 | ICF-f | F | F02 | F2 | LET | LET01 | Geotech Section 106 Initiation Letter (Draft) | 2019-06-17 | 2019-06-17 |  | Obsolete
147 | 2 | ICF-f | F | F02 | F2 | LET | LET02 | Geotech Section 106 Initiation Letter (Final) |  |  |  | Obsolete
90 | 2 | ICF-f | F | F02 | F2 | PER | PER04 | Geotech Documentation for Section 408 approval | 2019-06-19 | 2019-06-19 |  | Obsolete
91 | 2 | ICF-f | F | F02 | F2 | PER | PER05 | Geotech Encroachment permit application (CVFPB) | 2019-06-19 | 2019-06-19 |  | Obsolete
152 | 2 | ICF-f | F | F02 | F2 | PER | PER06 | State Lands Permit Geotech | 2019-06-19 | 2019-06-19 |  | Obsolete
86 | 2 | ICF-f | F | F02 | F2 | REP | REP04 | Geotech Section 106 Historic Properties Report (Draft) | 2019-06-17 | 2019-06-17 |  | Obsolete
149 | 2 | ICF-f | F | F03 | F3 | PLN | PLN02 | Public Involvement & Tribal Consultation Plan (Draft) |  |  |  | Obsolete
150 | 2 | ICF-f | F | F03 | F3 | PLN | PLN03 | Public Involvement & Tribal Consultation Plan (Final) |  |  |  | Obsolete
94 | 2 | ICF-f | F | F03 | F3 | REP | REP07 | Draft Archeological Resources Inventory Report | 2019-11-11 | 2019-11-11 |  | Obsolete
95 | 2 | ICF-f | F | F03 | F3 | REP | REP08 | Draft Built Environmental Inventory/Evaluation Report | 2019-11-11 | 2019-11-11 |  | Obsolete
83 | 2 | ICF-f | F | F01 | F1 | REP | REP02 | Draft Biological Assessment for Project | 2019-06-30 | 2019-06-30 |  | Paused
84 | 2 | ICF-f | F | F01 | F1 | REP | REP03 | Final Biological Assessment for Project | 2019-09-30 | 2019-09-30 |  | Paused
87 | 2 | ICF-f | F | F02 | F2 | PER | PER01 | Geotech CWA Section 404 Permit Application | 2019-06-19 | 2019-06-19 |  | Paused
88 | 2 | ICF-f | F | F02 | F2 | PER | PER02 | Geotech CWA Section 401 Permit Application | 2019-06-19 | 2019-06-19 |  | Paused
89 | 2 | ICF-f | F | F02 | F2 | PER | PER03 | Geotech Lake or Streambed Alteration Application Packet | 2019-06-19 | 2019-06-19 |  | Paused
151 | 2 | ICF-f | F | F03 | F3 | REP | REP09 | Concept Memo for PA Approach
96 | 2 | ICF-f | F | F03 | F3 | TMS | TMS01 | Draft Programmatic Agreement | 2019-11-11 | 2019-11-11
155 | 2 | ICF-f | F | F04 | F4 | PER | PER07 | 208/ITP (Draft) | 2019-12-31 | 2019-12-31
98 | 2 | ICF-f | F | F04 | F4 | TMS | TMS02 | Permitting Approach TM | 2019-12-31 | 2019-12-31
153 | 2 | ICF-f | F | F04 | F4 | TMS | TMS04 | Corps Permit Approach Memo
100 | 2 | ICF-f | F | F05 | F5 | REP | REP10 | Parcel spreadsheet for survey access | 2019-06-15 | 2019-06-15
154 | 2 | ICF-f | F | F05 | F5 | TMS | TMS05 | Field Survey Plans Bio
101 | 2 | ICF-f | F | F06 | F6 | TMS | TMS03 | Mitigation Approach TM | 2019-12-31 | 2019-12-31
102 | 2 | BRI | G | G03 | G3.1 | SYS | SYS01 | Line List | 2019-12-31 | 2019-12-31
103 | 2 | BRI | G | G04 | G4.1 | PLN | PLN01 | Property Management Plan (1) | 2019-12-31 | 2019-12-31
104 | 2 | BRI | G | G04 | G4.1 | PLN | PLN02 | Acquired Property Disposition Plan (1) | 2019-12-31 | 2019-12-31
140 | 1 | BRI | G |  |  | TMS | TMS01 | Compensation Protocol Draft
141 | 1 | BRI | G |  |  | TMS | TMS02 | Delegation and Approval Draft
142 | 1 | BRI | G |  |  | TMS | TMS03 | Notice To Proceed and Authorization Process Draft
143 | 1 | BRI | G |  |  | TMS | TMS04 | Policies and Procedures Workshop Draft
144 | 1 | BRI | G |  |  | TMS | TMS05 | Programmatic Negotiations Policies Draft
311 | 2 | FUG | I | I05 | I5 | PLN | PLN02 | Site Plan with Proposed Borings |  |  | Work Plan 1b | Active
312 | 2 | FUG | I | I05 | I5 | PLN | PLN03 | Field Data Collection Work Plan/Cost Estimate |  |  | Work Plan 1b | Active
105 | 2 | FUG | I | I01 | I1 | REP | REP01 | Documents Reviewed Tabulation | 2019-06-30 | 2019-06-30 |  | Completed
106 | 2 | FUG | I | I01 | I1 | REP | REP02 | Geologic & Geotechnical Data Requirements Tabulation | 2019-06-30 | 2019-06-30 |  | Completed
107 | 2 | FUG | I | I01 | I1 | SYS | SYS01 | Historic Boring Location GIS Layer | 2019-06-30 | 2019-06-30 |  | Completed
108 | 2 | FUG | I | I01 | I1 | PLN | PLN01 | Feasibility Study Field Investigation Work Plan | 2019-07-30 | 2019-07-30 |  | Obsolete

## vw_ConsultantTaskItems (hidden)
ID | VendorAlpha | Phase | Task | Status | Description | FullID | FullID2
22 | BC | 2 | B01 |  | Project Controls | B-BC | BC-B01
23 | BC | 2 | B02 |  | Contract Administration and Compliance | B-BC | BC-B02
24 | BC | 2 | B03 |  | Work Planning and Scheduling | B-BC | BC-B03
25 | BC | 2 | B04 |  | Project Administrative Support | B-BC | BC-B04
26 | BC | 2 | B05 |  | PMP Sections | B-BC | BC-B05
27 | BC | 2 | B98 |  | Project Management | B-BC | BC-B98
28 | BC | 2 | B99 |  | Expenses | B-BC | BC-B99
29 | BRI | 2 | G01 |  | Develop Draft Right-of-Way Manual Sections | G-BRI | BRI-G01
30 | BRI | 2 | G02 |  | Right-of-Way Planning Efforts | G-BRI | BRI-G02
31 | BRI | 2 | G03 |  | Right-of-Entry / Early-Access Program | G-BRI | BRI-G03
32 | BRI | 2 | G04 |  | Property Management Program | G-BRI | BRI-G04
33 | BRI | 2 | G05 |  | Public Outreach and Community Engagement | G-BRI | BRI-G05
34 | BRI | 2 | G98 |  | Project Management / QC | G-BRI | BRI-G98.1
36 | BRI | 2 | G99 |  | Expenses | G-BRI | BRI-G99.1
50 | CH2-d | 2 | D01 |  | Permitting and Resource Agency Technical Support | D-CH2-d | CH2-d-D01
51 | CH2-d | 2 | D02 |  | Environmental Document Support | D-CH2-d | CH2-d-D02
52 | CH2-d | 2 | D03 |  | Total Operations Technical Support | D-CH2-d | CH2-d-D03
77 | CH2-d | 2 | D04 |  | Value Planning | D-CH2-d | CH2-d-D04
53 | CH2-d | 2 | D98 |  | Project Management | D-CH2-d | CH2-d-D98
54 | CH2-d | 2 | D99 |  | Subs and ODCS | D-CH2-d | CH2-d-D99
55 | FUG | 2 | I01 |  | Data Review and Develop 2019 Feasibility Study Work Plan | I-FUG | FUG-I01
56 | FUG | 2 | I02 | C | - Obsolete - | I-FUG | FUG-I02
57 | FUG | 2 | I03 | C | 2019 Site Investigation | I-FUG | FUG-I03
58 | FUG | 2 | I04 | C | Future Site Investigation Work Plan for Design | I-FUG | FUG-I04
78 | FUG | 2 | I05 |  | Assessment of Proposed Field Data Collection Points | I-FUG | FUG-I05
59 | FUG | 2 | I98 |  | Project Management | I-FUG | FUG-I98
60 | FUG | 2 | I99 |  | Expenses | I-FUG | FUG-I99
1 | HDR | 2 | A01 |  | Communications Int. | A-HDR | HDR-A01
2 | HDR | 2 | A02 |  | Ops Modeling Int. | A-HDR | HDR-A02
3 | HDR | 2 | A03 |  | Env. Planning Int. | A-HDR | HDR-A03
4 | HDR | 2 | A04 |  | Permitting Int. | A-HDR | HDR-A04
5 | HDR | 2 | A05 |  | Real Estate Int. | A-HDR | HDR-A05
6 | HDR | 2 | A06 |  | Engineering Int. | A-HDR | HDR-A06
7 | HDR | 2 | A07 |  | Geotech Int. | A-HDR | HDR-A07
8 | HDR | 2 | A08 |  | Controls Int. | A-HDR | HDR-A08
9 | HDR | 2 | A09 |  | General Int. | A-HDR | HDR-A09
10 | HDR | 2 | A10 |  | Authority's Engineer | A-HDR | HDR-A10
11 | HDR | 2 | A11 |  | Health, Safety & Loss Prevention | A-HDR | HDR-A11
12 | HDR | 2 | A12 |  | Quality Management | A-HDR | HDR-A12
13 | HDR | 2 | A13 |  | Risk Management | A-HDR | HDR-A13
14 | HDR | 2 | A14 |  | IT | A-HDR | HDR-A14
15 | HDR | 2 | A15 |  | GIS | A-HDR | HDR-A15
16 | HDR | 2 | A16 |  | Document Management | A-HDR | HDR-A16
17 | HDR | 2 | A17 |  | Staff Support | A-HDR | HDR-A17
18 | HDR | 2 | A18 |  | Satellite Project Office | A-HDR | HDR-A18
19 | HDR | 2 | A19 |  | Land Conservation Approach | A-HDR | HDR-A19
20 | HDR | 2 | A98 |  | HDR Project Management | A-HDR | HDR-A98
21 | HDR | 2 | A99 |  | Expenses | A-HDR | HDR-A99
61 | ICF-e | 2 | E01 |  | Draft EIS/EIR Review and Strategic Consultation | E-ICF-e | ICF-e-E01
62 | ICF-e | 2 | E02 |  | Prepare Admin Final Responses to Comments | E-ICF-e | ICF-e-E02
63 | ICF-e | 2 | E03 |  | Prepare Administrative Final EIR/EIS | E-ICF-e | ICF-e-E03
64 | ICF-e | 2 | E04 |  | Begin Preparation of Administrative Record for Fin | E-ICF-e | ICF-e-E04
65 | ICF-e | 2 | E05 |  | Engagement | E-ICF-e | ICF-e-E05
66 | ICF-e | 2 | E06 |  | Geotechnical Environmental Document | E-ICF-e | ICF-e-E06
80 | ICF-e | 2 | E07 |  | Develop Environmental Document Work Plan | E-ICF-e | ICF-e-E99
81 | ICF-e | 2 | E08 |  | Support Development of EIR/EIS Project Description | E-ICF-e | ICF-e-E99
82 | ICF-e | 2 | E09 |  | Prepare Annotated Outline | E-ICF-e | ICF-e-E99
67 | ICF-e | 2 | E98 |  | Project Management | E-ICF-e | ICF-e-E98
68 | ICF-e | 2 | E99 |  | Expenses | E-ICF-e | ICF-e-E99
69 | ICF-f | 2 | F01 |  | Finalize Joint Biological Assessment | F-ICF-f | ICF-f-F01
70 | ICF-f | 2 | F02 |  | Finalize Geotechnical Permits and Fieldwork | F-ICF-f | ICF-f-F02
71 | ICF-f | 2 | F03 |  | Prepare Section 106 Documents | F-ICF-f | ICF-f-F03
72 | ICF-f | 2 | F04 |  | Begin Preparation of Permits and Agreements | F-ICF-f | ICF-f-F04
73 | ICF-f | 2 | F05 |  | Prepare for 2020 Field Work Studies | F-ICF-f | ICF-f-F05
74 | ICF-f | 2 | F06 |  | Strategize on Mitigation and Adaptive Management P | F-ICF-f | ICF-f-F06
79 | ICF-f | 2 | F07 |  | Early Coordination and Development of Key Permits | F-ICF-f | ICF-f-F07
75 | ICF-f | 2 | F98 |  | Project Management | F-ICF-f | ICF-f-F98
76 | ICF-f | 2 | F99 |  | Expenses | F-ICF-f | ICF-f-F99
37 | K&A | 2 | C01 |  | Local/Landowner Outreach | C-K&A | K&A-C01
38 | K&A | 2 | C02 |  | Statewide Outreach | C-K&A | K&A-C02
39 | K&A | 2 | C03 |  | NGO Outreach | C-K&A | K&A-C03
40 | K&A | 2 | C04 |  | Strategic Communications | C-K&A | K&A-C04
41 | K&A | 2 | C05 |  | Message Development/Training | C-K&A | K&A-C05
42 | K&A | 2 | C06 |  | Informational Materials Distribution | C-K&A | K&A-C06
43 | K&A | 2 | C07 |  | Website Modifications and Management | C-K&A | K&A-C07
44 | K&A | 2 | C08 |  | Video & Photography | C-K&A | K&A-C08
45 | K&A | 2 | C09 |  | Authority/Reservoir Committee Public Affairs Support | C-K&A | K&A-C09
46 | K&A | 2 | C10 |  | Media Relations | C-K&A | K&A-C10
47 | K&A | 2 | C11 |  | Social Media | C-K&A | K&A-C11
48 | K&A | 2 | C98 |  | Project Management | C-K&A | K&A-C98
49 | K&A | 2 | C99 |  | Expenses | C-K&A | K&A-C99