## Ch 1-3 Comment
Agency | Subject | Comment
USFWS | Access roads | WAPA uses access roads for maintenance and inspection of transmission lines and ROW easements (Vegetation management). Construction Access Roads do not address this use along new powerlines
USFWS | Access roads | 3. Construction Access Roads do not address this use along new powerlines. I think it should. 4. Clearing and Grubbing is not addressed along the powerline routes. I think it should.
USFWS | Access roads | WAPA has access roads for transmission lines and ROWs.
USFWS | Access roads | 1. For the New and Existing Roadways – should new access roads be included for the powerlines?
USACE | Additional information request | Add agencies
USACE | Additional information request | A brief table of all needed permit or approvals would be helpful
CDFW | Agreement review | CDFW cannot fully evaluate this project without reviewing the details of these agreements.
CDFW | Alternatives | There should be a difference between existing conditions and the “No-project” Alternative and the “No-project” Alternative should include an analysis that is comparable to the other Project Alternatives. The purpose in CEQA of the “No-project” alternative is to allow decision makers to compare the impacts of approving the proposed project with the impacts of not approving the proposed project so the impact analysis of the “No-project” alternative should include all foreseeable future impacts based on current plans and consistent with available infrastructure and community services. The existing conditions should be a set point in time (typically the NOP or the current conditions at the time of analysis), but the “No-project” Alternative would also include any future foreseeable changes in implementation of the SWP ITP and other projects that should not be included in existing conditions if they are not the current condition or baseline. CDFW commented on this in our DEIR letter that the existing conditions should more accurately reflect practice, not potential for water contractors and diverters to use their total allocation. Since we do not have the Existing Conditions section of the REIR to review, we cannot yet see how that comment was addressed.
USFWS | Alternatives | This talks about 2 alternatives at 1.3 MAF and one at 1.5 MAF and says the alternatives in the report are based on them but the alternatives in the report have 2 alternatives at 1.5 MAF and one at 1.3 MAF….so immediately confusing, at least to me. It takes a couple pages before this is explained on page 2-5…until then, it’s confusing. Consider revision.
USFWS | Alternatives | All Alternatives – Operation and Management Plans – should this include O&M of power facilities WAPA has EAs for ROW Maintenance that covers inspections, maintenance, and vegetation management.
USACE | Alternatives | I would discuss that this is not sufficient for a 404(B)(1) Alternatives report and would be provided at a different time
USACE | Alternatives | I do not believe this is a reasonable alternative, where funding comes from is not a screening mechanism as it cannot be compared to the human or environmental factor and another alternative with feasible criteria should be added.
CDFW | Alternatives | CEQA requires EIRs to describe a range of reasonable alternatives to the project, or to the location of the project, which would feasibly attain most of the basic objectives of the project but would avoid or substantially lessen any of the significant effects of the project. CDFW recommends a summary table showing which significant effects of the project are avoided or substantially lessened by each alternative.
NMFS | Alternatives | What Project alternatives were considered and rejected?
NMFS | Baseline assumptions | NMFS would recommend the use of a future baseline, considering the Project would not be operational until at least 2030.
NMFS | Baseline assumptions | Is Delta Conveyance included in the baseline? Where and how is it considered in the EIS?
NMFS | Baseline assumptions | Is the CALSIM period of record a reasonable baseline for current and future conditions (e.g. with regard to drought frequency and duration)?
CDFW | Baseline assumptions | Would this include SWRCB Water Quality Control Plan update if it is in place at the time of diversion?
CDFW | Baseline assumptions | Does not include proposed update to the Bay Delta WQCP. Does not include Delta Conveyance Project. Does not include Shasta Dam Raise. Will this going to be covered in cumulative impacts?
CDFW | Baseline assumptions | Delta Conveyance Project and WQCP should be considered reasonably foreseeable. What about programmatic components of the 2019 BOs like Shasta Dam Raise? Are these included in the baseline and in the No Project alternative?
CDFW | Baseline assumptions | CDFW recommends considering including all perennial creeks and rivers potentially impacted in the baseline studies. CDFW requests that all baseline all base line data (not synthesized data) be sent to chris.mckibbin@wildlife.ca.gov and Andrew.Huneycutt@wildlife.ca.gov.
CDFW | Baseline assumptions | CDFW recommends clarifying that these baseline conditions were not created using the Record of Decision (ROD), Feb 19, 2020 for the Central Valley Project (CVP). Agencies are still transition to these modernized operations.
CDFW | Baseline assumptions | The baseline in the DEIR should represent current conditions, not only represent state water contractors and diverters taking their full amount of water.
CDFW | Clarification | Need clarification on what this means.
CDFW | Clarification | CDFW recommends clarifying if Vector Control is involved in the design, and if so, which office is working on the Project.
NMFS | Clarification | Boxes in figure 2-4 should refer to figure 2-2 (not 2-1)
USFWS | Clarification | Include summary sentence of what has changed?
USFWS | Clarification | Is the whole chapter on terminology? Or is it the analysis itself…or is it elsewhere as in ch 5-27? Edit chapter title if needed.
USFWS | Clarification | Sounds like the analysis part of the environmental analysis is somewhere in here, right?
USFWS | Clarification | What are these improvements? I can’t tell from this description or the figure
USFWS | Clarification | Where are these existing lines/how far away?
USFWS | Clarification | Need to review Appendix C. Where are the lines on the main project figures?
EPA | Clarification | Sounds like the analysis part of the environmental analysis is somewhere in here, right?
USACE | Clarification | 40 CFR 1502.14 Does not state this
USACE | Clarification | How can this be an alternative when it only about costs and who pays?
NMFS | Clarification (acronym) | What is WSE?
CDFW | Clarification (additional information) | The DEIR should include baseline conditions for Bird Creek.
CDFW | Clarification (additional information) | Please, provide more detail regarding the nature of exchanges with Oroville Reservoir (i.e. exchange water year type, volumes of water to be exchanged). There is the potential that these exchanges could interfere with Oroville Reservoir operations, potentially impacting SWP contractor deliveries, and/or impacting future planned ecosystem water releases out of the reservoir. Sites should work closely with DWR to ensure that these exchanges are feasible given the other demands on the reservoir. These exchanges should also be described in this document, in enough detail to provide confidence that the exchanges will not adversely impact future Oroville Reservoir operations.
EPA | Clarification (additional information) | Include summary sentence of what has changed?
CDFW | Clarification (coordination) | Please coordinate with CDFW biologists for the development of a fisheries management plan (Andrew.Hunneycutt@wildlife.ca.gov and Chris.McKibbin@wildlife.ca.gov).
CDFW | Clarification (definition) | CDFW requests that “similar” be defined and described for each use in this table.
CDFW | Clarification (definition) | Please, provide documentation supporting this assertion.
CDFW | Clarification (definition) | CDFW requests that seasonal months be defined. Other actions such as spring pulse flows, storage rebuilding, contractual obligations, winter-run temperature management season all need to be considered and operations may vary greatly from one month to another.
CDFW | Clarification (definition) | CDFW requests that seasonal months be defined.
USFWS | Cultural surveys | WAPA has conducted biological and cultural surveys along the ROWs and has ROW Maintenance EA for activities including vegetation management along the ROWs and towers.
USFWS | Cultural surveys | WAPA has conducted cultural surveys along their ROW and has programmatic agreements with SHPO.
NMFS | Documentation | Is the December 2020, Final Feasibility Report for the North-of-Delta Offstream Storage Investigation available? Is that report the same as the August 2017 Feasibility Report?
NMFS | Documentation | Are results available for the additional analysis of “environmental effects of the new alternatives in the [Value Planning] Report”?
NMFS | Documentation | Appendix 1A and Chapter 5 not yet received.
CDFW | Ecosystem benefits | Benefits funded by Reclamation will need to be separate than the quantity of benefit provided to the state under WSIP.
CDFW | Ecosystem benefits | Suggest including statement that the Authority will also need to enter into a contract with the administering agencies for the public benefits prior to determining a project’s final funding award.
CDFW | Ecosystem benefits | More detail is needed here to substantiate a benefit (i.e. What water year types? What months? What volumes?). CDFW will need to analyze this in detail to determine how much water needs to be exchanged to realize an actual improvement.
CDFW | Ecosystem benefits | Please distinguish between benefits to water right holders and ecological function.
CDFW | Ecosystem benefits | This does not accurately reflect the role of DWR. DWR is not the administering agency for ecosystem benefits and does not represent the State of California in that respect. Also, funding decisions by the CA Water Commission should be separated from DWR. DWR cannot represent other state agencies on behalf of the State of California.
CDFW | Ecosystem benefits | Under Prop 1, ecosystem benefits are considered public benefits; whereas, water supply is not. Prop 1 can only fund public benefits. Ecosystem public benefits should be distinct from water supply benefits of the project.
CDFW | Ecosystem benefits | This is one of Sites’ ecosystem benefits, but there is no mention of IL4 Refuge Water Supply being an objective of the project. Because Prop 1 requires project to provide a net ecosystem improvement, CEQA documents should analyze any potential impacts from providing said benefits. Additionally, any benefits provided by the project under WSIP, cannot be used to avoid, minimize or mitigate impacts. Suggest including all WSIP ecosystem benefits as clear objectives.
CDFW | Ecosystem benefits | Suggest adding CDFW will use this RDEIR/SDEIS to evaluate if Sites Reservoir provides a net ecosystem benefit, in order to make a finding that the project is consistent with Prop 1, as required by the WSIP regulations. CWC can only issue a final funding award after CDFW has made a finding and a contract for ecosystem benefits between CDFW and the Sites Authority has been executed.
CDFW | Ecosystem benefits | Consider removing this language from this section. This could be construed as stating that these additional ecosystem benefits are proposition 1 benefits. It is recommended that the discussion, in this section, be restricted to the approved proposition 1 benefits.
CDFW | Ecosystem benefits | Additional IL4 refuge water supply can only be considered a benefit when it is delivered when needed and it is not needed in every year type and every month. This comment also pertains to the Yolo Bypass benefit.
USFWS | Electrical facilities | 5. Construction Timing table should address electrical facilities as taking place during the project window.
CDFW | Fish comments | What about DPS Green Sturgeon? Juvenile out-migration is highly correlated to pulse events (freshets) in the fall and early winter.
CDFW | Fish comments | CDFW recommends the DEIR include an impact analysis to fisheries from increased winter diversion of water into the GCID oxbow, including survival rate of listed winter and spring-run Chinook Salmon, and predation rate within the oxbow during peak emigration. The increase proportion of flow will likely change the migratory path of emigrating fish species (salmon, sturgeon, etc.).
CDFW | Fish comments | The DEIR should describe the monitoring protocols needed to ensure the new setbacks do not increase fish entrainment.
CDFW | Fish comments | CDFW recommends listing existing fish population in Funks reservoir, detailing the work window when the excavation will occur, and where the excavated material will be deposited.
CDFW | Fish comments | The DEIR should include fish monitoring protocols that include triggers that will affect water operations (diversions and releases), and appropriate measures that will be implemented to minimize the impacts to migrating listed fish species.
CDFW | Fish comments | Where and how will monitoring be conducted, so that fish presence can be detected?
CDFW | Fish comments | This seems to be actually controlled by flow up to the diversion capacity, rather than fish screen design (i.e. 1:1 except at the top end of diversion capacity maybe the last 300 cfs, or so).
CDFW | Fish comments | Please provide an analysis to show how protective these measures actually are. While the CalSim-2 modelling can be used to quantify changes to the total amount of water entering the Yolo Bypass over/through the Fremont Weir on a monthly basis, this may not provide enough detail to sufficiently assess potential impacts. For the Fremont Weir Big Notch Project, changes to the amount of flow diverted on a daily time scale may be more important than monthly changes to inundated acres because it is assumed that fish access to the Bypass is the limiting factor for floodplain rearing rather than total inundated acres. Relevant questions that will need assessed: · What is the reduction in the number of days with water flowing through the notch? · How does this reduction translate into the amount of fish that will be entrained in the Yolo Bypass? · How many adult fish passage days are being lost by this reduction?
CDFW | Fish comments | Winter-run Chinook salmon disperse downstream of Red Bluff Diversion Dam August through January with a peak in October. There are typically no rain events in the early part of this time frame and flow fluctuations are driven by reservoir releases. During this period, CDFW recommends use of real-time fish monitoring to drive flow adaptive management.
CDFW | Fish comments | CDFW recommends considering survival impacts upstream. The proposed 8,000 moving average at Bend Bridge is much less than the proposed requirements of 15,000 to 25,000 cfs estimated to maintain survival. Additionally, CDFW recommends identifying what flows facilitate downstream movement of anadromous fishes (salmonids and sturgeon).
CDFW | Fish comments | A ramping schedule will need to be developed to ensure that when pumping resumes upon cessation of the pulse event, flows in the river are not decreased at such a rapid rate that fish are adversely impacted.
CDFW | Fish comments | The rate of diversion is described as controlled and scalable due to the design of the fish screens. However, it appears that it is flow in the river that is controlling the diversion volume. CDFW is concerned that this could keep flow in the river at 3,250 cfs for extended periods of time.
CDFW | Fish comments | CDFW recommends implementing real-time fish monitoring to trigger avoidance and minimization actions. The proposed action has the potential to divert 3,900 cfs leaving flow in the mainstem at about 13,000 cfs. Not only is this approximately 30% of the flow, but it decreases the instances when anadromous fish may realize a benefit when flows exceed identified thresholds in the upper Sacramento River. In addition to diversions at GCID, this can be up to 40% at Hamilton City.
CDFW | Fish comments | As described, the project appears to be taking all flow between 4,000 and 5,800 cfs until full capacity is reached. This is simply maintaining the proposed bypass flow. CDFW is concerned that this could keep flow in the river at 4,000 cfs for long periods of time resulting in loss of base flow below the diversion with associated impacts to the native fish assemblage.
CDFW | Fish comments | Please, consider that another major objective of the Big Notch Project is to improve connectivity between the Sacramento River to provide safe and timely passage for winter- and spring-run Chinook, CCV steelhead, and green sturgeon. Therefore, Fremont Weir Notch Protections should consider potential impacts to the number of adult fish passage days.
CDFW | Fish comments | CDFW is concerned about impacts to listed fish caused by water quality. The Colusa Drain is well documented as having high levels of pollutants, turbidity, and temperature. The Sacramento River is degraded by CBD flows downstream of Knights Landing Outfall Gates (KLOG). Water quality from Sites can be expected to be similarly poor considering it will receive reclaimed agricultural runoff. CDFW requests the DEIR explore how directly diverting agriculture runoff into the Sacramento River will influence the aquatic environment and impacts to native fishes. CDFW recommends that water quality is fully examined in the DEIR. eased flows from Sites through KLOG will attract Sacramento origin adult salmonids to the base of KLOG to a larger degree than current conditions. KLOG has been identified as an entry point for anadromous fish to become entrained in the CBD. In fact, efforts have been designed and implemented to keep anadromous fish and other natives from entering the CBD via exclusion gates. These gates are not currently operational and release strategy through KLOG needs to be considered as not to create conditions that may facilitate entrainment into the CBD. The DEIR should analyze these effects and propose applicable avoidance and mitigation measures
CDFW | Fish comments | This was discussed at the Sites Joint Aquatic Meeting on April 9th and it was agreed that this would be removed, because Sacramento River temperature management objectives during the May-November period are for winter-run Chinook salmon. These fish are not present in the Feather River and temperature management is not an issue on the river.
CDFW | Fish comments | CDFW requests inclusion in the development of the Reservoir Operations Plan to address potential future concerns with fish and wildlife and their habitats.
CDFW | Fish comments | CDFW requests consideration of including a noise abatement plan depending on the results of fish communities’ surveys. This may be necessary based on the results of the fish community surveys in Funks and Stoney Coral Creek.
CDFW | Fish comments | Three Core 1 CV spring-run tributaries, two Core 2 CV spring-run tributaries, 3 Core-1 CV steelhead tributaries and 2 Core-2 CV steelhead tributaries (Antelope, Mill, Deer, Big Chico, and Butte Creeks) enter the Sacramento River downstream of RBDD. The Adaptive Management Plan and fish monitoring program should take these into consideration and use existing or new juvenile monitoring programs to inform Sites’ operations.
CDFW | Fish comments | The Sites Project has proposed conveying water through the Yolo Bypass, both as part of their WSIP benefit, and as a means of transporting water from the project to south-of-delta participants. CDFW has identified several potential negative impacts that need to be assessed by the project, including: • Increased straying of salmonids and sturgeon into the Yolo Bypass, with water deliveries through the bypass acting as attraction flows for fish. This may result in lethal and sub-lethal effects to adult migrating fish and increased reliance on the Wallace Weir Fish Rescue Facility. Please consider how these potential benefits/impacts will be balanced. • Temperature impacts to fish, water conveyed out of Sites Reservoir and into the Yolo Bypass could result in lethal and sub-lethal effects to fish in the Yolo Bypass. • Poor water quality in the Colusa Basin Drain (CBD) is well documented, as are the effects of poor water quality on aquatic ecosystems. The Department is concerned that delivering water from the CBD to the Yolo Bypass could have a negative impact on aquatic ecosystems. • There are capacity constraints in the CBD and Yolo Bypass, due to agricultural drainage and the presence of aquatic weeds. Sites needs to assess whether there is capacity to move water through the Yolo Bypass, at the times and at the volumes that the project intends to make releases.
CDFW | Fish comments | Flow augmentation from the project could influence straying of listed species in these waterways, actions identified in the Yolo Bypass BiOp, and fish projects that have been recently completed or are currently active. The DEIR should provide detailed analysis describing impacts to listed species and their life phases that occur in the Colusa Basin Drain, Knights Landing Ridge Cut, Toe Drain etc. The DEIR should also describe how the project will influence and interact with fishery projects occurring in these waterways.
CDFW | Fish comments | Please note that the North Delta Flow Action (NDFA) for which this proposed benefit is based off of has had limited and variable success in demonstrating food web benefits in the Cache Slough Complex/Lower Sacramento River. On the other hand, increased flow into the Knights Landing Ridge Cut and Yolo Bypass Toe Drain is likely to increase adult salmonid and sturgeon straying into the Yolo Bypass. This may result in a number of lethal and sub-lethal effects to adult migrating fish and increase reliance on the Wallace Weir Fish Rescue Facility. Please consider how these potential benefits/impacts will be balanced.
CDFW | Fish comments | This could result in the of dewatering fall run Chinook salmon redds and steelhead redds when flows recede. CDFW would need to see more detail to determine how much impact this type of action would create.
CDFW | Fish comments | The North Delta Flow Action (NDFA) for which this proposed benefit is based off of has had limited and variable success in demonstrating food web benefits in the Cache Slough Complex/Lower Sacramento River. While, increased flow into the Knights Landing Ridge Cut and Yolo Bypass Toe Drain is likely to increase adult salmonid straying into the Yolo Bypass. This may result in a number of lethal and sub-lethal effects to adult migrating fish and increase reliance on the Wallace Weir Fish Rescue Facility.
CDFW | Fish comments | CDFW recommends considering the needs of spring-run Chinook salmon during these months. Analysis needs to show what effects to Feather River flows and temperatures may occur due to these exchange operations. The hatchery has temperature requirements that need to be met which may disassociate temperature from flows. The draw from SWP to meet hatchery intake requirements may affect this estimate of SWP savings based on water exchanges.
CDFW | General format | The Appendixes were not included in the document library or in the comment solicitation, so no comments were made concerning them.
CDFW | General format | The DEIR should include monitoring provisions to ensure that these velocities and temperatures of releases are appropriate.
CDFW | General format | As written it sounds like these conditions are mutually exclusive.
CDFW | General format | This should say through the notch. Over the weir is a different implication meaning a weir overtopping extreme high flow event.
CDFW | General format | This should read “Salmon Management Team, Smelt Management Team, and Delta Monitoring Workgroup.”
CDFW | General format | The critical months for cold water pool management are the months of August through November, not just August and September.
CDFW | General format | This period is the transition between winter-run redd maintenance and minimizing fall run redd dewatering. The goal here is to bring flows down not up to minimize fall run redd dewatering.
USFWS | General format | Sites has been considered since at least the 70s, and probably earlier…it wasn’t a new idea/location in 2000…I added a minimal edit; you can decide how much more, if at all, you should include.
USFWS | General format | I don’t understand from this language or the figure what is being built or why, as in why would high river levels decrease water elevation. It may all be correct, but it isn’t clear to an unfamiliar reader.
USFWS | General format | I don’t see any road specified on that figure…I am presuming there is one on the”left”, if you say so…and if that left is facing downstream (south), would that be to the east?. And what about figure 2-9 (not referenced yet)…and what do all those letters in the figures mean? (not yet explained). Just trying to understand all this.
USFWS | General format | I cannot find this on a figure (none is cited) or decipher where it might be from this language alone.
USFWS | General format | These proposed transmission lines and connections should be illustrated on some of the maps. The figures later are schematics and not readily understood where the lines and connections would be placed on the landscape.
USFWS | General format | Fig 2-16 doesn’t show these.
USFWS | General format | Show locations for transmission lines in the project figures.
USFWS | General format | Need to show these features on the project figures.
USFWS | General format | Show on project figures.
USFWS | General format | No locations on that figure, which is a section only, maybe you mean figure 2-1?
EPA | General format | Sites has been considered since at least the 70s, and probably earlier…it wasn’t a new idea/location in 2000…I added a minimal edit; you can decide how much more, if at all, you should include.
EPA | General format | Is the whole chapter on terminology? Or is it the analysis itself…or is it elsewhere as in ch 5-27? Edit chapter title if needed.
USACE | General format | Would recommend to show which is the preferred alternative
USFWS | General statement | Overall the background about the funding and development is very clear and thorough.
USFWS | General statement | Noted…will keep these in mind to see if all of these are expected to be met, or not, in other sections of the document.
EPA | General statement | Overall the background about the funding and development is very clear and thorough.
CDFW | Groundwater | CDFW recommends describing the depth of the water table, describing the likelihood of it being affected, and what the impacts would be to the region if the groundwater was affected.
CDFW | Groundwater | The DEIR should analyze potential impacts and changes to groundwater movement caused by the project.
CDFW | Habitat comments or questions | Peak winter and spring flows are essential for lateral channel migration, floodplain inundation, and maintenance of riparian habitat. Altering peak stream flows in the reach between Red Bluff/Hamilton City and Colusa may have significant effects on vital riverine ecosystems, ground water recharge, and flood waters directed through the Sutter/Yolo Bypasses, and the DEIR should analyze and mitigate this potentially significant impact.
CDFW | Habitat comments or questions | The consequences of reduced flow in the Sacramento River in the spring months (upstream of Sites river release point in particular) on survival of out-migrating juvenile salmonids and reduced habitat for rearing juvenile salmonids should be weighed and analyzed here to understand tradeoffs/benefits. Modelling the cold-water pool in Shasta Reservoir may suggest better times to reduce Shasta releases to protect the cold-water pool, in addition to protecting other salmonid life-stages in the Sacramento River.
CDFW | Habitat comments or questions | CDFW recommends that the DEIR includes an analysis over the summer releases from Folsom reservoir, as this could potentially lead to decreased releases from Folsom, which equates to decreased rearing habitat for steelhead along with elevated temperatures.
CDFW | Habitat comments or questions | There will be impacts where is no empirical data to model. Sites would be responsible to collect empirical data in the field as necessary to develop best available science to evaluate the impacts of the alternatives. Example – there is no data to evaluate project effects on salmonid rearing habitat from RBDD to Benicia Bridge. A desktop review would be too limited to adequately evaluate the significance of the impact or the necessary mitigation without a high level of uncertainty.
CDFW | Mitigation comments | This cannot happen without first fully mitigating the impacts of the project.
CDFW | Mitigation comments | The DEIR should disclose project impacts related to the increase of traffic as a result of this project. If these impacts are considered significant, the DEIR should disclose additional avoidance, minimization and or mitigation measures to offset the impacts.
CDFW | Mitigation comments | Has there been any thoughts as to how these impacts will be mitigated? The Big Notch Project is already a major mitigation project for CVP & SWP operations, so any changes to floodplain inundation frequency and duration will need to be offset.
CDFW | Mitigation comments | There will need to be mitigation for the loss of stream habitat that will be inundated by Sites particularly if the habitat lost supports lotic species that will not transition to a lacustrine environment.
CDFW | Operations (clarification/confirmation) | CDFW is concerned that there may instances where “excess” conditions may be limited by existing ITPs or Biological Opinions that may interfere with Sites diversions. These limitations should be taken into consideration when modeling and calculating yield estimations.
CDFW | Operations (clarification/confirmation) | Temperature management and cold water pool conditions at Oroville Reservoir are not an issue. Oroville is the tallest dam in the United States and it has a very low river gate that can be used to blend very cold water with warmer power generation releases to meet temperature objectives.
CDFW | Operations (clarification/confirmation) | CDFW would need to run the iCPMM model to see if this would result in a better projected temperature schedule or a worse temperature schedule. CDFW will need more detail to conduct that type of analysis. Additionally, higher releases in the fall more often than not result in fall-run Chinook salmon redd dewatering when flows cannot be maintained for egg-incubation through to emergence.
USFWS | Operations (clarification/confirmation) | I will keep this in mind when reviewing the effects section…to see what the “no restriction” means in terms of flow, area, depth of inundation, etc., in the yolo bypass.
USFWS | Power requirements | 1. Construction Power Requirements: do these assume the new electrical facilities (lines and substations) would be installed and operational to support this? If not then the document does not address temporary construction power and its removal.
USFWS | Power requirements | From Howard Hirahara: ; the report makes reference to potential storage exchanges with Shasta, Oroville, and Folsom Reservoirs..... if these storage exchange do occur, more potential administrative headaches keeping track of the energy ins/outs. If CVP in particular makes exchanges with Sites (independent of whether Reclamation becomes a participating partner, there are going to be energy transactions which will need to be kept track of in order to assure that SPA and CVP as well as SWP storage exchanges which have an energy use component are properly recorded and balanced on the "energy books".
USFWS | Power requirements | From Howard Hirahara: I noticed on Tables 2.6 and Tables 2.7, MW's were put into the table. Since MWs reflect capacity and not necessarily actual energy used (MW-hours). Difficult to ascertain actual energy usage. If you assume that the pumps are running constantly. You may want to ask projected actual energy usage. I'm assuming that the pumps are not working 24/7, if they are, then using the figures 142.5 MW x 24 hours x 365 days = 1,2248,300 MW-hours energy used; 75.5 MW x 24 hours x 365 days = 661,388 MW-hours energy re-generated. Right now I'm not sure if they calculated the actual energy use and then levelized that to a MW capacity assuming 24/7, or they are using a capacity value and not sure how it relates to actual projected energy to be used..... Assuming 24/7 operations: total cost to CVP would be 586,912 MW-hours or 586 Gigawatts of Energy. Depending on whether there is no participation (Option 2) or partial (up to 7% under Option 1 and up to 25% under Option 3), could be a lot of energy to keep track of by the energy settlements people and Reclamation's energy analyst (replacement for Paul Landry). So the actual drain on CVP resources could be as low as zero, or up to 41 GW-hours (7% option) or 146 GW-hours under (25% option)
CDFW | Projecr Description | Please include a detailed description of how the capacity of the TRR spillway was developed.
USFWS | Projecr Description | Since the need for the project is to provide water storage north of the delta, I think it would be important to include information here on why CALFED found that storage is needed in the NORTH specifically (declining health of delta fisheries).
EPA | Projecr Description | Since the need for the project is to provide water storage north of the delta, I think it would be important to include information here on why CALFED found that storage is needed in the NORTH specifically (declining health of delta fisheries).
EPA | Projecr Description | I would recommend including more information about the need for the project. I don’t recommend altering the purpose and need statement and I think it is much clearer than it was in the 2017 document. However, supporting information for why fish need improved water temperature and why CVP needs additional operation flexibility to address restraints would support this section. It is important to explain not just what the project proponent/agency hopes to achieve, but why here, why now, and what problems will be solved/addressed.
CDFW | Projecr Description | The DEIR should describe why riprap was chosen over other erosion control methods.
CDFW | Projecr Description | Please describe how water quality will be monitored and protected when released to Sac or Liberty.
CDFW | Projecr Description | What does the term ‘losses’ mean and what is the magnitude of these losses?
NMFS | Projecr Description | Where is construction material coming from? How much is needed? How is it getting there?
NMFS | Projecr Description | What is the estimated volume and tonnage of off-site material? What methods would be used to transport said material to the construction site?
CDFW | Project Description | Please, clarify exactly the who, what, when, where, why how of this statement. The way that the statement is written, it could be construed that CDFW had significant input in shaping the alternatives, which it did not.
CDFW | Project Description | Please clarify if all of the water conveyed to the Sacramento River will be released through the CBD.
CDFW | Project Description | Please clarify if the temporary roads will be removed restored to pre-project conditions.
NMFS | Project Description | Has the TRR already been permitted?
USFWS | Project Description | AF of reservoir size? That’s not the same as having water in it, or AF of yield…somewhere in the document there needs to be a disclosure of how much it costs per unity of usable water. Be mindful I am coming into this recently, and these comments reflect that.
USFWS | Project Description | Sites Project functions include AG, M&I, and environment. Don't see anything about industrial water use. Should there be at least a passing reference to it?
USFWS | Project Description | Food for who?
USFWS | Project Description | A few pages ago, it said this was 1.3 MAF…as in VP5 please check/explain.
USFWS | Project Description | What is being done here with the fill? RU creating a levee of sorts on the sides in places to create 2.5 ft? It isn’t clear to me.
USFWS | Project Description | Where is this shown in the construction schedule later in this chapter? Do you need to discuss the interconnection application and studies that still will be needed?
USFWS | Project Description | Who is building the towers and lines? I realize this question is outside the scope of the EIS/EIR – just wondered who’s responsibility it would be.
USFWS | Project Description | How far north, or west and north?
USFWS | Project Description | Who is responsible for building and operating this substation? If WAPA then we will need a Federal NEPA document to cover this action. Footprints for ROW and substation would need to be studies for bio and cultural and land ownership impacts if not already part of project footprints studies.
USFWS | Project Description | Location for access to power lines?
USFWS | Project Description | 2. For the New and Existing Roadways – should new access roads be included for the powerlines?
USFWS | Project Description | 1. All Alternatives – Operation and Management Plans – should this include O&M of power facilities?
EPA | Project Description | AF of reservoir size? That’s not the same as having water in it, or AF of yield…somewhere in the document there needs to be a disclosure of how much it costs per unity of usable water. Be mindful I am coming into this recently, and these comments reflect that.
EPA | Project Description | Sites Project functions include AG, M&I, and environment. Don't see anything about industrial water use. Should there be at least a passing reference to it?
EPA | Project Description | Food for who?
CDFW | Project Water Diversions and Operations | Does this mean that exports are at maximum capacity at the CVP and SWP? Or that allocations are 100% south of delta or that San Luis Reservoir is full?
CDFW | Project Water Diversions and Operations | Freemont weir is at river mile (RM) 82 while the diversion points are at RM 205 and 243. How will real time operations stay within identified flow over weir thresholds? Will a tool be developed?
CDFW | Project Water Diversions and Operations | What is the biological rationale for the metrics in these conditions and how were they developed?
CDFW | Project Water Diversions and Operations | Does this mean that in the future if there are new requirements, Sites would not divert until those criteria were met?
CDFW | Project Water Diversions and Operations | Please, provide the rationale for this minimum bypass flow, along with supporting documentation for that rationale. Is this a redd dewatering criteria for upstream of RBDD?
CDFW | Project Water Diversions and Operations | Please, provide the rationale for this minimum bypass flow, along with supporting documentation for that rationale. This does not appear to be a biologically based criteria.
CDFW | Project Water Diversions and Operations | Please provide the rationale for the 8,000 cfs bypass flow, along with the supporting documentation that supports that rationale. If this is for fall run chinook emigrating at this time of the year, with the 10,000 cfs pulse flow science to be operationalized at Bend Bridge, it should be described clearly in this document.
CDFW | Project Water Diversions and Operations | Please provide justification for the Fremont Weir Protections. For example, how was the 600 cfs threshold chosen? Is this tied to any sort of threshold by which floodwaters in the Tule Canal/Toe Drain begin spilling onto the floodplain?
CDFW | Project Water Diversions and Operations | Please, describe or add a footnote to indicate what is meant by “trailing average.”
CDFW | Project Water Diversions and Operations | In this section, please describe the rationale for selecting this minimum bypass flow, along with supporting documentation for that rationale.
CDFW | Project Water Diversions and Operations | In this section, please provide the rationale for selecting this minimum bypass flow, along with supporting documentation for that rationale.
CDFW | Project Water Diversions and Operations | Please, describe how water quality standards may or may not be affected by releases from Sites at all times of the year in the Sacramento River and Delta.
CDFW | Project Water Diversions and Operations | Please, provide more detail on how Sites anticipates water would be routed and tracked through the Delta to ensure that water reaches South Delta pumping facilities.
CDFW | Project Water Diversions and Operations | Please, provide the supporting documentation to support the rationale for this minimum bypass flow.
CDFW | Project Water Diversions and Operations | Please specify river flow conditions that would justify a 2,500 cfs pump rate.
CDFW | Project Water Diversions and Operations | The DEIR should include documentation supporting a projected release flow of up to 100 cfs into Stone Corral Creek and analyze projected impacts as result of these flows.
CDFW | Project Water Diversions and Operations | Please, provide a rationale for not extending the 8,000 cfs bypass flow at Wilkins to March when winter-run smolts are out-migrating, including those released from LSNFH.
CDFW | Project Water Diversions and Operations | The 5,000 cfs minimum bypass criteria appears to be a navigation based criteria and a not a biologically based criteria. Is there a biological justification for this minimum bypass flow? If so, please provide the rationale, along with supporting documentation.
NMFS | Project Water Diversions and Operations | Why is the RBPP increasing capacity to 2,500cfs?
NMFS | Project Water Diversions and Operations | Why do all alternatives require a TC Canal gate structure modification to 3,000 cfs
NMFS | Project Water Diversions and Operations | Confirm that the GCID Main Canal capacity is 1,800cfs.
NMFS | Project Water Diversions and Operations | Confirm the Funks pump station (for TC) flow rate: 2,100 cfs or 2,000?
NMFS | Project Water Diversions and Operations | Confirm that the maximum reservoir inflow is 3,900cfs (2,100 + 1,800)
NMFS | Project Water Diversions and Operations | Confirm that the dunnigan pipeline capacity is 1,000 cfs
NMFS | Project Water Diversions and Operations | Confusing figure. GCID Main Canal capacity 1,800cfs why is it depicted up to 3,000cfs? Combined capacity (GCID+TC) is 3,900 why is it depicted at 3,000?
NMFS | Project Water Diversions and Operations | Regarding "precipitation-generated pulse events" Would a managed spring pulse be protected?
NMFS | Project Water Diversions and Operations | What constitutes "fish presence and migration"?
NMFS | Project Water Diversions and Operations | Does “at all times” apply to the period of operation (i.e. Sept 1 - June 15) or year round?
NMFS | Project Water Diversions and Operations | Confusing description of a “qualified pulse event,” is it a flow pulse or a pulse of fish?
NMFS | Project Water Diversions and Operations | Clarify the cessation of pulse protection after 7 days. What if fish are still present in high numbers?
NMFS | Project Water Diversions and Operations | Confirm that Sites reservoir deliveries can be made 'upstream' through the GCID or TC Canals
NMFS | Project Water Diversions and Operations | Confirm that Project diversions would be made Sept 1 - June 15.
NMFS | Project Water Diversions and Operations | Define 'excess conditions'
NMFS | Project Water Diversions and Operations | How would an 'expanded' Los Vaqueros Reservoir be considered?
CDFW | Project Water Diversions and Operations | This comment is regarding the minimum bypass flows at RBPP, Hamilton City, and Wilkins Slough. The minimum bypass flows listed for RBPP, Hamilton City, and Wilkins Slough are not sufficient for the persistence of anadromous fishes. These requirements are typically driven by diversion elevation and navigational requirements, yet past and recent literature highlight flow/survival relationships that indicate flows higher than these operational minimums are necessary to be considered sufficient for anadromous fishes. Additional diversions once the river reaches these minimum flow metrics decrease the number of instances when anadromous fish may experience a realized benefit brought on by environmental conditions and will therefore need to be minimized or mitigated.
CDFW | Project Water Diversions and Operations | CDFW recommends the DEIR discuss diversion window overlaps with Shasta/Trinity Reservoir and Keswick Reservoir release operations. Increasing withdrawals during the proposed window could place additional constraints on potential actions to avoid and minimize impacts to listed fish species. The proposed operational window has the potential to impact Shasta/Trinity Reservoir operations by diverting additional water in the upper Sacramento River during the September through December period, when Keswick Reservoir is typically reducing releases from summer deliveries to an operational minimum for the winter. During this time, Keswick Reservoir releases are driven by water needed for rice decomposition and meeting downstream requirements such as the flow metric at Wilkins Slough, while at the same time trying to minimize juvenile impacts to Chinook salmon (e.g. redd dewatering and juvenile stranding). Withdrawing additional water from the Sacramento River could limit the range of potential measures available to minimize impacts to listed fish, such as altering water flows and timing of releases.
CDFW | Recommendation | CDFW recommends changing the DOSS reference to Salmon Monitoring Team and Smelt Monitoring Team as the Delta Operations for Salmon and Sturgeon group no longer exists.
CDFW | Recommendation | CDFW recommends the development of a site specific Aquatic Invasive Species management plan.
CDFW | Recommendation | CDFW recommends expanding this section to detail which standards and metrics will be used, and how water quality will be modeled.
USFWS | Recommendation | I would recommend including more information about the need for the project. I don’t recommend altering the purpose and need statement and I think it is much clearer than it was in the 2017 document. However, supporting information for why fish need improved water temperature and why CVP needs additional operation flexibility to address restraints would support this section. It is important to explain not just what the project proponent/agency hopes to achieve, but why here, why now, and what problems will be solved/addressed.
USFWS | Recommendation | Under 1.2.5 Value Planning Process, a statement is made that, All three options included reservoir sizes from 1.3 to 1.5 million AF," eliminated the pump-back hydroelectrical facilities". Is that for the main reservoir only? I see that there is a proposed TRR Pumping Generating Plant, which implies pump-back storage for at lease the forebay reservoir from GCID faciliaties to Sites. If so, may want to clarify that no pump-back regernation for the main off-stream reservoir
CDFW | Recreation | CDFW recommends defining exact use planned to be allowed in the recreation area regarding angling and hunting. The reservoir is likely to attract a large contingent of migratory waterfowl, and deer, dove, and turkey populations. The fluctuating water level will likely result in regions of green vegetation due to receding water, creating a potential for increase tule elk usage. CDFW recommends considering coordination and use of lawful public hunting to manage increased populations.
CDFW | Recreation | CDFW recommends considering hunting and firearm use and their respective limitation or regulations within the Recreation Management Plan. CDFW recommends considering the management and regulation of public use facilities to discourage habituation of wildlife to people.
USFWS | Reference request | In Chapter 1.2.1 CALFED Record of Decision: a statement is made that over 50 storage sites were considered. Here we list 52 specifically. Perhaps want to keep the refernce to over 50, or explicityly state 52 whenever talking about water storage sites studied.
USFWS | Reference request | In Chpater 1.2.1. CALFED ROD section: reference is made to 5 storage sites selected for further study. It makes reference to 12 here. Perhaps time refernce indicates the reason why the difference? Maybe the 12 were identified prior to the CALFED ROD being finalized?
USACE | Reference request | Are these criteria referenced anywhere?
NMFS | Regulatory | Is there a lead federal agency for Project Operations?
NMFS | Regulatory | Has FWS produced a FWCA 2(b) report?
CDFW | Reservoir | The DEIR should include a reservoir profile modeling to justify the different elevations of ports and to analyze operational flexibility that would be feasible based on the location of these ports.
CDFW | Reservoir | CDFW requests consultation in the development of the Reservoir Management Plan. CDFW also requests clarification on how this plan is proposed for development, who will manage the plan, and if there will be public comment periods through its development.
CDFW | Reservoir | CDFW is concerned that having a 340-foot elevation port as the lowest port may not be sufficient to allow for appropriate temperature and turbidity releases, or access to the coldest water when reservoir levels are low. CDFW recommends that ports are located throughout the profile of the reservoir to allow for maximum operational flexibility.
CDFW | Reservoir | CDFW recommends that an analysis of reservoir temperatures at corresponding elevations, and drier water years be conducted for water that is to be released back into the Sacramento River.
USFWS | Transmission lines | Interconnection to transmission lines is missing. Map only shows partial transmission lines. WAPA can provide a GIS clip if needed.
USFWS | Transmission lines | Transmission lines are missing on figure. Unless I am not reading this correctly. It’s sort of faint.
USFWS | Transmission lines | 1. Add this task to any of the schedules. Transmission line access (lines and substations) seem to be covered adequately, including t]he interconnection requests. However, the time frames for the project do not address the interconnection timeline. Starting Construction in 2024 without any interconnection requests completed is a dream that is not likely to occur.
USFWS | Transmission lines | And for ROW and transmission line inspection and maintenance.
USFWS | Transmission lines | Keep in mind that transmission line ROW widths are standard for WAPA and easements obtained for vegetation maintenance under lines.
USFWS | Transmission lines | 1. Transmission line access (lines and substations) seem to be covered adequately, including the interconnection requests. However, the time frames for the project do not address the interconnection timeline. Starting Construction in 2024 without any interconnection requests completed is not likely to occur.
CDFW | Water Quality | CDFW recommends describing water quality impacts to the River from these discharges. If it is determined that agricultural runoff will result in a significant impact, CDFW recommends developing a mitigation strategy for the runoff’s impacts or developing an alternative to avoid actions where agricultural runoff enters the Sacramento River.
CDFW | Water Rights | What about excess with restrictions? (i.e. conditions are excess but prior water rights are not being fulfilled due to other regulatory restrictions that are curtailing exports.)
CDFW |  | This is not the purpose of these teams. These teams have limited scope to implement actions required in the USBR PA and the ITP.
USFWS |  | That figure shows various “stockpile” areas; so is it that the excavated material is going to be placed there? I am more used to the term “spoil” or “disposal” areas for places that material is going to be left. This narrative says it is assumed the material will remain “near”; does this mean it might be moved around again later?
USFWS |  | Similar comment for Funks Reservoir as mention is made for Funks Reservoir P-Gen Plant.
EPA |  | Noted…will keep these in mind to see if all of these are expected to be met, or not, in other sections of the document.