## Sheet1
Deliverable/Action | Revised Deliverable Date | Notes
Final Diversion Criteria | 2021-10-01
Draft Revised Criteria -Including Reclamation Operations | 2021-09-17
Approved Revised Criteria | 2021-09-28
Operations Modeling | 2021-11-15
Calsim Complete | 2021-10-04 | Uses 9/17 revised criteria
Other Aquatics Model | 2021-11-15 | Calsim + 6 weeks
Biological Assessment | 2022-01-24
Update Analysis | 10/4 - 12/6/2021 | Uses 9/17 revised criteria
Authority Review | 12/6 - 12/17/2021
ICF Revise | 12/20/21 - 01/10/22
RC and AB approval | 2022-01-21 | Assumed RC and Board meeting dates
To BOR for Review | 2022-01-24 | This is BOR and NMFS review? Would it come back with comments?
CESA ITP- Operations | 2022-01-20
Update Analysis | 10/4 - 12/13/2021
Authority Review | 12/13 - 1/10/2022
ICF Revise | 01/10 - 1/24/22
RC and AB approval to Release | 2022-01-21 | Assumed RC and Board meeting dates
Submit to CDFW | 2022-01-24
WAA and Water Rights Application | 2022-01-27
MBK developeing
CEQA/NEPA | 2023-01-30 | ICF developing - these are general placeholders
Draft Final EIR/EIS (includes responses to comments and updated text) | 2022-06-24 | assumes revised project modeling is available at the end of 2021, with 6 months to prepare analysis and text edits draft Final EIR/EIS
Final EIR/EIS | 2022-09-23 | Assumes approximately 3 months to prepare based on reviews by legal and Reclamation, may be longer
Board Decision and NOD | 10/26/2022-11/1/2022 | NOD filed within 5 days of Board approval
ROD | 2023-01-01 | Needs BO and Section 106 complete

## Sheet2
WR-005 | Water Availability Analysis & Planning/Coordination with SWRCB | 2020-09-01 | 2020-09-01 | 2021-10-01
WR-025 | Prepare Water Right Application | 2021-02-01 | 2021-02-01 | 2021-09-23
WR-035 | QA/QC and Legal Review of Draft Water Right Application | 2021-09-24 |  | 2021-10-08
WR-045 | Revise Draft Water Right Application | 2021-10-12 |  | 2021-11-05
WR-055 | Work Group Review of Draft Water Right Application | 2021-11-08 |  | 2021-11-12
WR-065 | Resolve Work Group Comments | 2021-11-15 |  | 2021-11-24
WR-075 | Authority Approval of Water Right Application, Submit to SWRCB | 2021-11-29 |  | 2021-12-17
WR-085 | Submit Water Right Application |  |  | 2021-12-17
WR-095 | SWRCB Review of Water Right Application | 2021-12-18 |  | 2022-02-16