## Sheet1
Activity ID | Activity Name | Remaining Duration | Start | Finish
Modeling (Erin, Ali) |  | 679 | 01-Sep-20 A | 2024-10-11
OS-1150 | Develop Sites-Specific Model | 344 | 2023-06-19 | 2024-10-11
BA/ITP Documentation |  | 20 | 01-Nov-20 A | 2022-03-01
OP-450 | BA/ITP and Water Rights Modeling Support | 20 | 01-Nov-20 A | 2022-03-01
OP-360 | Appendices for BA/ITP | 20 | 01-Apr-21 A | 2022-03-01
Bridging Analysis for CWC/WSIP Benefits |  | 73 | 01-Sep-20 A | 2022-05-16
CFS-010 | CWC/WSIP Operations Modeling | 73 | 01-Sep-20 A | 2022-05-16
CFS-030 | CWC/WSIP Documentation and Appendices | 73 | 03-May-21 A | 2022-05-16
Preliminary Hydraulics Modeling |  | 171 | 01-Sep-20 A | 2022-10-04
ENG-466 | Emergency Release Flood Modeling | 0 | 01-Sep-20 A | 16-Jul-21 A
ENG-420 | Preliminary Hydraulics Model Summary | 90 | 14-Oct-20 A | 2022-06-09
ENG-470 | Preliminary Pipeline Hydraulic Modeling | 90 | 2022-05-27 | 2022-10-04
ENG-480 | System Wide Hydraulic Modeling | 90 | 2022-05-27 | 2022-10-04
Operations Analysis (Erin, Ali) |  | 591 | 23-Sep-20 A | 2024-06-11
Operations Plan - Version 1 |  | 58 | 01-Nov-20 A | 2022-04-25
OP-470 | Operations Plan, Version 1 | 58 | 01-Nov-20 A | 2022-04-25
OP-475 | Support Development of Ops Plan Ver 1 Documentation | 55 | 01-Mar-21 A | 2022-04-20
Operations Plan - Version 2 |  | 356 | 27-Aug-21 A | 2023-07-03
FO-1050 | Operations Plan, Version 2 | 370 | 27-Aug-21 A | 2023-07-03
KD-1510 | Operations Plan, Version 2 | 21 | 2022-02-01 | 2022-03-02
Operational Agreements |  | 325 | 23-Sep-20 A | 2023-05-18
OP-480 ($$$) | Support Operational Agreements | 325 | 23-Sep-20 A | 2023-05-18
OP-490 | Support for Operational Agreements Documentation | 325 | 19-Nov-20 A | 2023-05-18
Final Sites-Reclamation Operating Agreement |  | 205 | 02-Nov-20 A | 2022-11-23
Reclamation Term Sheet |  | 205 | 02-Nov-20 A | 2022-11-23
OP-1110 | Sites-Reclamation Operating Agreement Term Sheet | 21 | 02-Nov-20 A | 2022-03-02
OP-1005 | Final Sites-Reclamation Operating Agreement | 205 | 14-Jun-21 A | 2022-11-23
Final Sites-DWR Operating Agreement |  | 206 | 02-Nov-20 A | 2022-11-28
DWR Term Sheet |  | 206 | 02-Nov-20 A | 2022-11-28
OP-1120 | Sites-DWR Operating Agreement Term Sheet | 21 | 02-Nov-20 A | 2022-03-02
OP-1015 | Final Sites-DWR Operating Agreement | 206 | 15-Jun-21 A | 2022-11-28
Annual Operating Plan Process and Procedures |  | 519 | 2022-06-16 | 2024-06-11
FO-1060 | Annual Operating Plan Processes and Procedures | 519 | 2022-06-16 | 2024-06-11
Provide Operations Input on Response to Comments and Final EIR/EIS |  | 20 | 2022-12-07 | 2023-01-03
FO-1080 | Provide Operations Input on Response to Comments and Final EIR/EIS | 20 | 2022-12-07 | 2023-01-03
Member Portal/Accounting System |  | 300 | 2022-06-10 | 2023-08-21
FO-1090 | Develop Member Portal/Accounting System | 300 | 2022-06-10 | 2023-08-21
FO-1100 | Member Portal/Accounting System Operational | 0 |  | 2023-08-21
Permitting (John, Ali) |  | 2198 | 11-Feb-20 A | 1930-08-08
Key Deliverables |  | 346 | 2022-02-01 | 2023-06-19
KD-1240 | Execute Federal Operations Agreement | 21 | 2022-02-01 | 2022-03-02
KD-1250 | Execute State Operations Agreement | 21 | 2022-02-01 | 2022-03-02
KD-1320 | Water Right - Complete Protest Resolution Period and Resolve as Many Protests as Possible | 21 | 2022-02-01 | 2022-03-02
KD-1350 | Section 106 - Final Programmatic Agreement | 21 | 2022-02-01 | 2022-03-02
KD-1360 | Section 106 - Programmatic Historic Properties Management Plan Development | 21 | 2022-02-01 | 2022-03-02
KD-1370 | Incidental Take Permit - Construction ITP Issued | 0 |  | 2022-02-01
KD-1380 | Incidental Take Permit - Operations ITP Issued | 0 |  | 2022-02-01
KD-1390 | CWA 404/401 - Submit Final Permit Applications | 0 | 2022-02-01
KD-1420 | Streambed Alteration Agreement | 21 | 2022-02-01 | 2022-03-02
KD-1460 | Develop Mitigation Acquisition Master Plan | 21 | 2022-02-01 | 2022-03-02
KD-1400 | CWA 404/401 - Permits Issued | 0 |  | 2022-02-01
KD-1410 | Levee and Flood Permits - Section 408 and CVFPB Encroachment Permits Issued | 0 |  | 2022-02-01
KD-1430 | Eagle Permit - Short Term and Nest Permit Issued | 0 |  | 2022-02-01
KD-1440 | Eagle Permit - Long Term Permit Issued | 0 |  | 2022-02-01
KD-1450 | Obtain Local Agency Agreements & Permits | 0 |  | 2022-02-01
KD-1330 | Water Right - Receive Water Right Order and Permit | 0 |  | 2023-06-19
Water Storage Investment Program (WSIP) Permits |  | 0
Water Rights Order & Permit |  | 0
Federal Agency Agreements & Permits |  | 731 | 14-Apr-20 A | 2024-12-24
Phase 1 Environmental Site Assessments |  | 421 | 2022-05-27 | 2024-01-05
FED-010 | Phase 1 Environmental Site Assessments | 421 | 2022-05-27 | 2024-01-05
US Army Corps of Engineers CWA 404, Rivers & Harbors Act Section 10 |  | 425 | 05-May-20 A | 2023-10-11
FED-020 | U.S. Army Corps of Engineers CWA 404, Rivers and Harbors Act Section 10 | 442 | 04-Feb-21 A | 2023-10-11
Clean Water Act Section 404 |  | 295 | 05-May-20 A | 2023-04-06
404-003 | USACE LEDPA & NEPA , 404/408 and WD Approach on Secion 404 Application | 0 | 05-May-20 A | 31-Aug-20 A
404-015 | Aquatic Resources Mapping and Reporting | 0 | 01-Sep-20 A | 03-May-21 A
404-010 | Desktop Wetland Delineation Analysis (includes Waters of the State) | 0 | 01-Sep-20 A | 28-Jun-21 A
404-00-00 | Clean Water Act 404 Permit Application Summary | 295 | 01-Sep-20 A | 2023-04-06
404-050 | Prepare Draft 404 Application | 36 | 04-Feb-21 A | 2022-03-23
404-035 | Prepare Compensatory Mitigation Plan | 36 | 04-Feb-21 A | 2022-03-23
404-025 | Pre-Application Meeting | 0 | 04-Feb-21 A | 04-Feb-21 A
404-001 | Prepare LEDPA analysis | 0 | 05-Feb-21 A | 28-May-21 A
404-020 | Submit Delineation to USACE | 0 |  | 29-Jun-21 A
404-030 | Preliminary Wetland Delineation Acceptance | 28 | 30-Jun-21 A | 2022-02-28
404-060 | Authority/Integration/Work Group Review of Draft 404 Application | 20 | 2022-03-24 | 2022-04-21
404-070 | Prepare Final 404 Application | 20 | 2023-03-10 | 2023-04-06
404-120 | Submit 404 Application | 0 |  | 2023-04-06
US Army Corps of Engineers Rivers & Harbors Act Section 14, Section 408 |  | 731 | 01-Sep-20 A | 2024-12-24
FED-030 | U.S. Army Corps of Engineers Rivers and Harbors Act Section 14, Section 408 | 442 | 04-Feb-21 A | 2023-10-11
Section 408 |  | 547 | 01-Sep-20 A | 2024-04-09
408-00-00 | Section 408/Encroachment Permit Summary | 90 | 01-Sep-20 A | 2022-06-09
408-005 | Coordinate with CVFPB and USACE on Section 408/Encroachment Permit | 66 | 2023-06-28 | 2023-09-29
408-010 | Assume Start of 50% Design of 408 Jurisdictional Features | 0 |  | 2023-09-29
408-130 | Prepare Draft Encroachment Permit/408 Request w/Engineering Team | 129 | 2023-10-02 | 2024-04-09
Section 408 Amend 3 |  | 184 | 2024-04-10 | 2024-12-24
408-135 | Continue Draft Encroachment Permit/408 Request w/Engineering Team | 124 | 2024-04-10 | 2024-10-01
408-140 | Authority/Integration/Work Group Review of Draft | 20 | 2024-10-02 | 2024-10-29
408-150 | Prepare Encroachment Permit/408 Request | 40 | 2024-10-30 | 2024-12-24
408-160 | Submit Encroachment Permit/408 Request | 0 |  | 2024-12-24
US EPA & U.S. Army Corps of Engineers LEDPA Review |  | 374 | 02-Nov-20 A | 2023-07-07
FED-040 | U.S. EPA and U.S. Army Corps of Engineers LEDPA Review | 374 | 02-Nov-20 A | 2023-07-07
Advisory Council on Historic Preservation NHPA Section 106 |  | 153 | 01-Sep-20 A | 2022-09-08
106-00-00 | Section 106 Programmatic Agreement Summary | 90 | 01-Sep-20 A | 2022-06-09
106-001 | Prepare SHPO Initiation Package | 0 | 01-Sep-20 A | 28-Sep-20 A
106-000 | Confirmation of Section 106 Federal Lead Agency | 0 |  | 01-Sep-20 A
FED-050 | Advisory Council on Historic Preservation NHPA Section 106 | 62 | 01-Sep-20 A | 2022-04-29
106-002 | Authority/Reclamation/Integration Reviews | 0 | 29-Sep-20 A | 12-Oct-20 A
106-003 | Management/Work Group Reviews | 0 | 13-Oct-20 A | 26-Oct-20 A
106-021 | Prepare Consultation Information Package | 0 | 01-Dec-20 A | 19-Mar-21 A
106-041 | Prepare Draft PA | 0 | 04-Feb-21 A | 30-Aug-21 A
106-022 | Reclamation Review | 0 | 22-Mar-21 A | 21-Jun-21 A
106-025 | Reclamation Distributes to SHPO and Invited Consulting Parties | 0 | 03-Jun-21 A | 12-Jul-21 A
106-024 | Revisions | 0 | 22-Jun-21 A | 02-Jul-21 A
106-032 | Arrange Meeting Logistics and Prepare Materials | 0 | 06-Jul-21 A | 02-Aug-21 A
106-026 | Parties Accept Invitation for Consulting Party Status | 0 | 20-Jul-21 A | 02-Aug-21 A
106-042 | Reclamation Review | 0 | 20-Jul-21 A | 31-Aug-21 A
106-044 | Revisions | 24 | 02-Aug-21 A | 2022-03-07
106-033 | Conduct Meetings | 0 | 03-Aug-21 A | 16-Aug-21 A
106-052 | Circulate Draft PA to SHPO and Consulting Parties | 14 | 2022-02-01 | 2022-02-18
106-053 | Deadline for Comments on Draft PA | 30 | 2022-02-19 | 2022-03-20
106-061 | Prepare Draft Final PA | 25 | 2022-03-21 | 2022-04-25
106-062 | Reclamation Review | 10 | 2022-04-26 | 2022-05-09
106-064 | Revisions | 10 | 2022-05-10 | 2022-05-23
106-071 | Consult with SHPO and Consulting Parties on Draft Final PA | 27 | 2022-05-24 | 2022-06-30
106-072 | Circulate Draft Final PA to SHPO and Consulting Parties | 5 | 2022-05-24 | 2022-05-31
106-073 | Deadline for Comments on Draft Final PA | 30 | 2022-06-01 | 2022-06-30
106-081 | Prepare Final PA | 20 | 2022-06-30 | 2022-07-29
106-082 | Reclamation Review | 10 | 2022-07-29 | 2022-08-12
106-084 | Revisions | 12 | 2022-08-12 | 2022-08-30
106-091 | Consult with SHPO and Consulting Parties on Final PA | 5 | 2022-08-30 | 2022-09-07
106-092 | Circulate Final PA to SHPO and Consulting Parties for Signatures | 5 | 2022-08-30 | 2022-09-07
106-093 | Deadline for Signatures on Final PA | 0 |  | 2022-09-08
US Fish & Wildlife Service & National Marine Fisheries Service Endangered Species Act Section 7 |  | 140 | 14-Apr-20 A | 2022-08-19
FED-060 | USFWS and NMFS ESA Section 7 | 104 | 01-Sep-20 A | 2022-06-29
Biological Assessment |  | 52 | 14-Apr-20 A | 2022-04-16
BA-010 | Mitigation Planning 1B | 0 | 14-Apr-20 A | 31-Aug-20 A
BA-019 | Confirm Federal Scope of Action (ESA) | 0 | 14-Apr-20 A | 31-Aug-20 A
BA-015 | Adaptive Management Plan 1B | 0 | 14-Apr-20 A | 31-Aug-20 A
BA-020 | Permitting Construction Project Description | 0 | 29-Jun-20 A | 31-Aug-20 A
BA-011 | Mitigation Planning | 31 | 01-Sep-20 A | 2022-03-16
BA-016 | Adaptive Management Plan | 33 | 01-Sep-20 A | 2022-03-18
BA-000 | Biological Assessment/Biological Opinion Summary | 52 | 01-Sep-20 A | 2022-04-15
BA-022 | Permitting Operations Project Description | 0 | 19-Oct-20 A | 24-Mar-21 A
BA-001 | Initial Desktop Analysis | 0 | 15-Feb-21 A | 15-Mar-21 A
BA-025 | Prepare Operations Analysis | 0 | 24-Feb-21 A | 14-Jun-21 A
BA-024 | Prepare Construction Analysis | 0 | 25-Mar-21 A | 01-Jun-21 A
BA-029 | Authority Review and Comment Construction and Operations Analysis | 0 | 15-Jun-21 A | 30-Jun-21 A
BA-030 | Finalize Admin Draft BA | 0 | 01-Jul-21 A | 30-Jul-21 A
BA-032 | Submit Final Admin Draft BA | 0 |  | 30-Jul-21 A
BA-035 | Independent Review Draft BA | 0 | 03-Aug-21 A | 23-Aug-21 A
BA-055 | Reclamation, Legal, and Work Group Review | 0 | 03-Aug-21 A | 23-Aug-21 A
BA-057 | Revise Admin Draft BA | 5 | 04-Aug-21 A | 2022-02-07
BA-067 | IFC Revise BA | 16 | 2022-02-08 | 2022-03-02
BA-060 | Submit Revised Admin Draft BA to Reclamation for NMFS Review | 0 |  | 2022-03-01
BA-065 | ICF Revise BA and Authority submit to Reclamation | 11 | 2022-03-02 | 2022-03-16
BA-075 | Final Reclamation and Solicitor Office Review | 31 | 2022-03-17 | 2022-04-16
BA-100 | Reclamation Submit BA to USFWS & NMFS | 0 |  | 2022-04-16
BO Incidental Task Authorization |  | 125 | 2022-04-17 | 2022-08-19
BA-1110 | BO Incidental Take Authorization | 125 | 2022-04-17 | 2022-08-19
USFWS Bald Eagle Protection Act |  | 443 | 01-Sep-20 A | 2023-11-06
FED-075 | USFWS Bald Eagle Protection Act (includes Pre-Application Surveys) | 443 | 01-Sep-20 A | 2023-11-06
US Coast Guard Navigability Determination |  | 239 | 2022-05-27 | 2023-05-11
FED-080 | U.S. Coast Guard Navigability Determination | 239 | 2022-05-27 | 2023-05-11
US Bureau of Reclamation Warren Act |  | 291 | 01-Jun-21 A | 2023-03-31
FED-090 | USBR Warren Act | 291 | 01-Jun-21 A | 2023-03-31
USBR - Land Agreement |  | 278 | 02-Nov-20 A | 2023-03-14
FED-100 | USBR Land Agreements | 278 | 02-Nov-20 A | 2023-03-14
State Agency Agreements & Permits |  | 2096 | 11-Feb-20 A | 1930-03-19
Caltrans Encroachment & Transportation |  | 605 | 2022-05-27 | 2024-10-22
STA-010 | Caltrans Encroachment & Transportation | 605 | 2022-05-27 | 2024-10-22
State Lands Commission/State Lands Lease, if needed |  | 242 | 2022-05-27 | 2023-05-16
STA-020 | State Lands Commission/State Lands lease, if needed | 242 | 2022-05-27 | 2023-05-16
Central Valley Flood Protection Board Levee Encroachment |  | 421 | 01-Sep-20 A | 2023-10-11
STA-030 | Central Valley Flood Protection Board Levee Encroachment | 421 | 01-Sep-20 A | 2023-10-11
SWRCB Water Rights Permit |  | 346 | 01-Sep-20 A | 2023-06-19
WR-00-00 | Water Right Application Summary | 90 | 01-Sep-20 A | 2022-06-09
WR-005 | Water Availability Analysis & Planning/Coordination with SWRCB | 22 | 01-Sep-20 A | 2022-03-03
WR-025 | Prepare Water Right Application | 16 | 01-Feb-21 A | 2022-02-23
WR-035 | QA/QC and Legal Review of Draft Water Right Application | 11 | 2022-02-24 | 2022-03-10
WR-045 | Revise Draft Water Right Application | 19 | 2022-03-11 | 2022-04-07
WR-055 | Work Group Review of Draft Water Right Application | 4 | 2022-04-08 | 2022-04-13
WR-065 | Resolve Work Group Comments | 8 | 2022-04-14 | 2022-04-25
WR-075 | Authority Approval of Water Right Application, Submit to SWRCB | 15 | 2022-04-26 | 2022-05-16
WR-085 | Submit Water Right Application | 0 |  | 2022-05-16
WR-095 | SWRCB Review of Water Right Application | 60 | 2022-05-17 | 2022-07-16
WR-105 | Receive Protests to Application | 43 | 2022-07-18 | 2022-09-15
WR-115 | Resolve Protests and Schedule Protest Hearing | 78 | 2022-09-15 | 2023-01-11
WR-125 | Notice Water Rights Hearing | 19 | 2023-01-11 | 2023-02-08
WR-135 | Conduct In-House Mock Water Right Hearing | 14 | 2023-02-08 | 2023-03-01
WR-145 | Conduct Water Right Hearing | 1 | 2023-03-13 | 2023-03-14
WR-155 | Negotiate Permit Terms | 42 | 2023-03-14 | 2023-05-11
WR-165 | SWRCB Prepare Draft Permit and CEQA Findings | 21 | 2023-05-11 | 2023-06-12
WR-175 | SWRCB Issue Water Right Permit | 5 | 2023-06-12 | 2023-06-19
SWRCB NPDES and CWA Section 402 (Multiple permits based on construction packages and/or ROW access) |  | 1234 | 2024-03-27 | 2028-12-19
STA-150 | SWRCB NPDES and CWA Section 402 - Initial Design Review | 90 | 2024-03-27 | 2024-07-31
STA-050 | SWRCB NPDES and CWA Section 402 - Implementation | 1144 | 2024-08-01 | 2028-12-19
SWRCB Waste Discharge Requirements (Multiple permits based on constr. packages and/or ROW access) |  | 1234 | 2024-03-27 | 2028-12-19
STA-160 | SWRCB Waste Discharge Requirements - Initial Design Review | 90 | 2024-03-27 | 2024-07-31
STA-060 | SWRCB Waste Discharge Requirements - Implementation | 1144 | 2024-08-01 | 2028-12-19
SWB CWA Section 401 Water Quality Certification |  | 1100 | 11-Feb-20 A | 2026-05-25
401-00-00 | Clean Water Act 401 Permit Application Summary | 77 | 11-Feb-20 A | 2022-05-20
SWB CWA Section 401 Water Quality Certification - Conditional Approval |  | 77 | 15-Jan-21 A | 2022-05-20
401-120 | Coordinate with RWQCB and SWRCB - Conditional Approval | 76 | 15-Jan-21 A | 2022-05-19
401-130 | Prepare Draft 401 Application - Conditional Approval | 8 | 01-Mar-21 A | 2022-02-10
401-140 | Authority/Integration/Work Group Review of Draft 401 - Conditional Approval | 20 | 2022-02-11 | 2022-03-11
401-150 | Prepare Final 401 Application - Conditional Approval | 43 | 2022-03-14 | 2022-05-12
401-160 | Submit 401 Application - Conditional Approval | 0 |  | 2022-05-20
SWB CWA Section 401 Water Quality Certification - Reservoir Approvals During Construction |  | 280 | 2025-04-29 | 2026-05-25
401-170 | Prepare Draft 401 Application - Final Approval During Construction | 200 | 2025-04-29 | 2026-02-02
401-180 | Authority/Integration/Work Group Review of Draft 401 - Final Approval During Construction | 20 | 2026-02-03 | 2026-03-02
401-190 | Prepare Final 401 Application - Final Approval During Construction | 60 | 2026-03-03 | 2026-05-25
401-200 | Submit 401 Application - Final Approval During Construction | 0 |  | 2026-05-25
DWR DSOD (Multiple permits based on construction packages and/or ROW access) |  | 210 | 2025-01-01 | 2025-10-21
STA-130 | DWR DSOD - Initital Review Approval | 90 | 2025-01-01 | 2025-05-06
STA-080 | DWR DSOD - Design Package Approvals | 200 | 2025-01-15 | 2025-10-21
Cal OSHA Permits (Multiple permits based on construction packages and/or ROW access) |  | 1550 | 2024-04-09 | 1930-03-19
STA-170 | Cal OSHA Permits - For Construction | 200 | 2024-04-09 | 2025-01-14
STA-090 | Cal OSHA Implementation | 1276 | 2025-04-29 | 1930-03-19
CDFW Streambed Alteration Agreements |  | 591 | 2022-06-10 | 2024-10-15
STA-100 | CDFW Streambed Alteration | 591 | 2022-06-10 | 2024-10-15
CDFW Incidental Take Permits |  | 207 | 01-Sep-20 A | 2022-11-29
STA-110 | CDFW Section 2081 | 207 | 01-Sep-20 A | 2022-11-29
ITP - CESA (Se 2081) Operations |  | 77 | 30-Sep-20 A | 2022-05-20
CES-210 | Prepare Draft ITP Application - Operations | 0 | 30-Sep-20 A | 16-Aug-21 A
CES-190 | Prepare Operations Analysis - Operations | 22 | 30-Sep-20 A | 2022-03-03
CES-00-10 | Incidental Take Permit (ITP) Operations Summary - Operations | 77 | 30-Sep-20 A | 2022-05-20
CES-200 | Additional Mitigation Planning - Operations | 34 | 2022-03-04 | 2022-04-21
CES-220 | Legal Review of Draft ITP App - Operations | 21 | 2022-03-04 | 2022-03-24
CES-230 | Work Group Review of Draft ITP App - Operations | 21 | 2022-03-04 | 2022-03-24
CES-240 | Revise Draft ITP Application - Operations | 19 | 2022-03-25 | 2022-04-21
CES-250 | Integration Review and Authority Board Approval of ITP App - Operations | 18 | 2022-04-22 | 2022-05-17
CES-260 | Prepare ITP Application to CDFW - Operations | 3 | 2022-05-18 | 2022-05-20
CES-270 | Submit ITP Application to CDFW - Operations | 0 |  | 2022-05-20
ITP - CESA (Se 2081) Construction |  | 76 | 01-Sep-20 A | 2022-05-19
CES-020 | Delineation Depot and Focused Species Survey - Construction | 6 | 01-Sep-20 A | 2022-02-08
CES-00-00 | Incidental Take Permit (ITP) Construction Summary - Construction | 76 | 30-Sep-20 A | 2022-05-19
CES-030 | Prepare Draft ITP Application - Construction | 0 | 30-Sep-20 A | 16-Aug-21 A
CES-010 | Initial Desktop Analysis - Construction | 0 | 30-Sep-20 A | 16-Aug-21 A
CES-040 | Legal Review of Draft ITP App - Construction | 17 | 2022-02-01 | 2022-02-17
CES-060 | Work Group Review of Draft ITP App - Construction | 17 | 2022-02-01 | 2022-02-17
CES-025 | Mitigation Planning - Construction | 50 | 2022-02-09 | 2022-04-21
CES-070 | Revise Draft ITP Application - Construction | 19 | 2022-02-18 | 2022-03-17
CES-080 | Integration Review and Authority Board Approval of ITP App - Construction | 5 | 2022-04-22 | 2022-04-28
CES-090 | Prepare ITP Application to CDFW - Construction | 15 | 2022-04-29 | 2022-05-19
CES-280 | Submit ITP Application to CDFW - Construction | 0 |  | 2022-05-19
NAHC/Local Tribes AB 52 Consultation |  | 148 | 01-Sep-20 A | 2022-08-31
STA-120 | NAHC/Local Tribes AB 52 Consultation | 148 | 01-Sep-20 A | 2022-08-31
SHPO Section 106 |  | 0
SMARA |  | 86 | 2022-06-27 | 2022-10-27
STA-140 | SMARA | 86 | 2022-06-27 | 2022-10-27
Local Agency Agreements & Permits |  | 400 | 2022-05-27 | 2024-01-04
Colusa County |  | 400 | 2022-05-27 | 2024-01-04
Colusa County Air Pollution Control Districts |  | 400 | 2022-05-27 | 2024-01-04
LOC-010 | Colusa County Air Pollution Control Districts | 400 | 2022-05-27 | 2024-01-04
Colusa County Public Works - Encroachments |  | 400 | 2022-05-27 | 2024-01-04
LOC-020 | Colusa County Public Works - Encroachments | 400 | 2022-05-27 | 2024-01-04
Colusa County Transportation |  | 400 | 2022-05-27 | 2024-01-04
LOC-030 | Colusa County Transportation | 400 | 2022-05-27 | 2024-01-04
Colusa County Public Works Building, Street Improvement, Grading Permits |  | 400 | 2022-05-27 | 2024-01-04
LOC-040 | Colusa County Public Works Building, Street Improvement, Grading Permits | 400 | 2022-05-27 | 2024-01-04
Colusa County General Plan and Zoning |  | 400 | 2022-05-27 | 2024-01-04
LOC-050 | Colusa County General Plan and Zoning | 400 | 2022-05-27 | 2024-01-04
Glenn County |  | 400 | 2022-05-27 | 2024-01-04
Glenn County Air Pollution Control |  | 400 | 2022-05-27 | 2024-01-04
LOC-100 | Glenn County Air Pollution Control | 400 | 2022-05-27 | 2024-01-04
Glenn County Public Works - Encroachments |  | 400 | 2022-05-27 | 2024-01-04
LOC-110 | Glenn County Public Works - Encroachments | 400 | 2022-05-27 | 2024-01-04
Glenn County Transportation |  | 400 | 2022-05-27 | 2024-01-04
LOC-120 | Glenn County Transportation | 400 | 2022-05-27 | 2024-01-04
Glenn County Public Works Building, Street Improvement, Grading Permits |  | 400 | 2022-05-27 | 2024-01-04
LOC-130 | Glenn County Public Works Building, Street Improvement, Grading Permits | 400 | 2022-05-27 | 2024-01-04
Glenn County General Plan and Zoning |  | 400 | 2022-05-27 | 2024-01-04
LOC-140 | Glenn County General Plan and Zoning | 400 | 2022-05-27 | 2024-01-04
Yolo County |  | 400 | 2022-05-27 | 2024-01-04
Yolo County Air Pollution Control |  | 400 | 2022-05-27 | 2024-01-04
LOC-50 | Yolo County Air Pollution Control | 400 | 2022-05-27 | 2024-01-04
Yolo County Public Works - Encroachments |  | 400 | 2022-05-27 | 2024-01-04
LOC-60 | Yolo County Public Works - Encroachments | 400 | 2022-05-27 | 2024-01-04
Yolo County Transportation |  | 400 | 2022-05-27 | 2024-01-04
LOC-70 | Yolo County Transportation | 400 | 2022-05-27 | 2024-01-04
Yolo County Public Works Building, Street Improvement, Grading Permits |  | 400 | 2022-05-27 | 2024-01-04
LOC-80 | Yolo County Public Works Building, Street Improvement, Grading Permits | 400 | 2022-05-27 | 2024-01-04
Yolo County General Plan and Zoning |  | 400 | 2022-05-27 | 2024-01-04
LOC-90 | Yolo County General Plan and Zoning | 400 | 2022-05-27 | 2024-01-04
Benefits Contracts (DWR / CDFW) |  | 0
Division of Safety of Dams (DSOD) Permit |  | 0
Mitigation Support |  | 2198 | 09-Dec-20 A | 1930-08-08
Early Mitigation |  | 90 | 09-Dec-20 A | 2022-06-09
EM-00-10 | Summary Report for Early Mitigation/Geotech Mitigation | 90 | 09-Dec-20 A | 2022-06-09
Pre-Construction Planning |  | 468 | 2023-06-28 | 2025-04-28
MIT-010 | Pre-Construction Planning | 468 | 2023-06-28 | 2025-04-28
Pre-Construction Implementation |  | 0 | 2022-11-28 | 2022-11-28
MIT-015 | Pre-Construction Implementation | 0 | 2022-11-28 | 2022-11-28
Construction Monitoring |  | 1387 | 2025-04-16 | 1930-08-08
MIT-020 | Construction Monitoring | 1387 | 2025-04-16 | 1930-08-08
Post Construction Monitoring |  | 5 | 1930-08-02 | 1930-08-08
MIT-030 | Post Construction Monitoring Begins | 5 | 1930-08-02 | 1930-08-08
Water Rights Support |  | 0
Environmental (Ali, Laurie) |  | 845 | 01-Sep-20 A | 2025-06-02
Key Deliverables |  | 289 | 2022-02-01 | 2023-03-29
KD-1220 | Negotiate and Execute Benefits Contracts with DWR & CDFW | 21 | 2022-02-01 | 2022-03-02
KD-1340 | Federal ESA - Receive Biological Opinions | 21 | 2022-02-01 | 2022-03-02
KD-1470 | Final EIR/EIS - Complete | 0 |  | 2023-03-09
KD-1480 | Certify Final EIR/EIS and approve preferred project and MMRP (30 day period for legal challenge) | 45 | 2023-01-25 | 2023-03-29
EIR/EIS |  | 845 | 01-Sep-20 A | 2025-06-02
Revised Draft EIR / Supplemental Draft EIS |  | 36 | 01-Sep-20 A | 2022-03-23
EIR-610 | Authority/Reclamation/Integration/Authority Legal Review of Revised Ch. 11 and Associated Appendices | 3 | 30-Aug-21 A | 2022-02-03
EIR-050 | ICF Incorporate final comments/edits,Authority Backcheck edits and Finalize Revised Draft EIR/SDEIS for Rec. Mgt. Review | 6 | 2022-02-04 | 2022-02-11
EIR-620 | ICF submittal of all other chapters with edits in track changes for Authority/Reclamation review | 4 | 2022-02-04 | 2022-02-09
EIR-067 | Final Editing, Formatting and Doc Production (508 Compliance) | 22 | 2022-02-14 | 2022-03-16
EIR-075 | Coordination with Reclamation, Reclamation internal clearance, and public noticing | 27 | 2022-02-14 | 2022-03-23
EIR-080 | Authority Release Revised Draft EIR/SDEIS and Issue Public Notices | 1 | 2022-03-16 | 2022-03-16
Prepare Administrative Revised Draft EIR/Supplemental Draft EIS |  | 0 | 01-Sep-20 A | 25-Jun-21 A
EIR-005 | Prepare Revised Admin Draft EIR/SDEIS Summary | 0 | 01-Sep-20 A | 23-Jun-21 A
EIR-018 | Prepare Revised Draft EIR/SDEIS Analysis (Construction 1A) | 0 | 01-Sep-20 A | 10-Dec-20 A
EIR-018A | Authority/Reclamation/Integration Review of Revised Draft EIR/SDEIS Analysis (Construction 1A) | 0 | 11-Dec-20 A | 08-Jan-21 A
EIR-019 | Prepare Revised Draft EIR/SDEIS Analysis (Construction 1B) | 0 | 21-Dec-20 A | 25-Jan-21 A
EIR-020 | Prepare Admin. RDEIR/SDEIS Groups 1, 2, and 3 | 0 | 13-Jan-21 A | 28-May-21 A
EIR-025 | Group 1 Submittal | 0 | 13-Jan-21 A | 03-May-21 A
EIR-027 | Group 2 Submittal | 0 | 13-Jan-21 A | 24-May-21 A
EIR-019A | Authority/Reclamation/Integration Review of Revised Draft EIR/SDEIS Analysis (Construction 1B) | 0 | 26-Jan-21 A | 22-Feb-21 A
EIR-065 | Authority Board - Admin RDEIR CEQA Process; Process for Approval; Local Agency Outreach and Input | 0 | 24-Mar-21 A | 24-Mar-21 A
EIR-085 | Authority Board - Part 1 Admin RDEIR/SDEIS Batch 1A and 1B Chapters | 0 | 21-Apr-21 A | 21-Apr-21 A
EIR-035 | Authority/Reclamation/Integration/Authority Legal Review of Admin Revised Draft EIR/SDEIS | 0 | 04-May-21 A | 25-Jun-21 A
EIR-125 | Authority Board - Part 2 Admin RDEIR/SDEIS Group 1 Chapters | 0 | 26-May-21 A | 26-May-21 A
EIR-030 | Complete Admin Revised Draft EIR/SDEIS (with Group 3 submittal) | 0 | 28-May-21 A | 28-May-21 A
EIR-590 | Cooperating Agency Review | 0 | 01-Jun-21 A | 25-Jun-21 A
EIR-135 | Authority Board - Part 3 Admin RDEIR/SDEIS Remaining Chapters | 0 | 23-Jun-21 A | 23-Jun-21 A
Prepare Public Revised Draft EIR/Supplemental Draft EIS |  | 0 | 28-Jun-21 A | 27-Aug-21 A
EIR-040 | Incorporate comments/edits and prepare Public Revised Draft EIR/SDEIS | 0 | 28-Jun-21 A | 23-Jul-21 A
EIR-026 | Prepare Public Revised Draft EIR/SDEIS Summary for Ad Hoc, Res. Comm., and Board | 0 | 28-Jun-21 A | 25-Aug-21 A
EIR-045 | Live Edit Meetings | 0 | 29-Jun-21 A | 07-Jul-21 A
EIR-060 | Authority Board - Review and Delegate Authority to Release the RDEIR/SDEIS in August | 0 | 21-Jul-21 A | 21-Jul-21 A
EIR-600 | Reclamation/CDFW Revisions to Chapter 11 and Associated Appendices | 0 | 26-Jul-21 A | 27-Aug-21 A
EIR-150 | Authority Board - Status of Release of RDEIR/SDEIS, Public Meeting Schedule | 0 | 25-Aug-21 A | 25-Aug-21 A
Public Review |  | 44 | 2022-03-23 | 2022-05-24
EIR-090 | Public Review Period | 63 | 2021-11-12 | 2022-01-28
EIR-530 | Public Meetings | 2 | 2022-05-02 | 2022-05-03
Begin Preparation of the Admin Final EIR/EIS |  | 38 | 2022-05-03 | 2022-06-24
EIR-092 | Determine Approach for EIR/EIS Response to Comments Summary | 38 | 2022-05-03 | 2022-06-24
EIR-140 | Authority Board - Summary of Comments received in the RDEIR/SDEIS and Approach to Responses | 1 | 2022-05-17 | 2022-05-17
EIR-100 | Approach to Response to Comments | 15 | 2022-05-25 | 2022-06-15
EIR-095 | Categorize and Sort Comments by Topic | 15 | 2022-05-25 | 2022-06-15
EIR-105 | Authority/Reclamation/Legal Review | 7 | 2022-06-16 | 2022-06-24
Final EIR/Final EIS |  | 143 | 2022-06-27 | 2023-01-24
EIR-210 | Preparation of Admin Final EIR/EIS | 78 | 2022-01-01 | 2022-10-26
EIR-212 | Authority/Reclamation/Integration Review of Admin Draft EIR/EIS/Legal Review of Admin Final | 30 | 2022-10-18 | 2022-12-01
EIR-214 | Incorporate Authority/Reclamation/Integration Comments/Legal Comments | 21 | 2022-12-02 | 2023-01-03
EIR-240 | Final EIR/EIS Live Edit Meeting(s) | 5 | 2023-01-04 | 2023-01-10
EIR-250 | Complete Final EIR/EIS | 9 | 2022-10-27 | 2023-03-02
NOD, Findings of Fact, Statement of Overriding Considerations, Mitigation Monitoring Program |  | 32 | 2023-01-03 | 2023-02-16
EIR-300 | Prepare Draft Findings of Fact, Statement of Overriding Considerations, Mitigation Monitoring Program | 15 | 2023-01-03 | 2023-01-24
EIR-330 | Authority and Legal Review of Findings of Fact, Statement of Overriding Considerations, Mitigation Monitoring Program | 5 | 2023-01-25 | 2023-01-31
EIR-350 | Incorporate Comments and Prepare NOD, Findings, Statement of Overriding Considerations, MMRP | 5 | 2023-02-01 | 2023-02-07
EIR-360 | Work Group and Reservoir Committee Briefings | 5 | 2023-02-10 | 2023-02-16
Authority Certifies EIR and Approves Project and File NOD |  | 1 | 2023-02-16 | 2023-02-17
EIR-370 | Authority Certifies EIR and Approves Project | 0 |  | 2023-02-16
EIR-380 | File NOD | 0 |  | 2023-03-09
ROD |  | 31 | 2023-01-25 | 2023-03-09
EIR-410 | Prepare Draft ROD | 15 | 2023-01-25 | 2023-02-14
EIR-400 | Reclamation Final EIS Process | 21 | 2023-01-25 | 2023-02-23
EIR-420 | Submit Draft ROD to NEPA Team | 0 |  | 2023-02-14
EIR-430 | NEPA Team Review | 5 | 2023-02-15 | 2023-02-22
EIR-440 | NEPA Team Approval to Sign | 0 |  | 2023-02-23
EIR-450 | ROD Signed | 0 |  | 2023-04-09
Additional NEPA/CEQA Review, if needed |  | 570 | 2023-03-10 | 2025-06-02
EIR-460 | Additional NEPA/CEQA Documents, if needed | 570 | 2023-03-10 | 2025-06-02