{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["FINAL_EIR-EIS"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":4,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"FINAL_EIR-EIS","index":0,"n_rows":20,"n_cols":15,"rows_kept":20,"cut":false,"hidden":false,"merged":[[2,2,2,14],[0,1,0,5]]}
[null,"PROPOSED FULL OPERATIONS ANALYSIS SCHEDULE FOR SITES RESERVOIR PROJECT FINAL EIR/EIS"]
[null,{"$f":"_xlfn.CONCAT(\"Assumed Start Date: \",TEXT(C4,\"mm/dd/yyyy\"))","v":"Assumed Start Date: 04/11/2022"}]
[null,null,"Weeks"]
[null,"ALTERNATIVE","2022-04-11",{"$f":"C4+7","v":"2022-04-18"},{"$f":"D4+7","v":"2022-04-25"},"2022-05-02","2022-05-09","2022-05-16",{"$f":"H4+7","v":"2022-05-23"},{"$f":"I4+7","v":"2022-05-30"},"2022-06-06","2022-06-13","2022-06-20","2022-06-27","2022-07-04"]
[null,"ALTERNATIVES 1A AND 3A"]
[null,"CalSim II (Alts 1A, 2, and 3A)"]
[null,"USRDOM"]
[null,"HEC-5Q & RecTemp"]
[null,"Fish Mortality (Anderson & Martin)"]
[null,"SALMOD"]
[null,"DSM2 (Hydro & Qual)"]
[null,"IOS & DPM (Cramer)"]
[null,"OBAN (QEDA)"]
[null,"Reservoir Temperature"]
[null,"Power (LTGen, SWP_Power, & Sites_Power)"]
[null,"CalSim II (2035CT & WSIP 2070)"]
[null,"Daily Divertible Flow Tool"]
[null,"Suitable Floodplain Habitat"]
[]
[null,"Documentation (Appendices)"]