## Combined General
Risk ID No. | HR or HC | Risk Category | Risk Location | What is the Problem or Issue? | Description of Consequences What Could go Wrong, How? | Unmitigated Rating |  |  | Mitigation Techniques |  |  |  | Mitigated Rating |  |  | Risk Rating Buy Down
|  |  |  | Risk Description | Consequences | Likelihood Rating Probability of Deviation from Expectation | Consequence Rating Severity of Impact on Project Outcomes | Unmitigated Risk Factor | Recommended Mitigation(s) for Reducing or "Buying Down" the Risk |  |  |  | Likelihood | Consequence | Mitigated Risk Factor | Risk Factor Buy Down from Mitigation
[9 empty] | Type | Scope | Responsible | Cost
1 | HR | Permitting | Permitting | Delay in FERC review(s) and/or approval(s) based on recent poor performance on another project. | Schedule delays due to late receipt of license, potential contractor claims due to late receipt of design package approvals for construction. | VH | VH | 80 | FERC Consultation by Agency and Engineer | Close agency coordination, effective communication, early agency involvement in project reviews (including pre-payment of a portion of the fee to utilize their time), utilize consultants with proven experience in working with FERC on a day to day basis (office and field), and/or defer FERC licensing and installation of hydroelectric generating capability. |  |  | M | M | 12 | 68
1 | HC | Permitting | Permitting | Delay in FERC review(s) and/or approval(s) based on recent poor performance on another project. | Schedule delays due to late receipt of license, potential contractor claims due to late receipt of design package approvals for construction. | VH | VH | 80 | FERC Consultation by Agency and Engineer | Close agency coordination, effective communication, early agency involvement in project reviews (including pre-payment of a portion of the fee to utilize their time), utilize consultants with proven experience in working with FERC on a day to day basis (office and field), and/or defer FERC licensing and installation of hydroelectric generating capability. |  |  | M | M | 12 | 68
2 | HR | Permitting | Permitting | The conditions of the joint Federally-listed and State-listed species (Delta Smelt, salmonids, sturgeon, and Killer Whale) and the State-listed Long-fin Smelt are declining. | Delays in schedule, reduced ability to fill the reservoir (reduced deliveries), and increased costs. | VH | VH | 80 |  | Cannot depend upon current biological opinions issued to DWR and Reclamation. This project will require separate Federal biological opinions from U.S. Fish and Wildlife Service and National Marine Fisheries Service, and take authorization from California Department of Fish and Wildlife. Preparation of an adequate biological assessment and negotiation of the biological opinions and take authorization could take time, and will probably result in restrictions of construction boundaries, construction methods, construction time periods, and additional environmental protections during construction. The biological opinions also could result in changes to the design of facilities to minimize light, glare, noise, and vibrations (including items like noise from fans in pump stations). The biological opinions and take authorizations also could result in currently not-defined limitations on diversion volumes and rates and timing of diversions. |  |  | M | M | 12 | 68
2 | HC | Permitting | Permitting | The conditions of the joint Federally-listed and State-listed species (Delta Smelt, salmonids, sturgeon, and Killer Whale) and the State-listed Long-fin Smelt are declining. | Delays in schedule, reduced ability to fill the reservoir (reduced deliveries), and increased costs. | VH | VH | 80 |  | Cannot depend upon current biological opinions issued to DWR and Reclamation. This project will require separate Federal biological opinions from U.S. Fish and Wildlife Service and National Marine Fisheries Service, and take authorization from California Department of Fish and Wildlife. Preparation of an adequate biological assessment and negotiation of the biological opinions and take authorization could take time, and will probably result in restrictions of construction boundaries, construction methods, construction time periods, and additional environmental protections during construction. The biological opinions also could result in changes to the design of facilities to minimize light, glare, noise, and vibrations (including items like noise from fans in pump stations). The biological opinions and take authorizations also could result in currently not-defined limitations on diversion volumes and rates and timing of diversions. |  |  | M | M | 12 | 68
3 | HR | Permitting | Permitting | Project will require a new water right from the SWRCB | It is anticipated that the application for the permit will result in protests by other legal users of water and concerned groups for the biological resources in the Sacramento River and the Delta. The hearings could require up to a year to allow for testimony from the applicant and protesters. The final water right permit could result in currently not-defined limitations on diversion volumes and rates and timing of diversions. | VH | VH | 80 | Water Rights | Requires significant upfront investment in legal and technical support and planning. |  |  | M | M | 12 | 68
3 | HC | Permitting | Permitting | Project will require a new water right from the SWRCB | It is anticipated that the application for the permit will result in protests by other legal users of water and concerned groups for the biological resources in the Sacramento River and the Delta. The hearings could require up to a year to allow for testimony from the applicant and protesters. The final water right permit could result in currently not-defined limitations on diversion volumes and rates and timing of diversions. | VH | VH | 80 | Water Rights | Requires significant upfront investment in legal and technical support and planning. |  |  | M | M | 12 | 68
4 | HR | Cost Schedule Permitting | Borrow Areas | Large haul distance to sand and gravel pits currently identified for concrete aggregate and dam filter and drain material (up to 35 miles from site). Existing quarries may not have the capacity to supply the materials in the quantity and timeframe for the project. | Increased cost to project, increased environmental impact and mitigation requirements. | VH | VH | 80 | Geotechnical Investigations, Estimating | Investigate current proposed source and other suitable sources of sand and gravel in the project region on both east and west sides of the reservoir to reduce reliance on commercial sources. |  |  | M | M | 12 | 68
4 | HC | Cost Schedule Permitting | Borrow Areas | Large haul distance to sand and gravel pits currently identified for concrete aggregate and dam filter and drain material (up to 35 miles from site). | Increased cost to project, increased environmental impact and mitigation requirements. | VH | VH | 80 | Geotechnical Investigations, Estimating | Investigate current proposed source and other suitable sources of sand and gravel in the project region on both east and west sides of the reservoir. |  |  | M | M | 12 | 68
5 | HR | Design Safety Cost | Pumping Plants | Suitability of pump station foundations and foundation excavations | Unsuitable foundation conditions, possible need for foundation piling at TRR and Sacramento River. | VH | VH | 80 | Geotechnical Investigations | Drilling, mapping, seismic refraction surveys, laboratory investigations |  | 125000 | L | L | 4 | 76
5 | HC | Design Safety Cost | Pumping Plants | Suitability of pump station foundations and foundation excavations | Unsuitable foundation conditions, possible need for foundation piling at TRR PGP and Funks PGP. | VH | VH | 80 | Geotechnical Investigations | Drilling, mapping, seismic refraction surveys, laboratory investigations |  | 125000 | L | L | 4 | 76
6 | HR |  | System Operations | Significantly reduced ability to divert water from the Sacramento River | Inability to divert water from the Sacramento River to fill the reservoir | VH | VH | 80 | Permits Operations | Develop acceptable diversion strategy or identify alternative water sources |  | 2000000 | H | M | 16 | 64
6 | HC |  | System Operations | Significantly reduced ability to divert water from the Sacramento River | Inability to divert water from the Sacramento River to fill the reservoir | VH | VH | 80 | Permits Operations | Develop acceptable diversion strategy or identify alternative water sources |  | 2000000 | H | M | 16 | 64
7 | HR | Planning Cost Impact identification | General | Currently, only undocumented, localized topographic mapping is available from previous studies to support design and construction planning. Available mapping is old. | Heightened risk of inaccuracy in laying out project facilities and estimating quantities; heightened risk of impacting existing features, facilities, and utilities not currently identified on available mapping; heightened risk of missing potential environmental impacts. | H | VH | 64 | Topographic Mapping | Topographic Mapping: Complete topographic mapping of project area from ground-controlled aerial photography. New aerial photography will also benefit the project for planning purposes and preparation of exhibits and plans. |  |  | L | L | 4 | 60
7 | HC | Planning Cost Impact identification | General | Currently, only undocumented, localized topographic mapping is available from previous studies to support design and construction planning. Available mapping is old. | Heightened risk of inaccuracy in laying out project facilities and estimating quantities; heightened risk of impacting existing features, facilities, and utilities not currently identified on available mapping; heightened risk of missing potential environmental impacts. | H | VH | 64 | Topographic Mapping | Topographic Mapping: Complete topographic mapping of project area from ground-controlled aerial photography. New aerial photography will also benefit the project for planning purposes and preparation of exhibits and plans. |  |  | L | L | 4 | 60
8 | HR | Financial Viability | General | Insufficient stakeholder participation to fund the project | Termination of project, loss of expended funds. | H | VH | 64 | Outreach | Investor outreach workshops, high quality WSIP application, support federal feasibility study and federal funding, political outreach. |  |  | M | H | 24 | 40
8 | HC | Financial Viability | General | Insufficient stakeholder participation to fund the project | Termination of project, loss of expended funds. | H | VH | 64 | Outreach | Investor outreach workshops, high quality WSIP application, support federal feasibility study and federal funding, political outreach. |  |  | M | H | 24 | 40
9 | HR | Permitting Cost Schedule | Permitting | Unidentified human remains associated with native American burials outside official cemeteries. | Permitting and construction delays | H | VH | 64 | Archaeologic Evaluation | Execute field surveys as soon as possible to identify risk and remediation cost. |  |  | M | L | 6 | 58
9 | HC | Permitting Cost Schedule | Permitting | Unidentified human remains associated with native American burials outside official cemeteries. | Permitting and construction delays | H | VH | 64 | Archaeologic Evaluation | Execute field surveys as soon as possible to identify risk and remediation cost. |  |  | M | L | 6 | 58
10 | HR | Cost Schedule | Sites Reservoir | South bridge abutment and foundation conditions are unknown | Unreliable design, increased cost, delay to schedule as bridge is constructed early. | VH | VH | 80 | Geotechnical Investigations | Drilling program, laboratory testing |  |  | L | L | 4 | 76
10 | HC | Cost Schedule | Sites Reservoir | South bridge abutment and foundation conditions are unknown | Unreliable design, increased cost, delay to schedule as bridge is constructed early. | H | VH | 64 | Geotechnical Investigations | Drilling program, laboratory testing |  |  | L | L | 4 | 60
11 | HR | Safety Schedule Cost | Main Dams | Foundation conditions need to be better defined at both dam sites. | Construction delays, additional cost for increased excavation and rock stabilization, additional costs for foundation preparation and grouting. | H | VH | 64 | Geotechnical Investigation | Additional site investigation (drilling water pressure testing, seismic refraction). |  |  | L | M | 8 | 56
11 | HC | Safety Schedule Cost | Main Dams | Foundation conditions need to be better defined at both dam sites. | Construction delays, additional cost for increased excavation and rock stabilization, additional costs for foundation preparation and grouting. | H | VH | 64 | Geotechnical Investigation | Additional site investigation (drilling water pressure testing, seismic refraction). |  |  | L | M | 8 | 56
12 | HR | Cost Schedule | Main Dams | Insufficient information to plan and cost foundation grouting. |  | H | VH | 64 | Geotechnical Investigation | Water pressure testing, test grouting program. |  |  | M | M | 12 | 52
12 | HC | Cost Schedule | Main Dams | Insufficient information to plan and cost foundation grouting. |  | H | VH | 64 | Geotechnical Investigation | Water pressure testing, test grouting program. |  |  | M | M | 12 | 52
13 | HR | Cost Schedule | Main Dams | Insufficient information available to evaluate dam alternative that could be better. | Higher cost, longer schedule for construction. | H | VH | 64 | Alternative Evaluations | Comprehensive evaluation of RCC and concrete-faced rockfill dam alternatives, ie., geotechnical evaluation of required material sources and properties and suitable foundation conditions. |  |  | L | L | 4 | 60
13 | HC | Cost Schedule | Main Dams | Insufficient information available to evaluate dam alternative that could be better. | Higher cost, longer schedule for construction. | H | VH | 64 | Alternative Evaluations | Comprehensive evaluation of RCC and concrete-faced rockfill dam alternatives, ie., geotechnical evaluation of required material sources and suitable foundation conditions. |  |  | L | L | 4 | 60
14 | HR | Cost Schedule | Saddle Dams | Insufficient information to plan and cost foundation grouting. |  | H | VH | 64 | Geotechnical Investigation | Water pressure testing, test grouting program. |  |  | M | M | 12 | 52
14 | HC | Cost Schedule | Saddle Dams | Insufficient information to plan and cost foundation grouting. |  | H | VH | 64 | Geotechnical Investigation | Water pressure testing, test grouting program. |  |  | M | M | 12 | 52
15 | HR | Safety Schedule Cost | Saddle Dams | Foundation conditions need to be better defined at both dam sites. | Construction delays, additional cost for increased excavation and rock stabilization, additional costs for foundation preparation and grouting. | H | VH | 64 | Geotechnical Investigation | Additional site investigation (drilling water pressure testing, seismic refraction). |  |  | L | M | 8 | 56
15 | HC | Safety Schedule Cost | Saddle Dams | Foundation conditions need to be better defined at both dam sites. | Construction delays, additional cost for increased excavation and rock stabilization, additional costs for foundation preparation and grouting. | H | VH | 64 | Geotechnical Investigation | Additional site investigation (drilling water pressure testing, seismic refraction). |  |  | L | M | 8 | 56
16 | HR | Safety Engineering permitting | Holthouse Reservoir | Spillway adequacy to handle emergency releases. | Downstream channel impacts need to be addressed. | H | VH | 64 | Engineering Environmental Assessments | Determine design flow assuming split in flows between Golden Gate Dam and Sites Dam diversion tunnel. Determine impacts to Funks Creek and public and private facilities downstream. |  |  | L | M | 8 | 56
16 | HC | Safety Engineering permitting | Holthouse Reservoir | Spillway adequacy to handle emergency releases. | Downstream channel impacts need to be addressed. | H | VH | 64 | Engineering Environmental Assessments | Determine design flow assuming split in flows between Golden Gate Dam and Sites Dam diversion tunnel. Determine impacts to Funks Creek and public and private facilities downstream. |  |  | L | M | 8 | 56
17 | HR | Coordination Engineering | Holthouse Reservoir | Several WAPA towers exist in the planned Holthouse reservoir expansion area. | Tower Relocation for new Reservoir may be needed. WAPA expressing concern. | VH | H | 40 | Alternative Investigations | Conduct alternative evaluation to relocate the two lines in question. Early and ongoing coordination with WAPA to resolve the conflict in line location. |  |  | L | L | 4 | 36
17 | HC | Coordination Engineering | Holthouse Reservoir | Several WAPA towers exist in the planned Holthouse reservoir expansion area. | Tower Relocation for new Reservoir may be needed. WAPA expressing concern. | VH | H | 40 | Alternative Investigations | Conduct alternative evaluation to relocate the two lines in question. Early and ongoing coordination with WAPA to resolve the conflict in line location. |  |  | L | L | 4 | 36
18 | HR | Design Safety Cost | Pumping Plants | Suitability of fish screen structure and cofferdam in Sacramento River | Unsuitable foundation conditions, lack of data to design in-river cofferdam system and foundation piles for fish screen structure. | H | VH | 64 | Geotechnical Investigations | Geotechnical Investigations: Drilling, mapping, laboratory investigations |  |  | L | L | 4 | 60
18 | HC | Design Safety Cost | Pumping Plants | Suitability of fish screen structure and cofferdam in Sacramento River | Unsuitable foundation conditions, lack of data to design in-river cofferdam system and foundation piles for fish screen structure. | H | VH | 64 | Geotechnical Investigations | Geotechnical Investigations: Drilling, mapping, laboratory investigations |  |  | L | L | 4 | 60
19 | HR | Permitting Design | General | Site seismicity higher than previously estimated, update needed. | Current site seismicity data dating back to 2003 may be inadequate for project design and permitting dams and other major structures through state and federal agencies. | H | H | 32 | Engineering | Conduct Site Seismicity Evaluation. Prepare updated site seismicity evaluation that will meet current State (DSOD) and Federal (FERC) standards. |  |  | L | L | 4 | 28
19 | HC | Permitting Design | General | Site seismicity higher than previously estimated, update needed. | Current site seismicity data dating back to 2003 may be inadequate for project design and permitting dams and other major structures through state and federal agencies. | H | H | 32 | Engineering | Conduct Site Seismicity Evaluation. Prepare updated site seismicity evaluation that will meet current State (DSOD) and Federal (FERC) standards. |  |  | L | L | 4 | 28
20 | HR | Permitting Cost Schedule | Permitting | Environmental impact of access road to east end of bridge may require deep cut through east reservoir ridge. | Unanticipated visual and environmental impacts | H | H | 32 | Engineering Environmental Reviews | Evaluate extent of cutting; evaluate potential impacts and mitigations, evaluate tunnel through ridge option. |  |  | L | M | 8 | 24
20 | HC | Permitting Cost Schedule | Permitting | Environmental impact of access road to east end of bridge may require deep cut through east reservoir ridge. | Unanticipated visual and environmental impacts | H | H | 32 | Engineering Environmental Reviews | Evaluate extent of cutting; evaluate potential impacts and mitigations, evaluate tunnel through ridge option. |  |  | L | M | 8 | 24
21 | HR | Cost | Construction - General | Significantly higher construction bids than estimated. | Impacts to cash flow, cash reserves, financing costs during construction, cost of water, financial viability of project. | H | H | 32 | Market Analysis, Contractor Outreach | Perform a market analysis as part of each cost estimate update to project market conditions and competition with other projects at the anticipated bid time. Perform market analysis of critical materials (steel, concrete, fabricated equipment, etc.) as part of each estimate. Package work with consideration to cost to avoid limiting bidder pool due to bonding limitations. Perform cost trend analysis along with design development to inform Authority of cost changes as we proceed. |  |  | L | M | 8 | 24
21 | HC | Cost | Construction - General | Significantly higher construction bids than estimated. | Impacts to cash flow, cash reserves, financing costs during construction, cost of water, financial viability of project. | H | H | 32 | Market Analysis, Contractor Outreach | Perform a market analysis as part of each cost estimate update to project market conditions and competition with other projects at the anticipated bid time. Perform market analysis of critical materials (steel, concrete, fabricated equipment, etc.) as part of each estimate. Package work with consideration to cost to avoid limiting bidder pool due to bonding limitations. |  |  | L | M | 8 | 24
22 | HR | Cost Schedule Permitting | Borrow Areas | Lack of core and shell borrow material in vicinity of dam. No investigations available in the vicinity of the dam. | Increased haul distances and costs to construct dam. | H | H | 32 | Geotechnical Investigations | Conduct site investigation between Holthouse Dam and existing Funks Dam to verify availability of construction material to supplement material from the removal of Funks Dam. (Investigation currently in planning stage by Reclamation.) |  |  | L | L | 4 | 28
22 | HC | Cost Schedule Permitting | Borrow Areas | Lack of core and shell borrow material in vicinity of dam. No investigations available in the vicinity of the dam. | Increased haul distances and costs to construct dam. | H | H | 32 | Geotechnical Investigations | Conduct site investigation between Holthouse Dam and existing Funks Dam to verify availability of construction material to supplement material from the removal of Funks Dam. (Investigation currently in planning stage by Reclamation.) |  |  | L | L | 4 | 28
23 | HR | Safety Project Operation | Sites Reservoir | Stability of all downstream outlet tunnel portals | Impact to pump station operation Construction: worker safety; Long-term: can bury infrastructure at toe of portal | M | H | 24 | Geotechnical Investigation | Drilling program and laboratory testing Design: Include slope reinforcement and drainage. Include contract provisions for monitoring and making adjustments during construction. |  |  | L | L | 4 | 20
23 | HC | Safety Project Operation | Sites Reservoir | Stability of downstream outlet tunnel portal | Impact to pump station operation | H | H | 32 | Geotechnical Investigation | Drilling program and laboratory testing |  |  | L | L | 4 | 28
24 | HR | Cost Schedule | Main Dams | Stability of conveyance channel slopes to Holthouse Reservoir. | Slope instability requiring re-work, increased excavation quantities, unanticipated lining and stabilization for slope. | H | H | 32 | Geotechnical Investigation | Additional site investigation (drilling, seismic refraction, geo mapping). |  |  | M | L | 6 | 26
24 | HC | Cost Schedule | Main Dams | Stability of conveyance channel slopes to Holthouse Reservoir. | Slope instability requiring re-work, increased excavation quantities, unanticipated lining and stabilization for slope. | H | H | 32 | Geotechnical Investigation | Additional site investigation (drilling, seismic refraction, geo mapping). |  |  | M | L | 6 | 26
25 | HR | Safety Schedule Cost | Saddle Dams | Depth to sound rock foundation for core trench not sufficiently documented for all dams, scope of previous investigations significantly less for saddle dams than for main dams, addition data needed to design underseepage control using grout cutoff or slurry wall. | Risk to design, potential construction delays, additional construction cost, additional borrow from pits and quarries. | H | H | 32 | Geotechnical Investigations | Additional site investigation (drilling water pressure testing, seismic refraction). |  |  | L | M | 8 | 24
25 | HC | Safety Schedule Cost | Saddle Dams | Depth to sound rock foundation for core trench not sufficiently documented for all dams, scope of previous investigations significantly less for saddle dams than for main dams, addition data needed to design underseepage control using grout cutoff or slurry wall. | Risk to design, potential construction delays, additional construction cost, additional borrow from pits and quarries. | H | H | 32 | Geotechnical Investigations | Additional site investigation (drilling water pressure testing, seismic refraction). |  |  | L | M | 8 | 24
26 | HR | Safety Schedule Cost Permitting | Holthouse Reservoir | Foundation conditions need to be better defined at dam site. No data currently available to support design or permitting for DSOD or FERC. No data available on borrow material source for core. | Permitting delays, design risks, construction delays, additional cost for increased excavation, foundation preparation, and foundation grouting. | H | H | 32 | Geotechnical Investigations | Drilling, piezometers, trenches in borrow area behind proposed dam. |  |  | M | L | 6 | 26
26 | HC | Safety Schedule Cost Permitting | Holthouse Reservoir | Foundation conditions need to be better defined at dam site. No data currently available to support design or permitting for DSOD or FERC. No data available on borrow material source for core. | Permitting delays, design risks, construction delays, additional cost for increased excavation, foundation preparation, and foundation grouting. | H | H | 32 | Geotechnical Investigations | Drilling, piezometers, trenches in borrow area behind proposed dam. |  |  | M | L | 6 | 26
27 | HR | Schedule Cost Permitting | Holthouse Reservoir | Difficulties in handling sediment in Funks. | No data available about composition of sediment that has accumulated in Funks Reservoir, no data on volume of sediment that has accumulated. | H | H | 32 | Geotechnical Investigations, Bathymetry | Perform bathymetric survey of top of sediment to compare with pre-Funks topography to estimate volume; sample and test material to identify character and potential for drainage. |  |  | L | L | 4 | 28
27 | HC | Schedule Cost Permitting | Holthouse Reservoir | Difficulties in handling sediment in Funks. | No data available about composition of sediment that has accumulated in Funks Reservoir, no data on volume of sediment that has accumulated. | H | H | 32 | Geotechnical Investigations, Bathymetry | Perform bathymetric survey of top of sediment to compare with pre-Funks topography to estimate volume; sample and test material to identify character and potential for drainage. |  |  | L | L | 4 | 28
28 | HR | Cost Schedule | Delevan/TRR Pipeline | High groundwater, significant construction dewatering and pipe flotation. | Cost and schedule impact, redesign, claims | H | H | 32 | Geotechnical Investigations | Drilling, piezometers, and monitoring data evaluate tunnel alternative. |  |  | L | M | 8 | 24
28 | HC | Cost Schedule | Dunnigan Pipeline | High groundwater, significant construction dewatering and pipe flotation. | Cost and schedule impact, redesign, claims | H | H | 32 | Geotechnical Investigations | Drilling, piezometers, evaluate tunnel alternative. |  |  | L | M | 8 | 24
29 | HR | Design Cost Schedule | Delevan/TRR Pipeline | Unanticipated utilities and drainage features | Potential schedule and cost impacts, claims | H | H | 32 | Mapping and Ground Surveys | Detailed utility surveys, potholing, topographic mapping, evaluate tunnel alternative. |  |  | L | L | 4 | 28
29 | HC | Design Cost Schedule | Delevan/TRR Pipeline | Unanticipated utilities and drainage features | Potential schedule and cost impacts, claims | H | H | 32 | Mapping and Ground Surveys | Detailed utility surveys, potholing, topographic mapping, evaluate tunnel alternative. |  |  | L | L | 4 | 28
30 | HR | Permitting | Delevan/TRR Pipeline | Inability to open cut through Colusa Basin Drain and adjacent to wildlife preserves due to environmental concerns and mitigation costs. | Potential schedule and cost impacts. | H | H | 32 | Geotechnical Investigations, Alternative Evaluation | Evaluate feasibility of soft ground tunneling in restrictive areas. |  |  | L | M | 8 | 24
30 | HC | Permitting | Delevan/TRR Pipeline | Inability to open cut through Colusa Basin Drain and adjacent to wildlife preserves due to environmental concerns and mitigation costs. | Potential schedule and cost impacts. | H | H | 32 | Geotechnical Investigations, Alternative Evaluation | Evaluate feasibility of soft ground tunneling in restrictive areas. |  |  | L | M | 8 | 24
31 | HR | Design Cost Operation | Pumping Plants | Selection of pumping and generating unit number and size. | Not having the appropriate number and size of units can introduce extra cost, cause operation problems, and increase operational and maintenance costs. Can also limit the number of potential equipment suppliers. | H | H | 32 | Alternative Evaluation | Alternative Evaluations: Study alternative unit size combinations, costs, and operational flexibility to match pumping and generating requirements based on current modeling results. |  |  | L | L | 4 | 28
32 | HR | Schedule Cost | Real Estate | Property acquisition delayed | Start of construction delayed. Jeopardizes on-schedule completion. | H | H | 32 | Planning | Develop Real Estate Acquisition Plan in Phase 2 and implement acquisition and Communication Plan at the beginning of Phase 3 and provide relocation assistance |  | 10000000 | M | M | 12 | 20
32 | HC | Schedule Cost | Real Estate | Property acquisition delayed | Start of construction delayed. Jeopardizes on-schedule completion. | H | H | 32 | Planning | Develop Real Estate Acquisition Plan in Phase 2 and implement acquisition and Communication Plan at the beginning of Phase 3 and provide relocation assistance |  | 10000000 | M | M | 12 | 20
33 | HR | Permitting | Permitting | Current reservoir design assumes full storage of the Probable Maximum Flood with no emergency spillway other than minimal pipe (signal spillway) at one saddle dam. | DSOD expressed concern with no emergency spillway. | VH | M | 20 | DSOD/FERC Consultation by Agency and Engineer | Further consultation with DSOD to clarify concern; clarify minimum design criteria required by DSOD specific to the project; reflect criteria in reservoir design criteria. |  |  | L | L | 4 | 16
33 | HC | Permitting | Permitting | Current reservoir design assumes full storage of the Probable Maximum Flood with no emergency spillway other than minimal pipe (signal spillway) at one saddle dam. | DSOD expressed concern with no emergency spillway. | VH | M | 20 | DSOD/FERC Consultation by Agency and Engineer | Further consultation with DSOD to clarify concern; clarify minimum design criteria required by DSOD specific to the project; reflect criteria in reservoir design criteria. |  |  | L | L | 4 | 16
34 | HR | Permitting | Permitting | Delay in DSOD review(s) and/or approval(s) | Schedule delays, potential contractor claims. | M | VH | 48 | DSOD Consultation by Agency and Engineer | Close agency coordination, effective communication, early agency involvement in the project (including pre-payment of a portion of the fee to utilize their time), utilize consultants with proven experience in working with DSOD on a day to day basis (office and field). |  |  | M | M | 12 | 36
34 | HC | Permitting | Permitting | Delay in DSOD review(s) and/or approval(s) | Schedule delays, potential contractor claims. | M | VH | 48 | DSOD Consultation by Agency and Engineer | Close agency coordination, effective communication, early agency involvement in the project (including pre-payment of a portion of the fee to utilize their time), utilize consultants with proven experience in working with DSOD on a day to day basis (office and field). |  |  | M | M | 12 | 36
35 | HR | Cost Schedule Claims | Construction - General | Interference among various contractors working on site due to poor packaging of project work. | Work activity interference, lack of access to work areas by multiple contractors simultaneously, restricted availability of materials (aggregate, cement, steel, power). Can lead to schedule delays and claims. | M | VH | 48 | Bidding Strategy | Develop a bidding strategy to package and schedule the work to minimize work interfaces between packages. Evaluate and include coordination requirements in contract documents, including critical milestone dates to vacate work areas or complete components of the work. Develop/implement a management plan that includes coordination. |  |  | L | M | 8 | 40
35 | HC | Cost Schedule Claims | Construction - General | Interference among various contractors working on site due to poor packaging of project work. | Work activity interference, lack of access to work areas by multiple contractors simultaneously, restricted availability of materials (aggregate, cement, steel, power). Can lead to schedule delays and claims. | M | VH | 48 | Bidding Strategy | Develop a bidding strategy to package and schedule the work to minimize work interfaces between packages. Evaluate and include coordination requirements in contract documents, including critical milestone dates to vacate work areas or complete components of the work. Develop/implement a management plan that includes coordination. |  |  | L | M | 8 | 40
36 | HR | Schedule Cost | Construction - General | Delay(s) in mechanical equipment fabrication, delivery, and quality control testing | Installation and construction completion delays, startup and commissioning delays. | M | VH | 48 | Planning Contracting | Early market analysis of shop floor availability. Possible pre-procurement of major mechanical/electrical components that are critical path items. |  |  | L | VH | 32 | 16
36 | HC | Schedule Cost | Construction - General | Delay(s) in mechanical equipment fabrication, delivery, and quality control testing | Installation and construction completion delays, startup and commissioning delays. | M | VH | 48 | Planning Contracting | Early market analysis of shop floor availability. Possible pre-procurement of major mechanical/electrical components that are critical path items. |  |  | L | VH | 32 | 16
37 | HR | Cost Schedule Permitting | Borrow Areas | Core borrow quantity available in reservoir for main dams and saddle dams. | Increased cost to project, increased environmental impact and mitigation requirements. | M | VH | 48 | Geotechnical Investigations, Estimating | Review of all available DWR data, supplemental investigations and testing as necessary. |  |  | L | L | 4 | 44
37 | HC | Cost Schedule Permitting | Borrow Areas | Core borrow quantity available in reservoir for main dams and saddle dams. | Increased cost to project, increased environmental impact and mitigation requirements. | M | VH | 48 | Geotechnical Investigations, Estimating | Review of all available DWR data, supplemental investigations and testing as necessary. |  |  | L | L | 4 | 44
38 | HR | Cost Schedule Permitting | Borrow Areas | Lack of rockfill and riprap quantity available in reservoir ridges and other excavations for main dams, saddle dams, and roadway causeway fill prism, including impact of interbedded soft and hard rock layers. | Increased cost to project, increased environmental impact and mitigation requirements. | M | VH | 48 | Geotechnical Investigations, Estimating | Review of all available DWR data, supplemental investigations and testing as necessary. |  |  | L | L | 4 | 44
38 | HC | Cost Schedule Permitting | Borrow Areas | Rock fill and rip rap quantity available in reservoir ridges and other excavations for main dams and saddle dams, including impact of interbedded soft and hard rock layers.. | Increased cost to project, increased environmental impact and mitigation requirements. | M | VH | 48 | Geotechnical Investigations, Estimating | Review of all available DWR data, supplemental investigations and testing as necessary. |  |  | L | L | 4 | 44
39 | HR | Safety Resource Protection Permitting | Sites Reservoir | East Rim Seepage | Loss of water resource, seeps and springs on east side, east side slope instability | M | VH | 48 | Geotechnical Investigations | Drilling program with water pressure testing to evaluate seepage potential and design mitigation measures (rim grouting) |  |  | L | L | 4 | 44
39 | HC | Safety Resource Protection Permitting | Sites Reservoir | East Rim Seepage | Loss of water resource, seeps and springs on east side, east side slope instability | M | VH | 48 | Geotechnical Investigations | Drilling program with water pressure testing to evaluate seepage potential and design mitigation measures (rim grouting) |  |  | L | L | 4 | 44
40 | HR | Safety Project Operation | Sites Reservoir | Stability of outlet works tower Intake excavation: Rock is not found where inferred from borings resulting in a requirement for more excavation | Loss of reservoir control Increase excavation and concrete costs. Delays to construction. | M | M | 12 | Evaluate Alternatives Engineering | Evaluate stability under static and seismic loading; evaluate alternatives, including sloping intake replacement. Design: Conduct a thorough geotechnical site investigation. Flexible design to accommodate rock being found at somewhat different elevations than expected. |  |  | L | VL | 2 | 10
40 | HC | Safety Project Operation | Sites Reservoir | Stability of outlet works tower | Loss of reservoir control | M | VH | 48 | Evaluate Alternatives | Evaluate stability under static and seismic loading; evaluate alternatives, including sloping intake replacement. |  |  | L | L | 4 | 44
41 | HR | Safety Schedule Constructability | Sites Reservoir | Stability of tunnel during excavation | Adverse impacts to construction cost and schedule, potential for claims. | M | VH | 48 | Geotechnical Investigations | Drilling program, engineering studies Design: Thorough geotechnical investigation, Geotechnical interpretaive report (GIR), GBR, Contingency in cost estimate; strengthened different site conditions clause; use of Dispute Resolution Board (DRB) and facilitated partnering; Add provisions for controlled blasting if material is harder than expected and for toolbox of items if additional support is needed. Construction: Qualified CM, 24/7 tunnel inspection |  |  | L | L | 4 | 44
41 | HC | Safety Schedule Constructability | Sites Reservoir | Stability of tunnel during excavation | Adverse impacts to construction cost and schedule, potential for claims. | M | VH | 48 | Geotechnical Investigations | Drilling program, engineering studies |  |  | L | L | 4 | 44
42 | HC | Cost Schedule | Main Dams | Dam axis not in optimum location to minimize cost. | Increased construction cost, increased need for imported filter/drain aggregates, increased DSOD permitting costs. | M | VH | 48 | Geotechnical Investigation, Alternative Evaluation | Additional site investigation (drilling water pressure testing, seismic refraction), alternative location evaluations. |  |  | L | L | 4 | 44
43 | HR | Cost Schedule | Saddle Dams | Dam axis not in optimum location to minimize cost. | Increased construction cost, increased need for imported filter/drain aggregates, increased DSOD permitting costs. | M | VH | 48 | Geotechnical Investigation, Alternative Evaluation | Additional site investigation (drilling water pressure testing, seismic refraction), alternative location evaluations. |  |  | L | L | 4 | 44
43 | HC | Cost Schedule | Saddle Dams | Dam axis not in optimum location to minimize cost. | Increased construction cost, increased need for imported filter/drain aggregates, increased DSOD permitting costs. | M | VH | 48 | Geotechnical Investigation, Alternative Evaluation | Additional site investigation (drilling water pressure testing, seismic refraction), alternative location evaluations. |  |  | L | L | 4 | 44
44 | HR | Design Cost Schedule | TRR Reservoir | High Groundwater | Increased reservoir footprint required due to high groundwater | M | VH | 48 | Geotechnical Investigations | Drilling and test pits, piezometers. |  |  | L | L | 4 | 44
45 | HR | Design Operation | TRR Reservoir | Rapid drawdown liner failure | Operational impacts, shutdown of Reservoir/canal | M | VH | 48 | Geotechnical Investigations | Review of geotec site conditions, drilling, appropriate liner and slope design. |  |  | L | L | 4 | 44
46 | HR | Cost Schedule | Pumping Plants | Delays in procuring major mechanical and electrical equipment. | Construction delays, start up and commissioning delays. Reservoir filling delays. | M | VH | 48 | Planning Contracting | Early market analysis of shop floor availability. Possible pre-procurement of major mechanical/electrical components that are critical path items. |  |  | L | VH | 32 | 16
47 | HR | Schedule Cost | General | New stakeholders (e.g., Board, JPA staff, member agencies). | Slows forward project momentum, could impact project configuration. | M | H | 24 | Team Building | Accelerated effort to bring new players up to speed as quickly as possible, limit ability of new players by agreement to radically modify project technical and financial details. |  |  | L | L | 4 | 20
47 | HC | Schedule Cost | General | New stakeholders (e.g., Board, JPA staff, member agencies). | Slows forward project momentum, could impact project configuration. | M | H | 24 | Team Building | Accelerated effort to bring new players up to speed as quickly as possible, limit ability of new players by agreement to radically modify project technical and financial details. |  |  | L | L | 4 | 20
48 | HR | Permitting Schedule Cost | Permitting | New endangered species identified. | Schedule delays, added cost, additional environmental studies, amendments required to EIR/EIS documents, unanticipated additional mitigation costs. | M | H | 24 | Agency Action | Early acquisition of easements and property with on-going land management. |  |  | L | M | 8 | 16
48 | HC | Permitting Schedule Cost | Permitting | New endangered species identified. | Schedule delays, added cost, additional environmental studies, amendments required to EIR/EIS documents, unanticipated additional mitigation costs. | M | H | 24 | Agency Action | Early acquisition of easements and property with on-going land management. |  |  | L | M | 8 | 16
49 | HR | Cost Schedule Claims | Construction - General | Excessive flooding occurs during construction. | Loss of complete work, schedule delays due to the event and to make repairs. | M | H | 24 | Planning Engineering | Develop a bidding strategy to package and schedule the work to minimize work interfaces between packages. Evaluate and include coordination requirements in contract documents, including critical milestone dates to vacate work areas or complete components of the work. Develop/implement a management plan that includes coordination. Planning: Clearly define design floods during construction and model floodplains. Design: Confirm proper flood protection measures (such as cofferdams and diversions) are in place during construction. |  |  | L | M | 8 | 16
49 | HC | Cost Schedule Claims | Construction - General | Excessive flooding occurs during construction. | Loss of complete work, schedule delays due to the event and to make repairs. | M | H | 24 | Planning Engineering | Develop a bidding strategy to package and schedule the work to minimize work interfaces between packages. Evaluate and include coordination requirements in contract documents, including critical milestone dates to vacate work areas or complete components of the work. Develop/implement a management plan that includes coordination. |  |  | L | M | 8 | 16
50 | HR | Safety | Construction - General | Serious accident(s) during construction. |  | M | H | 24 | Engineering Contracting | Implement a safety-by-design approach to comply with applicable industrial safety standards and minimize creating unsafe conditions. Require contractors to comply with all applicable federal and state safety requirements and have detailed job safety plans and work activity risk assessments. Provide a qualified safety officer on the construction management team to monitor performance, and enforce safety requirements if needed. |  |  | L | M | 8 | 16
50 | HC | Safety | Construction - General | Serious accident(s) during construction. |  | M | H | 24 | Engineering Contracting | Implement a safety-by-design approach to comply with applicable industrial safety standards and minimize creating unsafe conditions. Require contractors to comply with all applicable federal and state safety requirements and have detailed job safety plans and work activity risk assessments. Provide a qualified safety officer on the construction management team to monitor performance, and enforce safety requirements if needed. |  |  | L | M | 8 | 16
51 | HR | Cost Schedule | Construction - General | Disruption in availability of materials (cement, steel, rebar, etc.). | Reduced progress, increased cost, higher bids if disruption occurs at bid time. | M | H | 24 | Engineering Contracting | Conduct market analysis prior to bidding. If disruption is possible, consider including provisions in contract for contractor(s) to pre-procure sufficient material at NTP and cover storage costs to avoid shortage delays. |  |  | L | M | 8 | 16
51 | HC | Cost Schedule | Construction - General | Disruption in availability of materials (cement, steel, rebar, etc.). | Reduced progress, increased cost, higher bids if disruption occurs at bid time. | M | H | 24 | Engineering Contracting | Conduct market analysis prior to bidding. If disruption is possible, consider including provisions in contract for contractor(s) to pre-procure sufficient material at NTP and cover storage costs to avoid shortage delays. |  |  | L | M | 8 | 16
52 | HR | Cost | Construction - General | Unexpected escalation/run-up in price of construction materials and labor | Cost increases. | M | H | 24 | Contracting | Lock in price at award of contract, transfer risk to contractor. |  |  | L | L | 4 | 20
52 | HC | Cost | Construction - General | Unexpected escalation/run-up in price of construction materials and labor | Cost increases. | M | H | 24 | Contracting | Lock in price at award of contract, transfer risk to contractor. |  |  | L | L | 4 | 20
53 | HR | Schedule Cost Quality | Construction - General | Unsatisfactory performance by contractor(s) | Schedule delays, poor work quality. | M | H | 24 | Planning Contracting | Prequalify contractors for major packages. Performance goals and milestone dates in contract with liquidated damages. |  |  | L | H | 16 | 8
53 | HC | Schedule Cost Quality | Construction - General | Unsatisfactory performance by contractor(s) | Schedule delays, poor work quality. | M | H | 24 | Planning Contracting | Prequalify contractors for major packages. Performance goals and milestone dates in contract with liquidated damages. |  |  | L | H | 16 | 8
54 | HR | Cost | Construction - General | Availability of construction materials | The availability of materials could be impacted by WSIP awards to multiple projects at once, creating competition for materials | H | M | 16 | Planning | Keep track of potential concurrent multiple projects to adjust project compenent delivery time frames. Risk is project delays.
54 | HC | Cost | Construction - General | Availability of construction materials | The availability of materials could be impacted by WSIP awards to multiple projects at once, creating competition for materials | H | M | 16 | Planning
55 | HR | Safety Schedule Cost | Main Dams | Rock toppling issues in core trench excavations on slopes due to adverse rock bedding. | Construction delays, addition cost for increased excavation and rock stabilization. | M | H | 24 | Geotechnical Investigation | Additional drilling and geologic mapping of rock outcrops. |  |  | M | L | 6 | 18
55 | HC | Safety Schedule Cost | Main Dams | Rock toppling issues in core trench excavations on slopes due to adverse rock bedding. | Construction delays, addition cost for increased excavation and rock stabilization. | M | H | 24 | Geotechnical Investigation | Additional drilling and geologic mapping of rock outcrops. |  |  | M | L | 6 | 18
56 | HR | Cost Schedule | Delevan/TRR Pipeline | Encountering unsuitable foundation soils, particularly in CBD area. | Potential schedule and cost impacts, claims | H | M | 16 | Geotechnical Investigations | Drilling, sampling, laboratory testing, evaluate tunnel alternative. |  |  | L | L | 4 | 12
56 | HC | Cost Schedule | Dunnigan Pipeline | Encountering unsuitable foundation soils, particularly in CBD area. | Potential schedule and cost impacts, claims | H | M | 16 | Geotechnical Investigations | Drilling, sampling, laboratory testing, evaluate tunnel alternative. |  |  | L | L | 4 | 12
57 | HR | Cost Schedule | Delevan/TRR Pipeline | Encountering hard foundations (rock) west of GC Canal. | Potential schedule and cost impacts, claims | H | M | 16 | Geotechnical Investigations | Drilling, seismic refraction surveys, evaluate tunnel alternative. |  |  | L | L | 4 | 12
57 | HC | Cost Schedule | Funks/TRR Pipeline | Encountering hard foundations (rock) west of GCID Canal. | Potential schedule and cost impacts, claims | H | M | 16 | Geotechnical Investigations | Drilling, seismic refraction surveys, evaluate tunnel alternative. |  |  | L | L | 4 | 12
58 | HR | Cost Schedule | TRR Reservoir | Pump station foundation | Unsuitable foundation conditions | M | H | 24 | Geotechnical Investigations | Drilling, piezometers |  |  | L | L | 4 | 20
59 | HR | Schedule Cost | Intake | Wildlife at intake location (yellow billed cuckoo, bank swallow, and giant garter snake) | Difficulty in obtaining permits | H | M | 16 | Planning | Mitigation with compensatory acreage, pre-construction development of compensatory habitat, and reduced construction periods |  | 300000 | H | L | 8 | 8
59 | HC | Schedule Cost | Intake | Wildlife at intake location (yellow billed cuckoo, bank swallow, and giant garter snake) | Difficulty in obtaining permits | H | M | 16 | Planning | Mitigation with compensatory acreage, pre-construction development of compensatory habitat, and reduced construction periods |  | 300000 | H | L | 8 | 8
60 | HR | Schedule | Real Estate | Failure to acquire temporary entry permits on schedule. | Delay to completion of design and potential quality impact is timely access cannot be arranged. | H | M | 16 | Planning | Develop Real Estate Communication Plan and initiate temporary entry permit process prior to or at the beginning of Phase 2 |  | 200000 | H | L | 8 | 8
60 | HC | Schedule | Real Estate | Failure to acquire temporary entry permits on schedule. | Delay to completion of design and potential quality impact is timely access cannot be arranged. | H | M | 16 | Planning | Develop Real Estate Communication Plan and initiate temporary entry permit process prior to or at the beginning of Phase 2 |  | 200000 | H | L | 8 | 8
61 | HR | Schedule Cost | Real Estate | Potential requirement for condemnation of property for acquisition | Legal process delays construction | M | H | 24 | Planning | Develop robust alternative analysis in the EIR/S to support condemnation |  |  | M | M | 12 | 12
61 | HC | Schedule Cost | Real Estate | Potential requirement for condemnation of property for acquisition | Legal process delays construction | M | H | 24 | Planning | Develop robust alternative analysis in the EIR/S to support condemnation |  |  | M | M | 12 | 12
62 | HR | Permitting Schedule Cost | Permitting | Rejection of mitigation package by resource agencies. | Construction start delays, over-all schedule delays, added cost. | L | VH | 32 | Agency Coordination | Close coordination with agencies in pre-design. |  |  | L | M | 8 | 24
62 | HC | Permitting Schedule Cost | Permitting | Rejection of mitigation package by resource agencies. | Construction start delays, over-all schedule delays, added cost. | L | VH | 32 | Agency Coordination | Close coordination with agencies in pre-design. |  |  | L | M | 8 | 24
63 | HR | Permitting Schedule Cost | Permitting | Significant design feature(s) not covered in EIR/EIS document. | Schedule delays, added cost, additional environmental studies, amendments required to EIR/EIS documents, unanticipated additional mitigation costs. | L | VH | 32 | Engineering | Good early definition of all project components and footprints. |  |  | L | L | 4 | 28
63 | HC | Permitting Schedule Cost | Permitting | Significant design feature(s) not covered in EIR/EIS document. | Schedule delays, added cost, additional environmental studies, amendments required to EIR/EIS documents, unanticipated additional mitigation costs. | L | VH | 32 | Engineering | Good early definition of all project components and footprints. |  |  | L | L | 4 | 28
64 | HR | Schedule | Construction - General | Availability of power during construction | Construction delays, startup and testing delays, reservoir filling delays. | L | VH | 32 | Planning Coordination Engineering | Pre-planning and coordination with WAPA and PG&E to make sure power is available for construction, and that any required system upgrades are in place on schedule to support startup and testing. |  |  | L | L | 4 | 28
64 | HC | Schedule | Construction - General | Availability of power during construction | Construction delays, startup and testing delays, reservoir filling delays. | L | VH | 32 | Planning Coordination Engineering | Pre-planning and coordination with WAPA and PG&E to make sure power is available for construction, and that any required system upgrades are in place on schedule to support startup and testing. |  |  | L | L | 4 | 28
65 | HR | Safety Cost Permitting | Sites Reservoir | No prior consideration given to damage to Funks Creek downstream of Holthouse and Stone Corral Creek from emergency project releases. | Major erosion damage and potential damage to crops and structures, potential damage to roads and road closures. | L | VH | 32 | Engineering and Environmental Evaluation | Evaluate potential damage and identify potential mitigation measures to include in project design and in emergency response planning. |  |  | L | M | 8 | 24
65 | HC | Safety Cost Permitting | Sites Reservoir | No prior consideration given to damage to Funks Creek downstream of Holthouse and Stone Corral Creek from emergency project releases. | Major erosion damage and potential damage to crops and structures, potential damage to roads and road closures. | L | VH | 32 | Engineering and Environmental Evaluation | Evaluate potential damage and identify potential mitigation measures to include in project design and in emergency response planning. |  |  | L | M | 8 | 24
66 | HR | Cost | General | Higher appraisal/acquisition cost than budgeted for. | Cost impact, impact to project financial evaluation and BC ratio. | M | M | 12 | Consultant Services | Thorough, conservative evaluation of land costs, periodically updated, using consultants/agents familiar with real estate in project region. |  |  | L | L | 4 | 8
66 | HC | Cost | General | Higher appraisal/acquisition cost than budgeted for. | Cost impact, impact to project financial evaluation and BC ratio. | M | M | 12 | Consultant Services | Thorough, conservative evaluation of land costs, periodically updated, using consultants/agents familiar with real estate in project region. |  |  | L | L | 4 | 8
67 | HR | Permitting Schedule | Permitting | Public concerns - Recreation / Construction (light, traffic, noise) | Permitting delays due to public comments/concerns | M | M | 12 |  | Public outreach. |  |  | L | L | 4 | 8
67 | HC | Permitting Schedule | Permitting | Public concerns - Recreation / Construction (light, traffic, noise) | Permitting delays due to public comments/concerns | M | M | 12 |  | Public outreach. |  |  | L | L | 4 | 8
68 | HR | Permitting | Permitting | Agency restrictions for discharging ground/construction water onto surface water | Cost impact | M | M | 12 |  | Clarify agency requirements for EIR/EIS documents and include requirements in construction contract documents. |  |  | L | L | 4 | 8
68 | HC | Permitting | Permitting | Agency restrictions for discharging ground/construction water onto surface water | Cost impact | M | M | 12 |  | Clarify agency requirements for EIR/EIS documents and include requirements in construction contract documents. |  |  | L | L | 4 | 8
69 | HR | Safety Resource Protection Project Operation | Sites Reservoir | High pressure water leakage out of the tunnel during operation | Impact to natural and excavated slopes from unanticipated leakage. | M | M | 12 | Geotechnical Investigations | Drilling program, Water pressure tests to evaluate tunnel lining requirements, confirm with hydrojacking tests during construction. |  |  | L | L | 4 | 8
69 | HC | Safety Resource Protection Project Operation | Sites Reservoir | High pressure water leakage out of the tunnel during operation | Impact to natural and excavated slopes from unanticipated leakage. | M | M | 12 | Geotechnical Investigations | Drilling program, Water pressure tests to evaluate tunnel lining requirements, confirm with hydrojacking tests during construction. |  |  | L | L | 4 | 8
70 | HR | Permitting | Holthouse Reservoir | Dam construction can impact alkaline wetland identified on right abutment just downstream of planned dam. | Mitigation may be necessary that is not currently identified. Source of seepage water feeding area needs to be identified. | M | M | 12 | Geotechnical and Geologic Investigations | Identify the source of the seepage water and determine if dam foundation construction will reduce or dry up the source. Mitigation design may also be needed if the site will be impacted. |  |  | L | L | 4 | 8
70 | HC | Permitting | Holthouse Reservoir | Dam construction can impact alkaline wetland identified on right abutment just downstream of planned dam. | Mitigation may be necessary that is not currently identified. Source of seepage water feeding area needs to be identified. | M | M | 12 | Geotechnical and Geologic Investigations | Identify the source of the seepage water and determine if dam foundation construction will reduce or dry up the source. Mitigation design may also be needed if the site will be impacted. |  |  | L | L | 4 | 8
71 | HR | Operation | O&M | Catastrophic Flood events affecting facilities other than the dams and reservoir. (Dams, reservoir, and associated facilities assumed covered by Probable Maximum Flood requirements of DSOD and FERC.) | Impact to operation and maintenance activities, loss of access to some facilities, damage/loss of access roads, damage to some facilities and facilities. | M | M | 12 | Engineering Planning | Identify an appropriate design basis rainfall or flood event to provide a risk-tolerable level of protection for all facilities considered critical for continued operation. |  |  | L | L | 4 | 8
71 | HC | Operation | O&M | Catastrophic Flood events affecting facilities other than the dams and reservoir. (Dams, reservoir, and associated facilities assumed covered by Probable Maximum Flood requirements of DSOD and FERC.) | Impact to operation and maintenance activities, loss of access to some facilities, damage/loss of access roads, damage to some facilities and facilities. | M | M | 12 | Engineering Planning | Identify an appropriate design basis rainfall or flood event to provide a risk-tolerable level of protection for all facilities considered critical for continued operation. |  |  | L | L | 4 | 8
72 | HR | Cost Schedule | General | Unsatisfactory performance by design consultant(s). | Permitting and construction delays, cost impacts. | L | H | 16 | Contracting, Contract Management | Proper selection of consultants with current, relevant, proven, experience; frequent reporting of progress; periodic performance reviews; periodic quality reviews. |  |  | L | L | 4 | 12
72 | HC | Cost Schedule | General | Unsatisfactory performance by design consultant(s). | Permitting and construction delays, cost impacts. | L | H | 16 | Contracting, Contract Management | Proper selection of consultants with current, relevant, proven, experience; frequent reporting of progress; periodic performance reviews; periodic quality reviews. |  |  | L | L | 4 | 12
73 | HR | Schedule Quality Cost Claims | Construction - General | Unsatisfactory performance by construction management consultant(s) | Loss of control of construction contractors, schedule delays, quality issues, increased claim potential, risks to reimbursements from bond money and other funding sources. | L | H | 16 | Contracting | Pre-qualification shed portion of liability to consultant(s). |  |  | VL | H | 8 | 8
73 | HC | Schedule Quality Cost Claims | Construction - General | Unsatisfactory performance by construction management consultant(s) | Loss of control of construction contractors, schedule delays, quality issues, increased claim potential, risks to reimbursements from bond money and other funding sources. | L | H | 16 | Contracting | Pre-qualification, shed portion of liability to consultant(s). |  |  | VL | H | 8 | 8
74 | HR | Schedule Quality | Construction - General | Construction Defects | Schedule delays for repairs, risks to reimbursements from bond money and other funding sources because of quality concerns and nonconformance to plans and specifications. | L | H | 16 | CM | Implement QC inspection and testing program, implement FERC QCIP for all dams. |  |  | L | M | 8 | 8
74 | HC | Schedule Quality | Construction - General | Construction Defects | Schedule delays for repairs, risks to reimbursements from bond money and other funding sources because of quality concerns and nonconformance to plans and specifications. | L | H | 16 | CM | Implement QC inspection and testing program, implement FERC QCIP for all dams. |  |  | L | M | 8 | 8
75 | HR | Safety Resource Protection Project Operation Permitting | Sites Reservoir | Presence of alkaline springs identified at north end of reservoir area. | Contamination of reservoir, loss of water into springs. | L | H | 16 | Geotechnical Investigations | Evaluate, map, and possibly drill in vicinity of springs to determine extent of problem and methods to plug. |  |  | L | L | 4 | 12
75 | HC | Safety Resource Protection Project Operation Permitting | Sites Reservoir | Presence of alkaline springs identified at north end of reservoir area. | Contamination of reservoir, loss of water into springs. | L | H | 16 | Geotechnical Investigations | Evaluate, map, and possibly drill in vicinity of springs to determine extent of problem and methods to plug. |  |  | L | L | 4 | 12
76 | HR | Operation Safety | Sites Reservoir | Reservoir rim instability due to large reservoir fluctuations. | Maintenance issue for slope slumping. | M | L | 6 | Geotechnical and Geologic Investigations | Geotechnical and geologic review and mapping of reservoir rims. |  |  | L | L | 4 | 2
76 | HC | Operation Safety | Sites Reservoir | Reservoir rim instability due to large reservoir fluctuations. | Maintenance issue for slope slumping. | M | L | 6 | Geotechnical and Geologic Investigations | Geotechnical and geologic review and mapping of reservoir rims. |  |  | L | L | 4 | 2
77 | HR | Permitting | Permitting | Agency restrictions on air quality impacts due to heavy construction equipment | Cost impact | L | L | 4 |  | Clarify agency requirements for EIR/EIS documents and include requirements in construction contract documents. |  |  | L | L | 4 | 0
77 | HC | Permitting | Permitting | Agency restrictions on air quality impacts due to heavy construction equipment | Cost impact | L | L | 4 |  | Clarify agency requirements for EIR/EIS documents and include requirements in construction contract documents. |  |  | L | L | 4 | 0
100 | HR | Cost Schedule | Sites Reservoir | Poor fit-up between tunnels to inlets and outlets | Rework and overall delays to project | M | H | 24 | Engineering | Design: Provide tolerances for connections, inclusion of fit up pieces; prepare sequencing to optimize connections. Specify detailed submittal plans for connections during construction. Ensure good coordination between HR and HC teams. |  |  | L | L | 4 | 20
101 | HR | Environmental | Roads | Realignment of roadways | Impact new resource requiring new technical study and delay in construction. | L | L | 4 | Engineering | Align road to balance cost of excavation and environmental impacts. | Project Engineer |  | VL | VL | 1 | 3
102 | HR | Environmental | Roads | Cultural Resources | Adverse effect of historic or archaeological resources determined during construction requiring studies/tribal coordination/mitigation. | L | L | 4 | Permitting | Address mitigation needs during construction. | Construction Manager |  | L | L | 4 | 0
103 | HR | Right of Way | Real Estate | Noncooperative Property Owner | Property owner refuses to sell requiring condemnation | M | L | 6 | Acquisition | Early identifiication of ROW need and coordination with property owner. | ROW Agent |  | L | VL | 2 | 4
104 | HR | Utilities | Roads | Utility relocations. | Utility relocations not performed in time resulting in delays and claims. | M | L | 6 | Coordination | Early and regular coordination with utility company for timely relocation design and relocation. | Project Engineer/ Construction Manager |  | L | L | 4 | 2
105 | HR | Survey | General | Lack of topo survey | Lack of access to certain parcels to obtain topo could result in inacurate spot location design and quantities resulting in need to redesign later on and change orders claims during construction with redesign and change in quantities. | M | M | 12 | Coordination | Early and regular coordination with property owners to obtain trust and access to properties. | ROW Agent |  | L | L | 4 | 8
106 | HR | Construction | General | Varying delivery methods between DBB, DB, and CMGC. | Varying delivery methods could missalign the schedule of various project components, causing redesigns and or delays during construction. | M | H | 24 | Program Management | If varying alternative deliveries are implemented, emphasize need of Program Management to regularly coordinate across project components to avoid disconnects and project development and delivery impacts. | Program Manager |  | L | L | 4 | 20
107 | HR | Construction | Construction - General | Inadequate water source for construction. | Lack of planning for adequate water source for construction could result in construction delays and change orders. | L | M | 8 | Project Management | Evaluate demand and sources to confirm adequacey of water supply. | Project Manager |  | VL | VL | 1 | 7
108 | HR | Geotechnical | Bridge | Vulnerable valley floor subsurface strata requiring full-length bridge causway across reservoir. | Full-length bridge causeway would add $100M to the cost of the project. | M | H | 24 | Geotechnical Investigation | Complete subsurface investigations to inform recommendations for causeway design. | Project Manager |  | L | M | 8 | 16
109 | HR | Geotechnical | Roads | Lack of subsurface investigation | Lack of subsurface investigation during preliminary design could result in redesign, delays and construction change orders when final investigations are performed and possibly reveal unexpected results. | M | H | 24 | Geotechnical Investigation | Complete subsurface investigations during preliminary design to adequately inform design. | Project Manager |  | L | M | 8 | 16
110 | HR | Cost | Cost | Cost escallation due to size of project and limited contractors to perform the work. | Limited contractors to perform the work and the size of project could strain available resources to efficiently construct the project which could measurably increase project cost. | M | M | 12 | Program Management | Adequately plan for construction to attract appropriate numbers of contractors. Use contractor outreach. Possibly stagger components of the project which could extend overall project duration but control project cost. | Program Manager |  | L | M | 8 | 4
111 | HR | Cost | Cost | Competing large scale projects in the region such as Sites Reservoir and High Speed Train could strain available qualified contractors. | Lack of available qualified contractors could result in escalated cost to construct and lack of quality in the project. | M | M | 12 | Program Management | Consider the effects of multiple large scale projects on the market and plan accordingly - schedule and budget impacts. | Program Manager |  | L | M | 8 | 4
112 | HR | Cost | Cost | Passing of the Infrastructure Bill creating a flood of work in the construction industry. | Lack of available qualified contractors and high demand on materials and equipment could result in escalated cost to construct the project. | M | M | 12 | Program Management | Consider the effects of a magnitue of projects flooding the industry and plan accordingly - schedule and budget impacts. | Program Manager |  | L | M | 8 | 4
201 (Jacobs-Vanderweil) | HC | Cost Schedule | Overhead Transmission Lines | Delay in procuring large equipment such as poles, structures and conductors | Delays in schedule and added cost | M | M | 12 | Evaluate Alternatives | Good early definition of all project components and footprints. |  |  | M | M | 12 | 0
202 (Jacobs-Vanderweil) | HC | Cost Schedule | Overhead Transmission Lines | The transmission lines will need to cross the WAPA, TANC, and PGE existing lines, approval delays may impact installation | Delays in schedule and added cost | M | M | 12 | Planning Contracting | Close coordination with transmission operator in pre-design. |  |  | M | M | 12 | 0
203 (Jacobs-Vanderweil) | HC | Cost Schedule | Overhead Transmission Lines | The transmission lines will need to interconnect with PGE existing lines, interconnection approval delays may impact schedule and may include unknown requirements | Delays in schedule and added cost | M | H | 24 | Planning Engineering | Close coordination with transmission operator in pre-design. |  |  | M | M | 12 | 12
204 (Jacobs-Vanderweil) | HC | Cost Schedule | Overhead Transmission Lines | Interconnection with PG&E, as well as possible rework of some main line WAPA and PG&E structures, will require line outages that may be limited to certain months of the year. | Delays in schedule and added cost | M | H | 24 | Planning Engineering | Close coordination with transmission operator in pre-design. |  |  | M | M | 12 | 12
205 (Jacobs-Vanderweil) | HC | Cost Schedule | Electrical Substation | Delay in procuring large equipment such as transformers or breakers | Delays in schedule and added cost | M | M | 12 | Planning Engineering | Good early definition of all project components and footprints.
206 (Jacobs-Vanderweil) | HC | Cost Schedule | Electrical Substation | The substations will need approvals for Arrangement and Protective Relay Requirements to ensure that there are safe disconnect facilities for fault detection at the generators and faults on the PG&E Power System. Design approval delays from PGE, may impact the schedule. | Delays in schedule and added cost | M | H | 24 | Planning Engineering | Close coordination with transmission operator in pre-design.
207 (Jacobs-Vanderweil) | HC | Cost Schedule | Electrical Substation | Delays in procuring control & instrumentation cable for transformers or breakers and relay protection devices. | Delays in schedule and added cost | M | H | 24 | Planning Engineering | Good early definition of all project components and footprints.
208 (Jacobs-ZGlobal) | HC | Schedule | Pumping Generating Plants | Potential delays in CAISO study process due to recent "Super Cluster" Issue and canceled 2022 submission window and risk of 2024 being canceled | Delays in study process may result in delay in finalizing Interconnection Agreement and ability to reach COD for Pumping and Generationg plants | M | H | 24 |  | Little if anything can be done with CAISO timeline. Alternaive approach is to seek interconnection with WAPA. WAPA study process is significanly less complex with much shortend timeline. |  |  | M | L | 6 | 18
209 (Jacobs-ZGlobal) | HC | Schedule | Pumping Generating Plants | Potential delays in being released for full operation due to "time to construct" durations for network upgrades | Total or partial dealy in reaching full generation and pumpting operatoins. | H | H | 32 | Planning | Execute MOU and early funding with PG&E to advance design and engineering of requred network upgrades. |  |  | H | H | 32 | 0
210 (Jacobs-ZGlobal) | HC | Cost Schedule | Pumping Generating Plants | Large Interconnection Financial Security (IFS) Posting requried due to high cluster study participation. | Large financial scuring positng due at end of Phase 1 study due to large number of projects in study. For CAISO 50% of the IFS is at risk of project is withdrawn | VH | M | 20 | Planning | Include sizable budget item for the IFS. |  |  | VH | L | 10 | 10
211 (Jacobs-Dyok) | HC | Permitting | Permitting | Delay in FERC review(s) and/or approval(s) based on recent poor performance on another project. | Schedule delays due to late receipt of license/exemption, potential contractor claims due to late receipt of design package approvals for construction. | VH | VH | 80 | FERC Consultation by Agency and Engineer | Close agency coordination, effective communication, early agency involvement in project reviews (including pre-payment of a portion of the fee to utilize their time), utilize consultants with proven experience in working with FERC on a day to day basis (office and field), and/or formally verify that project qualifies for two municaipal exemptions after EIS/CEQA document has been prepared. |  |  | M | M | 12 | 68
212 Jacobs-Dyok) | HC | Cost Schedule | Pumping Plants | Delays in procuring major mechanical and electrical equipment. | Construction delays, start up and commissioning delays. Reservoir filling delays. | M | VH | 48 | Planning Contracting | Early market analysis of shop floor availability. Possible pre-procurement of major mechanical/electrical components that are critical path items. |  |  | L | VH | 32 | 16
213 (Jacobs-Dyok) | HC | Design Cost Operation | Pumping Plants | Selection of pumping and generating unit number and size. | Not having the appropriate number and size of units can introduce extra cost, cause operation problems, and increase operational and maintenance costs. Can also limit the number of potential equipment suppliers. | H | H | 32 | Alternative Evaluation | Alternative Evaluations: Study alternative unit size combinations, costs, and operational flexibility to match pumping and generating requirements based on current modeling results. |  |  | L | L | 4 | 28
214 (Jacobs-Geosyntec) | HC | Cost | Funks Reservoir | Several hundred thousand cubic yards of sediment are planned to be removed from Funks Reservoir. These materials are intended to be reused as fill and/or for resotration of quarries or borrow areas on Site. It is unkown whether or not the sediments contain any contaminates of concern (COCs) that may preclude their use as fill or restoration materials on Site. If COCs are present, the sediments will need to off-hauled to an appropriate containment site. | This would increase costs. | M | M | 12 | Environmental Characterization | Sample and test material to identify character and potential for drainage and contaminants. |  |  | L | M | 8 | 4
215 (Jacobs-Geosyntec) | HC | Stakeholder Relationships Schedule | Funks Reservoir | Removal of sediment from Funks may impact operation of TCC. | Increased water quality issue for downstream deliveries and may carry sediment that deposits in TCC downstream. Could result in schedule constraints. | M | M | 12 | Design Planning | Look at ways to isolate reservoir dredging operations from the main canal flow stream - use silt curtains, levees, timing of operations (when system shutdown in winter). Early agreement with TCC on requirements/criteria. |  |  | VL | M | 4 | 8
216 (Jacobs-Geosyntec) | HC | Schedule | Funks Reservoir | Two cofferdams within the reservoir are planned to facilitate construction of the Funks PGP and the TRR pipeline alignment. These are expected to be constructed within a short annual construction window when the reservoir is low. Unknown foundation conditions beneath planned cofferdams. | If adverse condition encountered during construction, these could significantly impact schedule - likely a 1-2 year delay of all in-reservoir work (e.g., pipelines). | M | H | 24 | Geotechnical Investigation Design Planning | Drilling, sampling, testing, evaluation, and design to develop an appropriate design and construciton plan that is schedule resilient. |  |  | L | L | 4 | 20
217 (Jacobs-Geosyntec) | HC | Schedule Costs | Funks Reservoir | Uncertain weather or existing TCCA facility operations impacts could shorten the annual construction window or result in difficult working conditions for the cofferdams and in-reservoir excavation when the reservoir is low. | Delays in schedule and increases in cost. | M | H | 24 | Geotechnical Investigation Planning | Develop a construction plan that is schedule resilient with information on the materials. |  |  | L | M | 8 | 16
218 (Jacobs-Geosyntec) | HC | Schedule Cost Construction | TRR Reservoir (East) | Groundwater may be higher than anticipated. | May impact schedule and cost during construction. | M | L | 6 | Geotechnical Investigation | Drilling and test pits, piezometers. |  |  | L | L | 4 | 2
219 (Jacobs-Geosyntec) | HC | Permitting Cost Real Estate Schedule | TRR Reservoir (East) | Funks Creek capacity to handle emergency spills | Environmental and DSOD permitting challenges. Additional real estate impacts not yet accounted for. Higher costs. Downstream and immediately upstream stakeholder concerns about induced flooding and bank erosion. | VH | VH | 80 | Design Planning | Attempt to reconfigure design or reduce the required release criteria to bring down the associated risks. |  |  | VH | H | 40 | 40
220 (Jacobs-Geosyntec) | HC | Real Estate Cost | TRR Reservoir (East) | Challlenge in getting heavy equipment in place on GCID canal to construct access bridge as designed | Additional real estate temporary easement and/or more expensive construction techniques. | M | M | 12 | Design Planning | Optimize bridge and/or abutment design. |  |  | L | M | 8 | 4
221 (Jacobs-Geosyntec) | HC | Real Estate Cost Schedule | TRR Reservoir (East) | Reservoir requires obtaining multiple lands from owners including multiple orchards and different orchard owners. | Unwilling seller could delay project and add cost | VH | H | 40 | Real Estate | To be addressed by Sites/Real Estate
222 (Jacobs-Geosyntec) | HC | Permitting Schedule Cost | TRR Reservoir (East) | Delay in DSOD review(s) and/or approval(s) | Schedule delays, potential contractor claims. | M | M | 12 | DSOD Consultation by Agency and Engineer Design | Close agency coordination and design conservatism. Cost of construction would increase due to design conservatism. |  |  | L | M | 8 | 4
223 (Jacobs-Geosyntec) | HC | Real Estate Schedule Cost | TRR Reservoir (East) | Induced settlement of exisitng facilities. | Adjacent stakeholder concerns, schedule delays, and cost insreases. | H | M | 16 | Design Planning | Conservatism in design. Cost of construction would increase. |  |  | L | M | 8 | 8
224 (Jacobs-Geosyntec) | HC | Cost | TRR Reservoir (West) | Construction requires significant cut which generates excess material for disposal | May generate excess cost to haul away in case cuts/fills for project not balanced. | H | M | 16 | Design Planning | Look for opportunities to use excess cut for embankments, dam construction, roads; integration among consultant teams. |  |  | VL | VL | 1 | 15
225 (Jacobs-Geosyntec) | HC | Real Estate Cost Schedule | TRR Reservoir (West) | Reservoir requires obtaining multiple lands from owners including one orchard. | Unwilling seller could delay project and add cost | H | M | 16 | Real Estate | To be addressed by Sites/Real Estate
226 (Jacobs-Geosyntec) | HC | Permitting Schedule | TRR Reservoir (West) | Current configuration requires PG&E approval to construct tunnel beneath underground utility corridor. Maybe difficult to gain concurrence. | Schedule delays due to obtaining permits. | H | M | 16 | Planning | Negotiate with GCID to reduce required storage capacity to reconfigure reservoir east of the PG&E corridor and avoid the need for the tunnel. Discuss with PG&E early in preliminary design |  |  | L | VL | 2 | 14
227 (Jacobs-Geosyntec) | HC | Schedule Cost | TRR Reservoir (West) | Due to lack of subsurface information, the slopes for the TRR West reservoir may be optimistically designed (too steep). | Expansion of footprint due to lack of subsurface information. Schedule delays and costs. | M | VH | 48 | Geotechnical Investigation Design | Drilling, sampling, testing, evaluation, and design. |  |  | L | L | 4 | 44
228 (Jacobs-Geosyntec) | HC | Schedule Cost | TRR Reservoir (West) | Foundation geotechnical conditions along the geologic contact of the southeastern margin of the reservoir could be worse than anticpated. | May increase cost and delay schedule if mitigation is required | M | H | 24 | Geotechnical Investigation Design | Drilling, sampling, testing, evaluation, and design. |  |  | L | M | 8 | 16
229 (Jacobs-Geosyntec) | HC | Permitting Schedule Cost | TRR Reservoir (West) | Delay in DSOD review(s) and/or approval(s) | Schedule delays, potential contractor claims. | M | M | 12 | DSOD Consultation by Agency and Engineer Design | Determine upfront of TRR West is a jurisdictional dam with DSOD. Close agency coordination and design conservatism. Cost of construction would increase due to design conservatism. |  |  | L | M | 8 | 4
230 (Jacobs) | HC | Permitting Schedule Cost | CBD | Landowners upstream/downstream of Project discharge point on CBD do not want Project Flows in CBD during certain critical months | Cost and Schedule delays and additional permitting. | M | M | 12 | Hydraulic Modeling, Engineer Design, Real Estate | Contact and work with affected landowners early. Coordinate and come to agreement with RD108 an DWR on KLOG and CBD Operations. |  |  | M | M | 12 | 0
231 (Jacobs) | HC | Permitting Schedule Cost | GCID Fish Screen - Diverson at Hamilton City | Fish Screen requires substantial retrofit to divert waters during winter | Cost and Schedule delays and additional permitting. | M | M | 12 | Hydraulic Modeling, Engineer Design | Work with GCiD during winter 2021/2022 to better understand potential impacts to existing fish screen facility |  |  | M | M | 12 | 0
Note on K95: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is a copy from the cell above - suggest deleting and adding something similar to what I added
Note on C155: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is not a Category and probably should be

## HR General
Risk ID No. | HR or HC | Risk Category | Risk Location | What is the Problem or Issue? | Description of Consequences What Could go Wrong, How? | Unmitigated Rating |  |  | Mitigation Techniques |  |  |  | Mitigated Rating |  |  | Risk Rating Buy Down
|  |  |  | Risk Description | Consequences | Likelihood Rating Probability of Deviation from Expectation | Consequence Rating Severity of Impact on Project Outcomes | Unmitigated Risk Factor | Recommended Mitigation(s) for Reducing or "Buying Down" the Risk |  |  |  | Likelihood | Consequence | Mitigated Risk Factor | Risk Factor Buy Down from Mitigation
[9 empty] | Type | Scope | Responsible | Cost
1 | HR | Permitting | Permitting | Delay in FERC review(s) and/or approval(s) based on recent poor performance on another project. | Schedule delays due to late receipt of license, potential contractor claims due to late receipt of design package approvals for construction. | VH | VH | 80 | FERC Consultation by Agency and Engineer | Close agency coordination, effective communication, early agency involvement in project reviews (including pre-payment of a portion of the fee to utilize their time), utilize consultants with proven experience in working with FERC on a day to day basis (office and field), and/or defer FERC licensing and installation of hydroelectric generating capability. |  |  | M | M | 12 | 68
2 | HR | Permitting | Permitting | The conditions of the joint Federally-listed and State-listed species (Delta Smelt, salmonids, sturgeon, and Killer Whale) and the State-listed Long-fin Smelt are declining. | Delays in schedule, reduced ability to fill the reservoir (reduced deliveries), and increased costs. | VH | VH | 80 |  | Cannot depend upon current biological opinions issued to DWR and Reclamation. This project will require separate Federal biological opinions from U.S. Fish and Wildlife Service and National Marine Fisheries Service, and take authorization from California Department of Fish and Wildlife. Preparation of an adequate biological assessment and negotiation of the biological opinions and take authorization could take time, and will probably result in restrictions of construction boundaries, construction methods, construction time periods, and additional environmental protections during construction. The biological opinions also could result in changes to the design of facilities to minimize light, glare, noise, and vibrations (including items like noise from fans in pump stations). The biological opinions and take authorizations also could result in currently not-defined limitations on diversion volumes and rates and timing of diversions. |  |  | M | M | 12 | 68
3 | HR | Permitting | Permitting | Project will require a new water right from the SWRCB | It is anticipated that the application for the permit will result in protests by other legal users of water and concerned groups for the biological resources in the Sacramento River and the Delta. The hearings could require up to a year to allow for testimony from the applicant and protesters. The final water right permit could result in currently not-defined limitations on diversion volumes and rates and timing of diversions. | VH | VH | 80 | Water Rights | Requires significant upfront investment in legal and technical support and planning. |  |  | M | M | 12 | 68
4 | HR | Cost Schedule Permitting | Borrow Areas | Large haul distance to sand and gravel pits currently identified for concrete aggregate and dam filter and drain material (up to 35 miles from site). Existing quarries may not have the capacity to supply the materials in the quantity and timeframe for the project. | Increased cost to project, increased environmental impact and mitigation requirements. | VH | VH | 80 | Geotechnical Investigations, Estimating | Investigate current proposed source and other suitable sources of sand and gravel in the project region on both east and west sides of the reservoir to reduce reliance on commercial sources. |  |  | M | M | 12 | 68
5 | HR | Design Safety Cost | Pumping Plants | Suitability of pump station foundations and foundation excavations | Unsuitable foundation conditions, possible need for foundation piling at TRR and Sacramento River. | VH | VH | 80 | Geotechnical Investigations | Drilling, mapping, seismic refraction surveys, laboratory investigations |  | 125000 | L | L | 4 | 76
6 | HR |  | System Operations | Significantly reduced ability to divert water from the Sacramento River | Inability to divert water from the Sacramento River to fill the reservoir | VH | VH | 80 | Permits Operations | Develop acceptable diversion strategy or identify alternative water sources |  | 2000000 | H | M | 16 | 64
7 | HR | Planning Cost Impact identification | General | Currently, only undocumented, localized topographic mapping is available from previous studies to support design and construction planning. Available mapping is old. | Heightened risk of inaccuracy in laying out project facilities and estimating quantities; heightened risk of impacting existing features, facilities, and utilities not currently identified on available mapping; heightened risk of missing potential environmental impacts. | H | VH | 64 | Topographic Mapping | Topographic Mapping: Complete topographic mapping of project area from ground-controlled aerial photography. New aerial photography will also benefit the project for planning purposes and preparation of exhibits and plans. |  |  | L | L | 4 | 60
8 | HR | Financial Viability | General | Insufficient stakeholder participation to fund the project | Termination of project, loss of expended funds. | H | VH | 64 | Outreach | Investor outreach workshops, high quality WSIP application, support federal feasibility study and federal funding, political outreach. |  |  | M | H | 24 | 40
9 | HR | Permitting Cost Schedule | Permitting | Unidentified human remains associated with native American burials outside official cemeteries. | Permitting and construction delays | H | VH | 64 | Archaeologic Evaluation | Execute field surveys as soon as possible to identify risk and remediation cost. |  |  | M | L | 6 | 58
10 | HR | Cost Schedule | Sites Reservoir | South bridge abutment and foundation conditions are unknown | Unreliable design, increased cost, delay to schedule as bridge is constructed early. | VH | VH | 80 | Geotechnical Investigations | Drilling program, laboratory testing |  |  | L | L | 4 | 76
11 | HR | Safety Schedule Cost | Main Dams | Foundation conditions need to be better defined at both dam sites. | Construction delays, additional cost for increased excavation and rock stabilization, additional costs for foundation preparation and grouting. | H | VH | 64 | Geotechnical Investigation | Additional site investigation (drilling water pressure testing, seismic refraction). |  |  | L | M | 8 | 56
12 | HR | Cost Schedule | Main Dams | Insufficient information to plan and cost foundation grouting. |  | H | VH | 64 | Geotechnical Investigation | Water pressure testing, test grouting program. |  |  | M | M | 12 | 52
13 | HR | Cost Schedule | Main Dams | Insufficient information available to evaluate dam alternative that could be better. | Higher cost, longer schedule for construction. | H | VH | 64 | Alternative Evaluations | Comprehensive evaluation of RCC and concrete-faced rockfill dam alternatives, ie., geotechnical evaluation of required material sources and properties and suitable foundation conditions. |  |  | L | L | 4 | 60
14 | HR | Cost Schedule | Saddle Dams | Insufficient information to plan and cost foundation grouting. |  | H | VH | 64 | Geotechnical Investigation | Water pressure testing, test grouting program. |  |  | M | M | 12 | 52
15 | HR | Safety Schedule Cost | Saddle Dams | Foundation conditions need to be better defined at both dam sites. | Construction delays, additional cost for increased excavation and rock stabilization, additional costs for foundation preparation and grouting. | H | VH | 64 | Geotechnical Investigation | Additional site investigation (drilling water pressure testing, seismic refraction). |  |  | L | M | 8 | 56
16 | HR | Safety Engineering permitting | Holthouse Reservoir | Spillway adequacy to handle emergency releases. | Downstream channel impacts need to be addressed. | H | VH | 64 | Engineering Environmental Assessments | Determine design flow assuming split in flows between Golden Gate Dam and Sites Dam diversion tunnel. Determine impacts to Funks Creek and public and private facilities downstream. |  |  | L | M | 8 | 56
17 | HR | Coordination Engineering | Holthouse Reservoir | Several WAPA towers exist in the planned Holthouse reservoir expansion area. | Tower Relocation for new Reservoir may be needed. WAPA expressing concern. | VH | H | 40 | Alternative Investigations | Conduct alternative evaluation to relocate the two lines in question. Early and ongoing coordination with WAPA to resolve the conflict in line location. |  |  | L | L | 4 | 36
18 | HR | Design Safety Cost | Pumping Plants | Suitability of fish screen structure and cofferdam in Sacramento River | Unsuitable foundation conditions, lack of data to design in-river cofferdam system and foundation piles for fish screen structure. | H | VH | 64 | Geotechnical Investigations | Geotechnical Investigations: Drilling, mapping, laboratory investigations |  |  | L | L | 4 | 60
19 | HR | Permitting Design | General | Site seismicity higher than previously estimated, update needed. | Current site seismicity data dating back to 2003 may be inadequate for project design and permitting dams and other major structures through state and federal agencies. | H | H | 32 | Engineering | Conduct Site Seismicity Evaluation. Prepare updated site seismicity evaluation that will meet current State (DSOD) and Federal (FERC) standards. |  |  | L | L | 4 | 28
20 | HR | Permitting Cost Schedule | Permitting | Environmental impact of access road to east end of bridge may require deep cut through east reservoir ridge. | Unanticipated visual and environmental impacts | H | H | 32 | Engineering Environmental Reviews | Evaluate extent of cutting; evaluate potential impacts and mitigations, evaluate tunnel through ridge option. |  |  | L | M | 8 | 24
21 | HR | Cost | Construction - General | Significantly higher construction bids than estimated. | Impacts to cash flow, cash reserves, financing costs during construction, cost of water, financial viability of project. | H | H | 32 | Market Analysis, Contractor Outreach | Perform a market analysis as part of each cost estimate update to project market conditions and competition with other projects at the anticipated bid time. Perform market analysis of critical materials (steel, concrete, fabricated equipment, etc.) as part of each estimate. Package work with consideration to cost to avoid limiting bidder pool due to bonding limitations. Perform cost trend analysis along with design development to inform Authority of cost changes as we proceed. |  |  | L | M | 8 | 24
22 | HR | Cost Schedule Permitting | Borrow Areas | Lack of core and shell borrow material in vicinity of dam. No investigations available in the vicinity of the dam. | Increased haul distances and costs to construct dam. | H | H | 32 | Geotechnical Investigations | Conduct site investigation between Holthouse Dam and existing Funks Dam to verify availability of construction material to supplement material from the removal of Funks Dam. (Investigation currently in planning stage by Reclamation.) |  |  | L | L | 4 | 28
23 | HR | Safety Project Operation | Sites Reservoir | Stability of all downstream outlet tunnel portals | Impact to pump station operation Construction: worker safety; Long-term: can bury infrastructure at toe of portal | M | H | 24 | Geotechnical Investigation | Drilling program and laboratory testing Design: Include slope reinforcement and drainage. Include contract provisions for monitoring and making adjustments during construction. |  |  | L | L | 4 | 20
24 | HR | Cost Schedule | Main Dams | Stability of conveyance channel slopes to Holthouse Reservoir. | Slope instability requiring re-work, increased excavation quantities, unanticipated lining and stabilization for slope. | H | H | 32 | Geotechnical Investigation | Additional site investigation (drilling, seismic refraction, geo mapping). |  |  | M | L | 6 | 26
25 | HR | Safety Schedule Cost | Saddle Dams | Depth to sound rock foundation for core trench not sufficiently documented for all dams, scope of previous investigations significantly less for saddle dams than for main dams, addition data needed to design underseepage control using grout cutoff or slurry wall. | Risk to design, potential construction delays, additional construction cost, additional borrow from pits and quarries. | H | H | 32 | Geotechnical Investigations | Additional site investigation (drilling water pressure testing, seismic refraction). |  |  | L | M | 8 | 24
26 | HR | Safety Schedule Cost Permitting | Holthouse Reservoir | Foundation conditions need to be better defined at dam site. No data currently available to support design or permitting for DSOD or FERC. No data available on borrow material source for core. | Permitting delays, design risks, construction delays, additional cost for increased excavation, foundation preparation, and foundation grouting. | H | H | 32 | Geotechnical Investigations | Drilling, piezometers, trenches in borrow area behind proposed dam. |  |  | M | L | 6 | 26
27 | HR | Schedule Cost Permitting | Holthouse Reservoir | Difficulties in handling sediment in Funks. | No data available about composition of sediment that has accumulated in Funks Reservoir, no data on volume of sediment that has accumulated. | H | H | 32 | Geotechnical Investigations, Bathymetry | Perform bathymetric survey of top of sediment to compare with pre-Funks topography to estimate volume; sample and test material to identify character and potential for drainage. |  |  | L | L | 4 | 28
28 | HR | Cost Schedule | Delevan/TRR Pipeline | High groundwater, significant construction dewatering and pipe flotation. | Cost and schedule impact, redesign, claims | H | H | 32 | Geotechnical Investigations | Drilling, piezometers, and monitoring data evaluate tunnel alternative. |  |  | L | M | 8 | 24
29 | HR | Design Cost Schedule | Delevan/TRR Pipeline | Unanticipated utilities and drainage features | Potential schedule and cost impacts, claims | H | H | 32 | Mapping and Ground Surveys | Detailed utility surveys, potholing, topographic mapping, evaluate tunnel alternative. |  |  | L | L | 4 | 28
30 | HR | Permitting | Delevan/TRR Pipeline | Inability to open cut through Colusa Basin Drain and adjacent to wildlife preserves due to environmental concerns and mitigation costs. | Potential schedule and cost impacts. | H | H | 32 | Geotechnical Investigations, Alternative Evaluation | Evaluate feasibility of soft ground tunneling in restrictive areas. |  |  | L | M | 8 | 24
31 | HR | Design Cost Operation | Pumping Plants | Selection of pumping and generating unit number and size. | Not having the appropriate number and size of units can introduce extra cost, cause operation problems, and increase operational and maintenance costs. Can also limit the number of potential equipment suppliers. | H | H | 32 | Alternative Evaluation | Alternative Evaluations: Study alternative unit size combinations, costs, and operational flexibility to match pumping and generating requirements based on current modeling results. |  |  | L | L | 4 | 28
32 | HR | Schedule Cost | Real Estate | Property acquisition delayed | Start of construction delayed. Jeopardizes on-schedule completion. | H | H | 32 | Planning | Develop Real Estate Acquisition Plan in Phase 2 and implement acquisition and Communication Plan at the beginning of Phase 3 and provide relocation assistance |  | 10000000 | M | M | 12 | 20
33 | HR | Permitting | Permitting | Current reservoir design assumes full storage of the Probable Maximum Flood with no emergency spillway other than minimal pipe (signal spillway) at one saddle dam. | DSOD expressed concern with no emergency spillway. | VH | M | 20 | DSOD/FERC Consultation by Agency and Engineer | Further consultation with DSOD to clarify concern; clarify minimum design criteria required by DSOD specific to the project; reflect criteria in reservoir design criteria. |  |  | L | L | 4 | 16
34 | HR | Permitting | Permitting | Delay in DSOD review(s) and/or approval(s) | Schedule delays, potential contractor claims. | M | VH | 48 | DSOD Consultation by Agency and Engineer | Close agency coordination, effective communication, early agency involvement in the project (including pre-payment of a portion of the fee to utilize their time), utilize consultants with proven experience in working with DSOD on a day to day basis (office and field). |  |  | M | M | 12 | 36
35 | HR | Cost Schedule Claims | Construction - General | Interference among various contractors working on site due to poor packaging of project work. | Work activity interference, lack of access to work areas by multiple contractors simultaneously, restricted availability of materials (aggregate, cement, steel, power). Can lead to schedule delays and claims. | M | VH | 48 | Bidding Strategy | Develop a bidding strategy to package and schedule the work to minimize work interfaces between packages. Evaluate and include coordination requirements in contract documents, including critical milestone dates to vacate work areas or complete components of the work. Develop/implement a management plan that includes coordination. |  |  | L | M | 8 | 40
36 | HR | Schedule Cost | Construction - General | Delay(s) in mechanical equipment fabrication, delivery, and quality control testing | Installation and construction completion delays, startup and commissioning delays. | M | VH | 48 | Planning Contracting | Early market analysis of shop floor availability. Possible pre-procurement of major mechanical/electrical components that are critical path items. |  |  | L | VH | 32 | 16
37 | HR | Cost Schedule Permitting | Borrow Areas | Core borrow quantity available in reservoir for main dams and saddle dams. | Increased cost to project, increased environmental impact and mitigation requirements. | M | VH | 48 | Geotechnical Investigations, Estimating | Review of all available DWR data, supplemental investigations and testing as necessary. |  |  | L | L | 4 | 44
38 | HR | Cost Schedule Permitting | Borrow Areas | Lack of rockfill and riprap quantity available in reservoir ridges and other excavations for main dams, saddle dams, and roadway causeway fill prism, including impact of interbedded soft and hard rock layers. | Increased cost to project, increased environmental impact and mitigation requirements. | M | VH | 48 | Geotechnical Investigations, Estimating | Review of all available DWR data, supplemental investigations and testing as necessary. |  |  | L | L | 4 | 44
39 | HR | Safety Resource Protection Permitting | Sites Reservoir | East Rim Seepage | Loss of water resource, seeps and springs on east side, east side slope instability | M | VH | 48 | Geotechnical Investigations | Drilling program with water pressure testing to evaluate seepage potential and design mitigation measures (rim grouting) |  |  | L | L | 4 | 44
40 | HR | Safety Project Operation | Sites Reservoir | Stability of outlet works tower Intake excavation: Rock is not found where inferred from borings resulting in a requirement for more excavation | Loss of reservoir control Increase excavation and concrete costs. Delays to construction. | M | M | 12 | Evaluate Alternatives Engineering | Evaluate stability under static and seismic loading; evaluate alternatives, including sloping intake replacement. Design: Conduct a thorough geotechnical site investigation. Flexible design to accommodate rock being found at somewhat different elevations than expected. |  |  | L | VL | 2 | 10
41 | HR | Safety Schedule Constructability | Sites Reservoir | Stability of tunnel during excavation | Adverse impacts to construction cost and schedule, potential for claims. | M | VH | 48 | Geotechnical Investigations | Drilling program, engineering studies Design: Thorough geotechnical investigation, Geotechnical interpretaive report (GIR), GBR, Contingency in cost estimate; strengthened different site conditions clause; use of Dispute Resolution Board (DRB) and facilitated partnering; Add provisions for controlled blasting if material is harder than expected and for toolbox of items if additional support is needed. Construction: Qualified CM, 24/7 tunnel inspection |  |  | L | L | 4 | 44
42 | HR | Cost Schedule | Main Dams | Dam axis not in optimum location to minimize cost. | Increased construction cost, increased need for imported filter/drain aggregates, increased DSOD permitting costs. | M | VH | 48 | Geotechnical Investigation, Alternative Evaluation | Additional site investigation (drilling water pressure testing, seismic refraction), alternative location evaluations. |  |  | L | L | 4 | 44
43 | HR | Cost Schedule | Saddle Dams | Dam axis not in optimum location to minimize cost. | Increased construction cost, increased need for imported filter/drain aggregates, increased DSOD permitting costs. | M | VH | 48 | Geotechnical Investigation, Alternative Evaluation | Additional site investigation (drilling water pressure testing, seismic refraction), alternative location evaluations. |  |  | L | L | 4 | 44
44 | HR | Design Cost Schedule | TRR Reservoir | High Groundwater | Increased reservoir footprint required due to high groundwater | M | VH | 48 | Geotechnical Investigations | Drilling and test pits, piezometers. |  |  | L | L | 4 | 44
45 | HR | Design Operation | TRR Reservoir | Rapid drawdown liner failure | Operational impacts, shutdown of Reservoir/canal | M | VH | 48 | Geotechnical Investigations | Review of geotec site conditions, drilling, appropriate liner and slope design. |  |  | L | L | 4 | 44
46 | HR | Cost Schedule | Pumping Plants | Delays in procuring major mechanical and electrical equipment. | Construction delays, start up and commissioning delays. Reservoir filling delays. | M | VH | 48 | Planning Contracting | Early market analysis of shop floor availability. Possible pre-procurement of major mechanical/electrical components that are critical path items. |  |  | L | VH | 32 | 16
47 | HR | Schedule Cost | General | New stakeholders (e.g., Board, JPA staff, member agencies). | Slows forward project momentum, could impact project configuration. | M | H | 24 | Team Building | Accelerated effort to bring new players up to speed as quickly as possible, limit ability of new players by agreement to radically modify project technical and financial details. |  |  | L | L | 4 | 20
48 | HR | Permitting Schedule Cost | Permitting | New endangered species identified. | Schedule delays, added cost, additional environmental studies, amendments required to EIR/EIS documents, unanticipated additional mitigation costs. | M | H | 24 | Agency Action | Early acquisition of easements and property with on-going land management. |  |  | L | M | 8 | 16
49 | HR | Cost Schedule Claims | Construction - General | Excessive flooding occurs during construction. | Loss of complete work, schedule delays due to the event and to make repairs. | M | H | 24 | Planning Engineering | Develop a bidding strategy to package and schedule the work to minimize work interfaces between packages. Evaluate and include coordination requirements in contract documents, including critical milestone dates to vacate work areas or complete components of the work. Develop/implement a management plan that includes coordination. Planning: Clearly define design floods during construction and model floodplains. Design: Confirm proper flood protection measures (such as cofferdams and diversions) are in place during construction. |  |  | L | M | 8 | 16
50 | HR | Safety | Construction - General | Serious accident(s) during construction. |  | M | H | 24 | Engineering Contracting | Implement a safety-by-design approach to comply with applicable industrial safety standards and minimize creating unsafe conditions. Require contractors to comply with all applicable federal and state safety requirements and have detailed job safety plans and work activity risk assessments. Provide a qualified safety officer on the construction management team to monitor performance, and enforce safety requirements if needed. |  |  | L | M | 8 | 16
51 | HR | Cost Schedule | Construction - General | Disruption in availability of materials (cement, steel, rebar, etc.). | Reduced progress, increased cost, higher bids if disruption occurs at bid time. | M | H | 24 | Engineering Contracting | Conduct market analysis prior to bidding. If disruption is possible, consider including provisions in contract for contractor(s) to pre-procure sufficient material at NTP and cover storage costs to avoid shortage delays. |  |  | L | M | 8 | 16
52 | HR | Cost | Construction - General | Unexpected escalation/run-up in price of construction materials and labor | Cost increases. | M | H | 24 | Contracting | Lock in price at award of contract, transfer risk to contractor. |  |  | L | L | 4 | 20
53 | HR | Schedule Cost Quality | Construction - General | Unsatisfactory performance by contractor(s) | Schedule delays, poor work quality. | M | H | 24 | Planning Contracting | Prequalify contractors for major packages. Performance goals and milestone dates in contract with liquidated damages. |  |  | L | H | 16 | 8
54 | HR | Cost | Construction - General | Availability of construction materials | The availability of materials could be impacted by WSIP awards to multiple projects at once, creating competition for materials | H | M | 16 | Planning | Keep track of potential concurrent multiple projects to adjust project compenent delivery time frames. Risk is project delays.
55 | HR | Safety Schedule Cost | Main Dams | Rock toppling issues in core trench excavations on slopes due to adverse rock bedding. | Construction delays, addition cost for increased excavation and rock stabilization. | M | H | 24 | Geotechnical Investigation | Additional drilling and geologic mapping of rock outcrops. |  |  | M | L | 6 | 18
56 | HR | Cost Schedule | Delevan/TRR Pipeline | Encountering unsuitable foundation soils, particularly in CBD area. | Potential schedule and cost impacts, claims | H | M | 16 | Geotechnical Investigations | Drilling, sampling, laboratory testing, evaluate tunnel alternative. |  |  | L | L | 4 | 12
57 | HR | Cost Schedule | Delevan/TRR Pipeline | Encountering hard foundations (rock) west of GC Canal. | Potential schedule and cost impacts, claims | H | M | 16 | Geotechnical Investigations | Drilling, seismic refraction surveys, evaluate tunnel alternative. |  |  | L | L | 4 | 12
58 | HR | Cost Schedule | TRR Reservoir | Pump station foundation | Unsuitable foundation conditions | M | H | 24 | Geotechnical Investigations | Drilling, piezometers |  |  | L | L | 4 | 20
59 | HR | Schedule Cost | Intake | Wildlife at intake location (yellow billed cuckoo, bank swallow, and giant garter snake) | Difficulty in obtaining permits | H | M | 16 | Planning | Mitigation with compensatory acreage, pre-construction development of compensatory habitat, and reduced construction periods |  | 300000 | H | L | 8 | 8
60 | HR | Schedule | Real Estate | Failure to acquire temporary entry permits on schedule. | Delay to completion of design and potential quality impact is timely access cannot be arranged. | H | M | 16 | Planning | Develop Real Estate Communication Plan and initiate temporary entry permit process prior to or at the beginning of Phase 2 |  | 200000 | H | L | 8 | 8
61 | HR | Schedule Cost | Real Estate | Potential requirement for condemnation of property for acquisition | Legal process delays construction | M | H | 24 | Planning | Develop robust alternative analysis in the EIR/S to support condemnation |  |  | M | M | 12 | 12
62 | HR | Permitting Schedule Cost | Permitting | Rejection of mitigation package by resource agencies. | Construction start delays, over-all schedule delays, added cost. | L | VH | 32 | Agency Coordination | Close coordination with agencies in pre-design. |  |  | L | M | 8 | 24
63 | HR | Permitting Schedule Cost | Permitting | Significant design feature(s) not covered in EIR/EIS document. | Schedule delays, added cost, additional environmental studies, amendments required to EIR/EIS documents, unanticipated additional mitigation costs. | L | VH | 32 | Engineering | Good early definition of all project components and footprints. |  |  | L | L | 4 | 28
64 | HR | Schedule | Construction - General | Availability of power during construction | Construction delays, startup and testing delays, reservoir filling delays. | L | VH | 32 | Planning Coordination Engineering | Pre-planning and coordination with WAPA and PG&E to make sure power is available for construction, and that any required system upgrades are in place on schedule to support startup and testing. |  |  | L | L | 4 | 28
65 | HR | Safety Cost Permitting | Sites Reservoir | No prior consideration given to damage to Funks Creek downstream of Holthouse and Stone Corral Creek from emergency project releases. | Major erosion damage and potential damage to crops and structures, potential damage to roads and road closures. | L | VH | 32 | Engineering and Environmental Evaluation | Evaluate potential damage and identify potential mitigation measures to include in project design and in emergency response planning. |  |  | L | M | 8 | 24
66 | HR | Cost | General | Higher appraisal/acquisition cost than budgeted for. | Cost impact, impact to project financial evaluation and BC ratio. | M | M | 12 | Consultant Services | Thorough, conservative evaluation of land costs, periodically updated, using consultants/agents familiar with real estate in project region. |  |  | L | L | 4 | 8
67 | HR | Permitting Schedule | Permitting | Public concerns - Recreation / Construction (light, traffic, noise) | Permitting delays due to public comments/concerns | M | M | 12 |  | Public outreach. |  |  | L | L | 4 | 8
68 | HR | Permitting | Permitting | Agency restrictions for discharging ground/construction water onto surface water | Cost impact | M | M | 12 |  | Clarify agency requirements for EIR/EIS documents and include requirements in construction contract documents. |  |  | L | L | 4 | 8
69 | HR | Safety Resource Protection Project Operation | Sites Reservoir | High pressure water leakage out of the tunnel during operation | Impact to natural and excavated slopes from unanticipated leakage. | M | M | 12 | Geotechnical Investigations | Drilling program, Water pressure tests to evaluate tunnel lining requirements, confirm with hydrojacking tests during construction. |  |  | L | L | 4 | 8
70 | HR | Permitting | Holthouse Reservoir | Dam construction can impact alkaline wetland identified on right abutment just downstream of planned dam. | Mitigation may be necessary that is not currently identified. Source of seepage water feeding area needs to be identified. | M | M | 12 | Geotechnical and Geologic Investigations | Identify the source of the seepage water and determine if dam foundation construction will reduce or dry up the source. Mitigation design may also be needed if the site will be impacted. |  |  | L | L | 4 | 8
71 | HR | Operation | O&M | Catastrophic Flood events affecting facilities other than the dams and reservoir. (Dams, reservoir, and associated facilities assumed covered by Probable Maximum Flood requirements of DSOD and FERC.) | Impact to operation and maintenance activities, loss of access to some facilities, damage/loss of access roads, damage to some facilities and facilities. | M | M | 12 | Engineering Planning | Identify an appropriate design basis rainfall or flood event to provide a risk-tolerable level of protection for all facilities considered critical for continued operation. |  |  | L | L | 4 | 8
72 | HR | Cost Schedule | General | Unsatisfactory performance by design consultant(s). | Permitting and construction delays, cost impacts. | L | H | 16 | Contracting, Contract Management | Proper selection of consultants with current, relevant, proven, experience; frequent reporting of progress; periodic performance reviews; periodic quality reviews. |  |  | L | L | 4 | 12
73 | HR | Schedule Quality Cost Claims | Construction - General | Unsatisfactory performance by construction management consultant(s) | Loss of control of construction contractors, schedule delays, quality issues, increased claim potential, risks to reimbursements from bond money and other funding sources. | L | H | 16 | Contracting | Pre-qualification shed portion of liability to consultant(s). |  |  | VL | H | 8 | 8
74 | HR | Schedule Quality | Construction - General | Construction Defects | Schedule delays for repairs, risks to reimbursements from bond money and other funding sources because of quality concerns and nonconformance to plans and specifications. | L | H | 16 | CM | Implement QC inspection and testing program, implement FERC QCIP for all dams. |  |  | L | M | 8 | 8
75 | HR | Safety Resource Protection Project Operation Permitting | Sites Reservoir | Presence of alkaline springs identified at north end of reservoir area. | Contamination of reservoir, loss of water into springs. | L | H | 16 | Geotechnical Investigations | Evaluate, map, and possibly drill in vicinity of springs to determine extent of problem and methods to plug. |  |  | L | L | 4 | 12
76 | HR | Operation Safety | Sites Reservoir | Reservoir rim instability due to large reservoir fluctuations. | Maintenance issue for slope slumping. | M | L | 6 | Geotechnical and Geologic Investigations | Geotechnical and geologic review and mapping of reservoir rims. |  |  | L | L | 4 | 2
77 | HR | Permitting | Permitting | Agency restrictions on air quality impacts due to heavy construction equipment | Cost impact | L | L | 4 |  | Clarify agency requirements for EIR/EIS documents and include requirements in construction contract documents. |  |  | L | L | 4 | 0
100 | HR | Cost Schedule | Sites Reservoir | Poor fit-up between tunnels to inlets and outlets | Rework and overall delays to project | M | H | 24 | Engineering | Design: Provide tolerances for connections, inclusion of fit up pieces; prepare sequencing to optimize connections. Specify detailed submittal plans for connections during construction. Ensure good coordination between HR and HC teams. |  |  | L | L | 4 | 20
101 | HR | Environmental | Roads | Realignment of roadways | Impact new resource requiring new technical study and delay in construction. | L | L | 4 | Engineering | Align road to balance cost of excavation and environmental impacts. | Project Engineer |  | VL | VL | 1 | 3
102 | HR | Environmental | Roads | Cultural Resources | Adverse effect of historic or archaeological resources determined during construction requiring studies/tribal coordination/mitigation. | L | L | 4 | Permitting | Address mitigation needs during construction. | Construction Manager |  | L | L | 4 | 0
103 | HR | Right of Way | Real Estate | Noncooperative Property Owner | Property owner refuses to sell requiring condemnation | M | L | 6 | Acquisition | Early identifiication of ROW need and coordination with property owner. | ROW Agent |  | L | VL | 2 | 4
104 | HR | Utilities | Roads | Utility relocations. | Utility relocations not performed in time resulting in delays and claims. | M | L | 6 | Coordination | Early and regular coordination with utility company for timely relocation design and relocation. | Project Engineer/ Construction Manager |  | L | L | 4 | 2
105 | HR | Survey | General | Lack of topo survey | Lack of access to certain parcels to obtain topo could result in inacurate spot location design and quantities resulting in need to redesign later on and change orders claims during construction with redesign and change in quantities. | M | M | 12 | Coordination | Early and regular coordination with property owners to obtain trust and access to properties. | ROW Agent |  | L | L | 4 | 8
106 | HR | Construction | General | Varying delivery methods between DBB, DB, and CMGC. | Varying delivery methods could missalign the schedule of various project components, causing redesigns and or delays during construction. | M | H | 24 | Program Management | If varying alternative deliveries are implemented, emphasize need of Program Management to regularly coordinate across project components to avoid disconnects and project development and delivery impacts. | Program Manager |  | L | L | 4 | 20
107 | HR | Construction | Construction - General | Inadequate water source for construction. | Lack of planning for adequate water source for construction could result in construction delays and change orders. | L | M | 8 | Project Management | Evaluate demand and sources to confirm adequacey of water supply. | Project Manager |  | VL | VL | 1 | 7
108 | HR | Geotechnical | Bridge | Vulnerable valley floor subsurface strata requiring full-length bridge causway across reservoir. | Full-length bridge causeway would add $100M to the cost of the project. | M | H | 24 | Geotechnical Investigation | Complete subsurface investigations to inform recommendations for causeway design. | Project Manager |  | L | M | 8 | 16
109 | HR | Geotechnical | Roads | Lack of subsurface investigation | Lack of subsurface investigation during preliminary design could result in redesign, delays and construction change orders when final investigations are performed and possibly reveal unexpected results. | M | H | 24 | Geotechnical Investigation | Complete subsurface investigations during preliminary design to adequately inform design. | Project Manager |  | L | M | 8 | 16
110 | HR | Cost | Cost | Cost escallation due to size of project and limited contractors to perform the work. | Limited contractors to perform the work and the size of project could strain available resources to efficiently construct the project which could measurably increase project cost. | M | M | 12 | Program Management | Adequately plan for construction to attract appropriate numbers of contractors. Use contractor outreach. Possibly stagger components of the project which could extend overall project duration but control project cost. | Program Manager |  | L | M | 8 | 4
111 | HR | Cost | Cost | Competing large scale projects in the region such as Sites Reservoir and High Speed Train could strain available qualified contractors. | Lack of available qualified contractors could result in escalated cost to construct and lack of quality in the project. | M | M | 12 | Program Management | Consider the effects of multiple large scale projects on the market and plan accordingly - schedule and budget impacts. | Program Manager |  | L | M | 8 | 4
112 | HR | Cost | Cost | Passing of the Infrastructure Bill creating a flood of work in the construction industry. | Lack of available qualified contractors and high demand on materials and equipment could result in escalated cost to construct the project. | M | M | 12 | Program Management | Consider the effects of a magnitue of projects flooding the industry and plan accordingly - schedule and budget impacts. | Program Manager |  | L | M | 8 | 4
Note on K52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is a copy from the cell above - suggest deleting and adding something similar to what I added
Note on C84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is not a Category and probably should be

## HR Lists
Ratings | Likelihood |  |  | Consequence
Very High | VH | 5 |  | VH | 16 | Probability (%) |  | Prob. Score | Impact
Medium | H | 4 |  | H | 8 | Very High (81 - 100) | VH | 5 | 5 | 10 | 20 | 40 | 80
High | M | 3 |  | M | 4 | High (61 - 80) | H | 4 | 4 | 8 | 16 | 32 | 64
Very High | L | 2 |  | L | 2 | Mod (41 - 60) | M | 3 | 3 | 6 | 12 | 24 | 48
| VL | 1 |  | VL | 1 | Low (21 - 40) | L | 2 | 2 | 4 | 8 | 16 | 32
[6 empty] | Very Low (1 - 20) | VL | 1 | 1 | 2 | 4 | 8 | 16
| H | 4 |  | H | 8 |  |  |  | 1 | 2 | 4 | 8 | 16
| L | 2 |  | L | 2 |  |  | Impact Score | VL | L | M | H | VH
| M | 3 |  | M | 4 |  |  |  | Very Low | Low | Moderate | High | Very High
| VH | 5 |  | VH | 16
| VL | 1 |  | VL | 1
|  |  | 1 | 1
|  |  | 2 | 4
|  |  | 3 | 9
|  |  | 4 | 16
|  |  | 5 | 25

## HC General
Risk ID No. | Risk Category | Risk Location | What is the Problem or Issue? | Description of Consequences What Could go Wrong, How? | Unmitigated Rating |  |  | Mitigation Techniques |  |  |  | Mitigated Rating |  |  | Risk Rating Buy Down
|  |  | Risk Description | Consequences | Likelihood Rating Probability of Deviation from Expectation | Consequence Rating Severity of Impact on Project Outcomes | Unmitigated Risk Factor | Recommended Mitigation(s) for Reducing or "Buying Down" the Risk |  |  |  | Likelihood | Consequence | Mitigated Risk Factor | Risk Factor Buy Down from Mitigation
[8 empty] | Type | Scope | Responsible | Cost
1 | Permitting | Permitting | Delay in FERC review(s) and/or approval(s) based on recent poor performance on another project. | Schedule delays due to late receipt of license, potential contractor claims due to late receipt of design package approvals for construction. | VH | VH | 80 | FERC Consultation by Agency and Engineer | Close agency coordination, effective communication, early agency involvement in project reviews (including pre-payment of a portion of the fee to utilize their time), utilize consultants with proven experience in working with FERC on a day to day basis (office and field), and/or defer FERC licensing and installation of hydroelectric generating capability. |  |  | M | M | 12 | 68
2 | Permitting | Permitting | The conditions of the joint Federally-listed and State-listed species (Delta Smelt, salmonids, sturgeon, and Killer Whale) and the State-listed Long-fin Smelt are declining. | Delays in schedule, reduced ability to fill the reservoir (reduced deliveries), and increased costs. | VH | VH | 80 |  | Cannot depend upon current biological opinions issued to DWR and Reclamation. This project will require separate Federal biological opinions from U.S. Fish and Wildlife Service and National Marine Fisheries Service, and take authorization from California Department of Fish and Wildlife. Preparation of an adequate biological assessment and negotiation of the biological opinions and take authorization could take time, and will probably result in restrictions of construction boundaries, construction methods, construction time periods, and additional environmental protections during construction. The biological opinions also could result in changes to the design of facilities to minimize light, glare, noise, and vibrations (including items like noise from fans in pump stations). The biological opinions and take authorizations also could result in currently not-defined limitations on diversion volumes and rates and timing of diversions. |  |  | M | M | 12 | 68
3 | Permitting | Permitting | Project will require a new water right from the SWRCB | It is anticipated that the application for the permit will result in protests by other legal users of water and concerned groups for the biological resources in the Sacramento River and the Delta. The hearings could require up to a year to allow for testimony from the applicant and protesters. The final water right permit could result in currently not-defined limitations on diversion volumes and rates and timing of diversions. | VH | VH | 80 | Water Rights | Requires significant upfront investment in legal and technical support and planning. |  |  | M | M | 12 | 68
4 | Cost Schedule Permitting | Borrow Areas | Large haul distance to sand and gravel pits currently identified for concrete aggregate and dam filter and drain material (up to 35 miles from site). | Increased cost to project, increased environmental impact and mitigation requirements. | VH | VH | 80 | Geotechnical Investigations, Estimating | Investigate current proposed source and other suitable sources of sand and gravel in the project region on both east and west sides of the reservoir. |  |  | M | M | 12 | 68
5 | Design Safety Cost | Pumping Plants | Suitability of pump station foundations and foundation excavations | Unsuitable foundation conditions, possible need for foundation piling at TRR PGP and Funks PGP. | VH | VH | 80 | Geotechnical Investigations | Drilling, mapping, seismic refraction surveys, laboratory investigations |  | 125000 | L | L | 4 | 76
6 |  | System Operations | Significantly reduced ability to divert water from the Sacramento River | Inability to divert water from the Sacramento River to fill the reservoir | VH | VH | 80 | Permits Operations | Develop acceptable diversion strategy or identify alternative water sources |  | 2000000 | H | M | 16 | 64
7 | Planning Cost Impact identification | General | Currently, only undocumented, localized topographic mapping is available from previous studies to support design and construction planning. Available mapping is old. | Heightened risk of inaccuracy in laying out project facilities and estimating quantities; heightened risk of impacting existing features, facilities, and utilities not currently identified on available mapping; heightened risk of missing potential environmental impacts. | H | VH | 64 | Topographic Mapping | Topographic Mapping: Complete topographic mapping of project area from ground-controlled aerial photography. New aerial photography will also benefit the project for planning purposes and preparation of exhibits and plans. |  |  | L | L | 4 | 60
8 | Financial Viability | General | Insufficient stakeholder participation to fund the project | Termination of project, loss of expended funds. | H | VH | 64 | Outreach | Investor outreach workshops, high quality WSIP application, support federal feasibility study and federal funding, political outreach. |  |  | M | H | 24 | 40
9 | Permitting Cost Schedule | Permitting | Unidentified human remains associated with native American burials outside official cemeteries. | Permitting and construction delays | H | VH | 64 | Archaeologic Evaluation | Execute field surveys as soon as possible to identify risk and remediation cost. |  |  | M | L | 6 | 58
10 | Cost Schedule | Sites Reservoir | South bridge abutment and foundation conditions are unknown | Unreliable design, increased cost, delay to schedule as bridge is constructed early. | H | VH | 64 | Geotechnical Investigations | Drilling program, laboratory testing |  |  | L | L | 4 | 60
11 | Safety Schedule Cost | Main Dams | Foundation conditions need to be better defined at both dam sites. | Construction delays, additional cost for increased excavation and rock stabilization, additional costs for foundation preparation and grouting. | H | VH | 64 | Geotechnical Investigation | Additional site investigation (drilling water pressure testing, seismic refraction). |  |  | L | M | 8 | 56
12 | Cost Schedule | Main Dams | Insufficient information to plan and cost foundation grouting. |  | H | VH | 64 | Geotechnical Investigation | Water pressure testing, test grouting program. |  |  | M | M | 12 | 52
13 | Cost Schedule | Main Dams | Insufficient information available to evaluate dam alternative that could be better. | Higher cost, longer schedule for construction. | H | VH | 64 | Alternative Evaluations | Comprehensive evaluation of RCC and concrete-faced rockfill dam alternatives, ie., geotechnical evaluation of required material sources and suitable foundation conditions. |  |  | L | L | 4 | 60
14 | Cost Schedule | Saddle Dams | Insufficient information to plan and cost foundation grouting. |  | H | VH | 64 | Geotechnical Investigation | Water pressure testing, test grouting program. |  |  | M | M | 12 | 52
15 | Safety Schedule Cost | Saddle Dams | Foundation conditions need to be better defined at both dam sites. | Construction delays, additional cost for increased excavation and rock stabilization, additional costs for foundation preparation and grouting. | H | VH | 64 | Geotechnical Investigation | Additional site investigation (drilling water pressure testing, seismic refraction). |  |  | L | M | 8 | 56
16 | Safety Engineering permitting | Holthouse Reservoir | Spillway adequacy to handle emergency releases. | Downstream channel impacts need to be addressed. | H | VH | 64 | Engineering Environmental Assessments | Determine design flow assuming split in flows between Golden Gate Dam and Sites Dam diversion tunnel. Determine impacts to Funks Creek and public and private facilities downstream. |  |  | L | M | 8 | 56
17 | Coordination Engineering | Holthouse Reservoir | Several WAPA towers exist in the planned Holthouse reservoir expansion area. | Tower Relocation for new Reservoir may be needed. WAPA expressing concern. | VH | H | 40 | Alternative Investigations | Conduct alternative evaluation to relocate the two lines in question. Early and ongoing coordination with WAPA to resolve the conflict in line location. |  |  | L | L | 4 | 36
18 | Design Safety Cost | Pumping Plants | Suitability of fish screen structure and cofferdam in Sacramento River | Unsuitable foundation conditions, lack of data to design in-river cofferdam system and foundation piles for fish screen structure. | H | VH | 64 | Geotechnical Investigations | Geotechnical Investigations: Drilling, mapping, laboratory investigations |  |  | L | L | 4 | 60
19 | Permitting Design | General | Site seismicity higher than previously estimated, update needed. | Current site seismicity data dating back to 2003 may be inadequate for project design and permitting dams and other major structures through state and federal agencies. | H | H | 32 | Engineering | Conduct Site Seismicity Evaluation. Prepare updated site seismicity evaluation that will meet current State (DSOD) and Federal (FERC) standards. |  |  | L | L | 4 | 28
20 | Permitting Cost Schedule | Permitting | Environmental impact of access road to east end of bridge may require deep cut through east reservoir ridge. | Unanticipated visual and environmental impacts | H | H | 32 | Engineering Environmental Reviews | Evaluate extent of cutting; evaluate potential impacts and mitigations, evaluate tunnel through ridge option. |  |  | L | M | 8 | 24
21 | Cost | Construction - General | Significantly higher construction bids than estimated. | Impacts to cash flow, cash reserves, financing costs during construction, cost of water, financial viability of project. | H | H | 32 | Market Analysis, Contractor Outreach | Perform a market analysis as part of each cost estimate update to project market conditions and competition with other projects at the anticipated bid time. Perform market analysis of critical materials (steel, concrete, fabricated equipment, etc.) as part of each estimate. Package work with consideration to cost to avoid limiting bidder pool due to bonding limitations. |  |  | L | M | 8 | 24
22 | Cost Schedule Permitting | Borrow Areas | Lack of core and shell borrow material in vicinity of dam. No investigations available in the vicinity of the dam. | Increased haul distances and costs to construct dam. | H | H | 32 | Geotechnical Investigations | Conduct site investigation between Holthouse Dam and existing Funks Dam to verify availability of construction material to supplement material from the removal of Funks Dam. (Investigation currently in planning stage by Reclamation.) |  |  | L | L | 4 | 28
23 | Safety Project Operation | Sites Reservoir | Stability of downstream outlet tunnel portal | Impact to pump station operation | H | H | 32 | Geotechnical Investigation | Drilling program and laboratory testing |  |  | L | L | 4 | 28
24 | Cost Schedule | Main Dams | Stability of conveyance channel slopes to Holthouse Reservoir. | Slope instability requiring re-work, increased excavation quantities, unanticipated lining and stabilization for slope. | H | H | 32 | Geotechnical Investigation | Additional site investigation (drilling, seismic refraction, geo mapping). |  |  | M | L | 6 | 26
25 | Safety Schedule Cost | Saddle Dams | Depth to sound rock foundation for core trench not sufficiently documented for all dams, scope of previous investigations significantly less for saddle dams than for main dams, addition data needed to design underseepage control using grout cutoff or slurry wall. | Risk to design, potential construction delays, additional construction cost, additional borrow from pits and quarries. | H | H | 32 | Geotechnical Investigations | Additional site investigation (drilling water pressure testing, seismic refraction). |  |  | L | M | 8 | 24
26 | Safety Schedule Cost Permitting | Holthouse Reservoir | Foundation conditions need to be better defined at dam site. No data currently available to support design or permitting for DSOD or FERC. No data available on borrow material source for core. | Permitting delays, design risks, construction delays, additional cost for increased excavation, foundation preparation, and foundation grouting. | H | H | 32 | Geotechnical Investigations | Drilling, piezometers, trenches in borrow area behind proposed dam. |  |  | M | L | 6 | 26
27 | Schedule Cost Permitting | Holthouse Reservoir | Difficulties in handling sediment in Funks. | No data available about composition of sediment that has accumulated in Funks Reservoir, no data on volume of sediment that has accumulated. | H | H | 32 | Geotechnical Investigations, Bathymetry | Perform bathymetric survey of top of sediment to compare with pre-Funks topography to estimate volume; sample and test material to identify character and potential for drainage. |  |  | L | L | 4 | 28
28 | Cost Schedule | Dunnigan Pipeline | High groundwater, significant construction dewatering and pipe flotation. | Cost and schedule impact, redesign, claims | H | H | 32 | Geotechnical Investigations | Drilling, piezometers, evaluate tunnel alternative. |  |  | L | M | 8 | 24
29 | Design Cost Schedule | Delevan/TRR Pipeline | Unanticipated utilities and drainage features | Potential schedule and cost impacts, claims | H | H | 32 | Mapping and Ground Surveys | Detailed utility surveys, potholing, topographic mapping, evaluate tunnel alternative. |  |  | L | L | 4 | 28
30 | Permitting | Delevan/TRR Pipeline | Inability to open cut through Colusa Basin Drain and adjacent to wildlife preserves due to environmental concerns and mitigation costs. | Potential schedule and cost impacts. | H | H | 32 | Geotechnical Investigations, Alternative Evaluation | Evaluate feasibility of soft ground tunneling in restrictive areas. |  |  | L | M | 8 | 24
32 | Schedule Cost | Real Estate | Property acquisition delayed | Start of construction delayed. Jeopardizes on-schedule completion. | H | H | 32 | Planning | Develop Real Estate Acquisition Plan in Phase 2 and implement acquisition and Communication Plan at the beginning of Phase 3 and provide relocation assistance |  | 10000000 | M | M | 12 | 20
33 | Permitting | Permitting | Current reservoir design assumes full storage of the Probable Maximum Flood with no emergency spillway other than minimal pipe (signal spillway) at one saddle dam. | DSOD expressed concern with no emergency spillway. | VH | M | 20 | DSOD/FERC Consultation by Agency and Engineer | Further consultation with DSOD to clarify concern; clarify minimum design criteria required by DSOD specific to the project; reflect criteria in reservoir design criteria. |  |  | L | L | 4 | 16
34 | Permitting | Permitting | Delay in DSOD review(s) and/or approval(s) | Schedule delays, potential contractor claims. | M | VH | 48 | DSOD Consultation by Agency and Engineer | Close agency coordination, effective communication, early agency involvement in the project (including pre-payment of a portion of the fee to utilize their time), utilize consultants with proven experience in working with DSOD on a day to day basis (office and field). |  |  | M | M | 12 | 36
35 | Cost Schedule Claims | Construction - General | Interference among various contractors working on site due to poor packaging of project work. | Work activity interference, lack of access to work areas by multiple contractors simultaneously, restricted availability of materials (aggregate, cement, steel, power). Can lead to schedule delays and claims. | M | VH | 48 | Bidding Strategy | Develop a bidding strategy to package and schedule the work to minimize work interfaces between packages. Evaluate and include coordination requirements in contract documents, including critical milestone dates to vacate work areas or complete components of the work. Develop/implement a management plan that includes coordination. |  |  | L | M | 8 | 40
36 | Schedule Cost | Construction - General | Delay(s) in mechanical equipment fabrication, delivery, and quality control testing | Installation and construction completion delays, startup and commissioning delays. | M | VH | 48 | Planning Contracting | Early market analysis of shop floor availability. Possible pre-procurement of major mechanical/electrical components that are critical path items. |  |  | L | VH | 32 | 16
37 | Cost Schedule Permitting | Borrow Areas | Core borrow quantity available in reservoir for main dams and saddle dams. | Increased cost to project, increased environmental impact and mitigation requirements. | M | VH | 48 | Geotechnical Investigations, Estimating | Review of all available DWR data, supplemental investigations and testing as necessary. |  |  | L | L | 4 | 44
38 | Cost Schedule Permitting | Borrow Areas | Rock fill and rip rap quantity available in reservoir ridges and other excavations for main dams and saddle dams, including impact of interbedded soft and hard rock layers.. | Increased cost to project, increased environmental impact and mitigation requirements. | M | VH | 48 | Geotechnical Investigations, Estimating | Review of all available DWR data, supplemental investigations and testing as necessary. |  |  | L | L | 4 | 44
39 | Safety Resource Protection Permitting | Sites Reservoir | East Rim Seepage | Loss of water resource, seeps and springs on east side, east side slope instability | M | VH | 48 | Geotechnical Investigations | Drilling program with water pressure testing to evaluate seepage potential and design mitigation measures (rim grouting) |  |  | L | L | 4 | 44
40 | Safety Project Operation | Sites Reservoir | Stability of outlet works tower | Loss of reservoir control | M | VH | 48 | Evaluate Alternatives | Evaluate stability under static and seismic loading; evaluate alternatives, including sloping intake replacement. |  |  | L | L | 4 | 44
41 | Safety Schedule Constructability | Sites Reservoir | Stability of tunnel during excavation | Adverse impacts to construction cost and schedule, potential for claims. | M | VH | 48 | Geotechnical Investigations | Drilling program, engineering studies |  |  | L | L | 4 | 44
42 | Cost Schedule | Main Dams | Dam axis not in optimum location to minimize cost. | Increased construction cost, increased need for imported filter/drain aggregates, increased DSOD permitting costs. | M | VH | 48 | Geotechnical Investigation, Alternative Evaluation | Additional site investigation (drilling water pressure testing, seismic refraction), alternative location evaluations. |  |  | L | L | 4 | 44
43 | Cost Schedule | Saddle Dams | Dam axis not in optimum location to minimize cost. | Increased construction cost, increased need for imported filter/drain aggregates, increased DSOD permitting costs. | M | VH | 48 | Geotechnical Investigation, Alternative Evaluation | Additional site investigation (drilling water pressure testing, seismic refraction), alternative location evaluations. |  |  | L | L | 4 | 44
47 | Schedule Cost | General | New stakeholders (e.g., Board, JPA staff, member agencies). | Slows forward project momentum, could impact project configuration. | M | H | 24 | Team Building | Accelerated effort to bring new players up to speed as quickly as possible, limit ability of new players by agreement to radically modify project technical and financial details. |  |  | L | L | 4 | 20
48 | Permitting Schedule Cost | Permitting | New endangered species identified. | Schedule delays, added cost, additional environmental studies, amendments required to EIR/EIS documents, unanticipated additional mitigation costs. | M | H | 24 | Agency Action | Early acquisition of easements and property with on-going land management. |  |  | L | M | 8 | 16
49 | Cost Schedule Claims | Construction - General | Excessive flooding occurs during construction. | Loss of complete work, schedule delays due to the event and to make repairs. | M | H | 24 | Planning Engineering | Develop a bidding strategy to package and schedule the work to minimize work interfaces between packages. Evaluate and include coordination requirements in contract documents, including critical milestone dates to vacate work areas or complete components of the work. Develop/implement a management plan that includes coordination. |  |  | L | M | 8 | 16
50 | Safety | Construction - General | Serious accident(s) during construction. |  | M | H | 24 | Engineering Contracting | Implement a safety-by-design approach to comply with applicable industrial safety standards and minimize creating unsafe conditions. Require contractors to comply with all applicable federal and state safety requirements and have detailed job safety plans and work activity risk assessments. Provide a qualified safety officer on the construction management team to monitor performance, and enforce safety requirements if needed. |  |  | L | M | 8 | 16
51 | Cost Schedule | Construction - General | Disruption in availability of materials (cement, steel, rebar, etc.). | Reduced progress, increased cost, higher bids if disruption occurs at bid time. | M | H | 24 | Engineering Contracting | Conduct market analysis prior to bidding. If disruption is possible, consider including provisions in contract for contractor(s) to pre-procure sufficient material at NTP and cover storage costs to avoid shortage delays. |  |  | L | M | 8 | 16
52 | Cost | Construction - General | Unexpected escalation/run-up in price of construction materials and labor | Cost increases. | M | H | 24 | Contracting | Lock in price at award of contract, transfer risk to contractor. |  |  | L | L | 4 | 20
53 | Schedule Cost Quality | Construction - General | Unsatisfactory performance by contractor(s) | Schedule delays, poor work quality. | M | H | 24 | Planning Contracting | Prequalify contractors for major packages. Performance goals and milestone dates in contract with liquidated damages. |  |  | L | H | 16 | 8
54 | Cost | Construction - General | Availability of construction materials | The availability of materials could be impacted by WSIP awards to multiple projects at once, creating competition for materials | H | M | 16 | Planning
55 | Safety Schedule Cost | Main Dams | Rock toppling issues in core trench excavations on slopes due to adverse rock bedding. | Construction delays, addition cost for increased excavation and rock stabilization. | M | H | 24 | Geotechnical Investigation | Additional drilling and geologic mapping of rock outcrops. |  |  | M | L | 6 | 18
56 | Cost Schedule | Dunnigan Pipeline | Encountering unsuitable foundation soils, particularly in CBD area. | Potential schedule and cost impacts, claims | H | M | 16 | Geotechnical Investigations | Drilling, sampling, laboratory testing, evaluate tunnel alternative. |  |  | L | L | 4 | 12
57 | Cost Schedule | Funks/TRR Pipeline | Encountering hard foundations (rock) west of GCID Canal. | Potential schedule and cost impacts, claims | H | M | 16 | Geotechnical Investigations | Drilling, seismic refraction surveys, evaluate tunnel alternative. |  |  | L | L | 4 | 12
59 | Schedule Cost | Intake | Wildlife at intake location (yellow billed cuckoo, bank swallow, and giant garter snake) | Difficulty in obtaining permits | H | M | 16 | Planning | Mitigation with compensatory acreage, pre-construction development of compensatory habitat, and reduced construction periods |  | 300000 | H | L | 8 | 8
60 | Schedule | Real Estate | Failure to acquire temporary entry permits on schedule. | Delay to completion of design and potential quality impact is timely access cannot be arranged. | H | M | 16 | Planning | Develop Real Estate Communication Plan and initiate temporary entry permit process prior to or at the beginning of Phase 2 |  | 200000 | H | L | 8 | 8
61 | Schedule Cost | Real Estate | Potential requirement for condemnation of property for acquisition | Legal process delays construction | M | H | 24 | Planning | Develop robust alternative analysis in the EIR/S to support condemnation |  |  | M | M | 12 | 12
62 | Permitting Schedule Cost | Permitting | Rejection of mitigation package by resource agencies. | Construction start delays, over-all schedule delays, added cost. | L | VH | 32 | Agency Coordination | Close coordination with agencies in pre-design. |  |  | L | M | 8 | 24
63 | Permitting Schedule Cost | Permitting | Significant design feature(s) not covered in EIR/EIS document. | Schedule delays, added cost, additional environmental studies, amendments required to EIR/EIS documents, unanticipated additional mitigation costs. | L | VH | 32 | Engineering | Good early definition of all project components and footprints. |  |  | L | L | 4 | 28
64 | Schedule | Construction - General | Availability of power during construction | Construction delays, startup and testing delays, reservoir filling delays. | L | VH | 32 | Planning Coordination Engineering | Pre-planning and coordination with WAPA and PG&E to make sure power is available for construction, and that any required system upgrades are in place on schedule to support startup and testing. |  |  | L | L | 4 | 28
65 | Safety Cost Permitting | Sites Reservoir | No prior consideration given to damage to Funks Creek downstream of Holthouse and Stone Corral Creek from emergency project releases. | Major erosion damage and potential damage to crops and structures, potential damage to roads and road closures. | L | VH | 32 | Engineering and Environmental Evaluation | Evaluate potential damage and identify potential mitigation measures to include in project design and in emergency response planning. |  |  | L | M | 8 | 24
66 | Cost | General | Higher appraisal/acquisition cost than budgeted for. | Cost impact, impact to project financial evaluation and BC ratio. | M | M | 12 | Consultant Services | Thorough, conservative evaluation of land costs, periodically updated, using consultants/agents familiar with real estate in project region. |  |  | L | L | 4 | 8
67 | Permitting Schedule | Permitting | Public concerns - Recreation / Construction (light, traffic, noise) | Permitting delays due to public comments/concerns | M | M | 12 |  | Public outreach. |  |  | L | L | 4 | 8
68 | Permitting | Permitting | Agency restrictions for discharging ground/construction water onto surface water | Cost impact | M | M | 12 |  | Clarify agency requirements for EIR/EIS documents and include requirements in construction contract documents. |  |  | L | L | 4 | 8
69 | Safety Resource Protection Project Operation | Sites Reservoir | High pressure water leakage out of the tunnel during operation | Impact to natural and excavated slopes from unanticipated leakage. | M | M | 12 | Geotechnical Investigations | Drilling program, Water pressure tests to evaluate tunnel lining requirements, confirm with hydrojacking tests during construction. |  |  | L | L | 4 | 8
70 | Permitting | Holthouse Reservoir | Dam construction can impact alkaline wetland identified on right abutment just downstream of planned dam. | Mitigation may be necessary that is not currently identified. Source of seepage water feeding area needs to be identified. | M | M | 12 | Geotechnical and Geologic Investigations | Identify the source of the seepage water and determine if dam foundation construction will reduce or dry up the source. Mitigation design may also be needed if the site will be impacted. |  |  | L | L | 4 | 8
71 | Operation | O&M | Catastrophic Flood events affecting facilities other than the dams and reservoir. (Dams, reservoir, and associated facilities assumed covered by Probable Maximum Flood requirements of DSOD and FERC.) | Impact to operation and maintenance activities, loss of access to some facilities, damage/loss of access roads, damage to some facilities and facilities. | M | M | 12 | Engineering Planning | Identify an appropriate design basis rainfall or flood event to provide a risk-tolerable level of protection for all facilities considered critical for continued operation. |  |  | L | L | 4 | 8
72 | Cost Schedule | General | Unsatisfactory performance by design consultant(s). | Permitting and construction delays, cost impacts. | L | H | 16 | Contracting, Contract Management | Proper selection of consultants with current, relevant, proven, experience; frequent reporting of progress; periodic performance reviews; periodic quality reviews. |  |  | L | L | 4 | 12
73 | Schedule Quality Cost Claims | Construction - General | Unsatisfactory performance by construction management consultant(s) | Loss of control of construction contractors, schedule delays, quality issues, increased claim potential, risks to reimbursements from bond money and other funding sources. | L | H | 16 | Contracting | Pre-qualification, shed portion of liability to consultant(s). |  |  | VL | H | 8 | 8
74 | Schedule Quality | Construction - General | Construction Defects | Schedule delays for repairs, risks to reimbursements from bond money and other funding sources because of quality concerns and nonconformance to plans and specifications. | L | H | 16 | CM | Implement QC inspection and testing program, implement FERC QCIP for all dams. |  |  | L | M | 8 | 8
75 | Safety Resource Protection Project Operation Permitting | Sites Reservoir | Presence of alkaline springs identified at north end of reservoir area. | Contamination of reservoir, loss of water into springs. | L | H | 16 | Geotechnical Investigations | Evaluate, map, and possibly drill in vicinity of springs to determine extent of problem and methods to plug. |  |  | L | L | 4 | 12
76 | Operation Safety | Sites Reservoir | Reservoir rim instability due to large reservoir fluctuations. | Maintenance issue for slope slumping. | M | L | 6 | Geotechnical and Geologic Investigations | Geotechnical and geologic review and mapping of reservoir rims. |  |  | L | L | 4 | 2
77 | Permitting | Permitting | Agency restrictions on air quality impacts due to heavy construction equipment | Cost impact | L | L | 4 |  | Clarify agency requirements for EIR/EIS documents and include requirements in construction contract documents. |  |  | L | L | 4 | 0
201 (Jacobs-Vanderweil) | Cost Schedule | Overhead Transmission Lines | Delay in procuring large equipment such as poles, structures and conductors | Delays in schedule and added cost | M | M | 12 | Evaluate Alternatives | Good early definition of all project components and footprints. |  |  | M | M | 12 | 0
202 (Jacobs-Vanderweil) | Cost Schedule | Overhead Transmission Lines | The transmission lines will need to cross the WAPA, TANC, and PGE existing lines, approval delays may impact installation | Delays in schedule and added cost | M | M | 12 | Planning Contracting | Close coordination with transmission operator in pre-design. |  |  | M | M | 12 | 0
203 (Jacobs-Vanderweil) | Cost Schedule | Overhead Transmission Lines | The transmission lines will need to interconnect with PGE existing lines, interconnection approval delays may impact schedule and may include unknown requirements | Delays in schedule and added cost | M | H | 24 | Planning Engineering | Close coordination with transmission operator in pre-design. |  |  | M | M | 12 | 12
204 (Jacobs-Vanderweil) | Cost Schedule | Overhead Transmission Lines | Interconnection with PG&E, as well as possible rework of some main line WAPA and PG&E structures, will require line outages that may be limited to certain months of the year. | Delays in schedule and added cost | M | H | 24 | Planning Engineering | Close coordination with transmission operator in pre-design. |  |  | M | M | 12 | 12
205 (Jacobs-Vanderweil) | Cost Schedule | Electrical Substation | Delay in procuring large equipment such as transformers or breakers | Delays in schedule and added cost | M | M | 12 | Planning Engineering | Good early definition of all project components and footprints.
206 (Jacobs-Vanderweil) | Cost Schedule | Electrical Substation | The substations will need approvals for Arrangement and Protective Relay Requirements to ensure that there are safe disconnect facilities for fault detection at the generators and faults on the PG&E Power System. Design approval delays from PGE, may impact the schedule. | Delays in schedule and added cost | M | H | 24 | Planning Engineering | Close coordination with transmission operator in pre-design.
207 (Jacobs-Vanderweil) | Cost Schedule | Electrical Substation | Delays in procuring control & instrumentation cable for transformers or breakers and relay protection devices. | Delays in schedule and added cost | M | H | 24 | Planning Engineering | Good early definition of all project components and footprints.
208 (Jacobs-ZGlobal) | Schedule | Pumping Generating Plants | Potential delays in CAISO study process due to recent "Super Cluster" Issue and canceled 2022 submission window and risk of 2024 being canceled | Delays in study process may result in delay in finalizing Interconnection Agreement and ability to reach COD for Pumping and Generationg plants | M | H | 24 |  | Little if anything can be done with CAISO timeline. Alternaive approach is to seek interconnection with WAPA. WAPA study process is significanly less complex with much shortend timeline. |  |  | M | L | 6 | 18
209 (Jacobs-ZGlobal) | Schedule | Pumping Generating Plants | Potential delays in being released for full operation due to "time to construct" durations for network upgrades | Total or partial dealy in reaching full generation and pumpting operatoins. | H | H | 32 | Planning | Execute MOU and early funding with PG&E to advance design and engineering of requred network upgrades. |  |  | H | H | 32 | 0
210 (Jacobs-ZGlobal) | Cost Schedule | Pumping Generating Plants | Large Interconnection Financial Security (IFS) Posting requried due to high cluster study participation. | Large financial scuring positng due at end of Phase 1 study due to large number of projects in study. For CAISO 50% of the IFS is at risk of project is withdrawn | VH | M | 20 | Planning | Include sizable budget item for the IFS. |  |  | VH | L | 10 | 10
211 (Jacobs-Dyok) | Permitting | Permitting | Delay in FERC review(s) and/or approval(s) based on recent poor performance on another project. | Schedule delays due to late receipt of license/exemption, potential contractor claims due to late receipt of design package approvals for construction. | VH | VH | 80 | FERC Consultation by Agency and Engineer | Close agency coordination, effective communication, early agency involvement in project reviews (including pre-payment of a portion of the fee to utilize their time), utilize consultants with proven experience in working with FERC on a day to day basis (office and field), and/or formally verify that project qualifies for two municaipal exemptions after EIS/CEQA document has been prepared. |  |  | M | M | 12 | 68
212 Jacobs-Dyok) | Cost Schedule | Pumping Plants | Delays in procuring major mechanical and electrical equipment. | Construction delays, start up and commissioning delays. Reservoir filling delays. | M | VH | 48 | Planning Contracting | Early market analysis of shop floor availability. Possible pre-procurement of major mechanical/electrical components that are critical path items. |  |  | L | VH | 32 | 16
213 (Jacobs-Dyok) | Design Cost Operation | Pumping Plants | Selection of pumping and generating unit number and size. | Not having the appropriate number and size of units can introduce extra cost, cause operation problems, and increase operational and maintenance costs. Can also limit the number of potential equipment suppliers. | H | H | 32 | Alternative Evaluation | Alternative Evaluations: Study alternative unit size combinations, costs, and operational flexibility to match pumping and generating requirements based on current modeling results. |  |  | L | L | 4 | 28
214 (Jacobs-Geosyntec) | Cost | Funks Reservoir | Several hundred thousand cubic yards of sediment are planned to be removed from Funks Reservoir. These materials are intended to be reused as fill and/or for resotration of quarries or borrow areas on Site. It is unkown whether or not the sediments contain any contaminates of concern (COCs) that may preclude their use as fill or restoration materials on Site. If COCs are present, the sediments will need to off-hauled to an appropriate containment site. | This would increase costs. | M | M | 12 | Environmental Characterization | Sample and test material to identify character and potential for drainage and contaminants. |  |  | L | M | 8 | 4
215 (Jacobs-Geosyntec) | Stakeholder Relationships Schedule | Funks Reservoir | Removal of sediment from Funks may impact operation of TCC. | Increased water quality issue for downstream deliveries and may carry sediment that deposits in TCC downstream. Could result in schedule constraints. | M | M | 12 | Design Planning | Look at ways to isolate reservoir dredging operations from the main canal flow stream - use silt curtains, levees, timing of operations (when system shutdown in winter). Early agreement with TCC on requirements/criteria. |  |  | VL | M | 4 | 8
216 (Jacobs-Geosyntec) | Schedule | Funks Reservoir | Two cofferdams within the reservoir are planned to facilitate construction of the Funks PGP and the TRR pipeline alignment. These are expected to be constructed within a short annual construction window when the reservoir is low. Unknown foundation conditions beneath planned cofferdams. | If adverse condition encountered during construction, these could significantly impact schedule - likely a 1-2 year delay of all in-reservoir work (e.g., pipelines). | M | H | 24 | Geotechnical Investigation Design Planning | Drilling, sampling, testing, evaluation, and design to develop an appropriate design and construciton plan that is schedule resilient. |  |  | L | L | 4 | 20
217 (Jacobs-Geosyntec) | Schedule Costs | Funks Reservoir | Uncertain weather or existing TCCA facility operations impacts could shorten the annual construction window or result in difficult working conditions for the cofferdams and in-reservoir excavation when the reservoir is low. | Delays in schedule and increases in cost. | M | H | 24 | Geotechnical Investigation Planning | Develop a construction plan that is schedule resilient with information on the materials. |  |  | L | M | 8 | 16
218 (Jacobs-Geosyntec) | Schedule Cost Construction | TRR Reservoir (East) | Groundwater may be higher than anticipated. | May impact schedule and cost during construction. | M | L | 6 | Geotechnical Investigation | Drilling and test pits, piezometers. |  |  | L | L | 4 | 2
219 (Jacobs-Geosyntec) | Permitting Cost Real Estate Schedule | TRR Reservoir (East) | Funks Creek capacity to handle emergency spills | Environmental and DSOD permitting challenges. Additional real estate impacts not yet accounted for. Higher costs. Downstream and immediately upstream stakeholder concerns about induced flooding and bank erosion. | VH | VH | 80 | Design Planning | Attempt to reconfigure design or reduce the required release criteria to bring down the associated risks. |  |  | VH | H | 40 | 40
220 (Jacobs-Geosyntec) | Real Estate Cost | TRR Reservoir (East) | Challlenge in getting heavy equipment in place on GCID canal to construct access bridge as designed | Additional real estate temporary easement and/or more expensive construction techniques. | M | M | 12 | Design Planning | Optimize bridge and/or abutment design. |  |  | L | M | 8 | 4
221 (Jacobs-Geosyntec) | Real Estate Cost Schedule | TRR Reservoir (East) | Reservoir requires obtaining multiple lands from owners including multiple orchards and different orchard owners. | Unwilling seller could delay project and add cost | VH | H | 40 | Real Estate | To be addressed by Sites/Real Estate
222 (Jacobs-Geosyntec) | Permitting Schedule Cost | TRR Reservoir (East) | Delay in DSOD review(s) and/or approval(s) | Schedule delays, potential contractor claims. | M | M | 12 | DSOD Consultation by Agency and Engineer Design | Close agency coordination and design conservatism. Cost of construction would increase due to design conservatism. |  |  | L | M | 8 | 4
223 (Jacobs-Geosyntec) | Real Estate Schedule Cost | TRR Reservoir (East) | Induced settlement of exisitng facilities. | Adjacent stakeholder concerns, schedule delays, and cost insreases. | H | M | 16 | Design Planning | Conservatism in design. Cost of construction would increase. |  |  | L | M | 8 | 8
224 (Jacobs-Geosyntec) | Cost | TRR Reservoir (West) | Construction requires significant cut which generates excess material for disposal | May generate excess cost to haul away in case cuts/fills for project not balanced. | H | M | 16 | Design Planning | Look for opportunities to use excess cut for embankments, dam construction, roads; integration among consultant teams. |  |  | VL | VL | 1 | 15
225 (Jacobs-Geosyntec) | Real Estate Cost Schedule | TRR Reservoir (West) | Reservoir requires obtaining multiple lands from owners including one orchard. | Unwilling seller could delay project and add cost | H | M | 16 | Real Estate | To be addressed by Sites/Real Estate
226 (Jacobs-Geosyntec) | Permitting Schedule | TRR Reservoir (West) | Current configuration requires PG&E approval to construct tunnel beneath underground utility corridor. Maybe difficult to gain concurrence. | Schedule delays due to obtaining permits. | H | M | 16 | Planning | Negotiate with GCID to reduce required storage capacity to reconfigure reservoir east of the PG&E corridor and avoid the need for the tunnel. Discuss with PG&E early in preliminary design |  |  | L | VL | 2 | 14
227 (Jacobs-Geosyntec) | Schedule Cost | TRR Reservoir (West) | Due to lack of subsurface information, the slopes for the TRR West reservoir may be optimistically designed (too steep). | Expansion of footprint due to lack of subsurface information. Schedule delays and costs. | M | VH | 48 | Geotechnical Investigation Design | Drilling, sampling, testing, evaluation, and design. |  |  | L | L | 4 | 44
228 (Jacobs-Geosyntec) | Schedule Cost | TRR Reservoir (West) | Foundation geotechnical conditions along the geologic contact of the southeastern margin of the reservoir could be worse than anticpated. | May increase cost and delay schedule if mitigation is required | M | H | 24 | Geotechnical Investigation Design | Drilling, sampling, testing, evaluation, and design. |  |  | L | M | 8 | 16
229 (Jacobs-Geosyntec) | Permitting Schedule Cost | TRR Reservoir (West) | Delay in DSOD review(s) and/or approval(s) | Schedule delays, potential contractor claims. | M | M | 12 | DSOD Consultation by Agency and Engineer Design | Determine upfront of TRR West is a jurisdictional dam with DSOD. Close agency coordination and design conservatism. Cost of construction would increase due to design conservatism. |  |  | L | M | 8 | 4
230 (Jacobs) | Permitting Schedule Cost | CBD | Landowners upstream/downstream of Project discharge point on CBD do not want Project Flows in CBD during certain critical months | Cost and Schedule delays and additional permitting. | M | M | 12 | Hydraulic Modeling, Engineer Design, Real Estate | Contact and work with affected landowners early. Coordinate and come to agreement with RD108 an DWR on KLOG and CBD Operations. |  |  | M | M | 12 | 0
231 (Jacobs) | Permitting Schedule Cost | GCID Fish Screen - Diverson at Hamilton City | Fish Screen requires substantial retrofit to divert waters during winter | Cost and Schedule delays and additional permitting. | M | M | 12 | Hydraulic Modeling, Engineer Design | Work with GCiD during winter 2021/2022 to better understand potential impacts to existing fish screen facility |  |  | M | M | 12 | 0

## HC Lists
Ratings | Likelihood |  |  | Consequence
Very High | VH | 5 |  | VH | 16 | Probability (%) |  | Prob. Score | Impact
Medium | H | 4 |  | H | 8 | Very High (81 - 100) | VH | 5 | 5 | 10 | 20 | 40 | 80
High | M | 3 |  | M | 4 | High (61 - 80) | H | 4 | 4 | 8 | 16 | 32 | 64
Very High | L | 2 |  | L | 2 | Mod (41 - 60) | M | 3 | 3 | 6 | 12 | 24 | 48
| VL | 1 |  | VL | 1 | Low (21 - 40) | L | 2 | 2 | 4 | 8 | 16 | 32
[6 empty] | Very Low (1 - 20) | VL | 1 | 1 | 2 | 4 | 8 | 16
| H | 4 |  | H | 8 |  |  |  | 1 | 2 | 4 | 8 | 16
| L | 2 |  | L | 2 |  |  | Impact Score | VL | L | M | H | VH
| M | 3 |  | M | 4 |  |  |  | Very Low | Low | Moderate | High | Very High
| VH | 5 |  | VH | 16
| VL | 1 |  | VL | 1
|  |  | 1 | 1
|  |  | 2 | 4
|  |  | 3 | 9
|  |  | 4 | 16
|  |  | 5 | 25