## Sheet2
Activity Name | Start | Finish
Water Right Permit | 12-May-22 A | 2024-09-26
SWRCB Determines Application is Complete | 12-May-22 A | 2023-02-02
SWRCB Issues Notice of Application & Petitions for Assignment & Releases from Priority | 2023-03-06 | 2023-03-06
Deadline to Submit Protests | 2023-05-04 | 2023-05-04
Sites Authority & Protestants Resolve Protests | 2023-05-05 | 2023-10-27
Pre-Hearing Conference | 2023-12-01 | 2023-12-01
SWRCB Issues Hearing Notice | 2024-01-04 | 2024-01-04
Case in Chief Testimony Due | 2024-03-07 | 2024-03-07
Hearings (Presentation of Cases-in-Chief) | 2024-03-22 | 2024-04-18
Rebuttal Testimony Due | 2024-05-03 | 2024-05-03
Rebuttal Hearing | 2024-05-20 | 2024-06-03
Briefs Due | 2024-07-31 | 2024-07-31
SWRCB Issues Water Right Permit |  | 2024-09-26
Clean Water Act 401 & 404 Permits (SWRCB & USACE) | 04-Jan-21 A | 2024-05-31
Prepare Draft CWA 401 Permit Application | 04-Jan-21 A | 2023-05-30
Submit CWA 401 Application | 2023-05-31 | 2023-05-31
Receive CWA Section 401 Permit |  | 2024-05-31
Prepare Draft 404 Application | 04-Feb-21 A | 2023-05-30
Submit 404 Application | 2023-05-31 | 2023-05-31
Receive 404 Permit |  | 2024-05-31
National Historic Preservation Act (NHPA) | 14-Mar-22 A | 2023-08-01
Prepare Final PA | 14-Mar-22 A | 2023-03-31
Circulate Final PA to SHPO & Consulting Parties | 2023-04-03 | 2023-05-26
Circulate Final PA to Parties for Signatures | 2023-06-20 | 2023-07-18
Execute Final PA | 2023-07-19 | 2023-08-01
Incidental Take Permits (ITP's) | 2023-01-31 | 2023-08-31
Submit CESA ITP Application - Operations | 2023-01-31 | 2023-01-31
Re-Submit CESA ITP Application - Construction | 2023-01-31 | 2023-01-31
Receive CESA ITP - Operations |  | 2023-08-31
Receive CESA ITP - Construction |  | 2023-08-31
Endangered Species Act Section 7 | 11-Jan-21 A | 2023-10-31
Prepare Draft BA | 11-Jan-21 A | 2023-02-10
Reclamation Submits BA to USFWS & NMFS | 2023-02-13 | 2023-02-13
Reclamation Initiates Consultation with FWS & NMFS | 2023-04-07 | 2023-04-20
Receive USFWS/NMFS Biological Opinions (Incidental Take Authorizations) |  | 2023-10-31
Other Agreements & Benefits | 01-Feb-22 A | 2025-02-20
Initiate Application for Permit to Construct from DSOD | 01-Feb-22 A | 2024-12-30
Develop & Execute Agreement for Administration of Public Benefits with DWR | 31-Mar-22 A | 2023-07-31
Develop & Execute Agreement for Administration of Public Benefits with CDFW | 31-Mar-22 A | 2023-07-31
Final Operating Agreement - Sites/DWR/Reclamation | 19-Apr-22 A | 2023-05-26
Develop Benefits & Obligations Contract with Participants | 2023-02-03 | 2023-11-14
Negotiate Reclamation Benefits & Obligations Contract | 2023-02-17 | 2023-10-17
Refuge Delivery Agreement with Reclamation | 2023-02-17 | 2023-10-19
Submit Power Interconnection Application | 2023-03-20 | 2023-04-14
Authority Certifies EIR & Approves Project |  | 2023-05-19
ROD Signed |  | 2023-10-31
Investor Commitment |  | 24-Oct-24*
Receive WSIP Final Award from CWC |  | 2024-11-25
Participation Agreement: Home Board Execution & Final Rebalancing | 2024-12-10 | 2025-02-20
Financing & Estimating | 2023-03-29 | 2024-07-08
Submittal of Final WIFIA Application |  | 2023-03-29
WIFIA Loan Negotiation | 2023-03-30 | 2024-03-25
Close USDA Loan |  | 2024-07-08
Consultation, Coordination & Oversight | 01-Sep-20 A | 2024-12-30
NAHC/Local Tribes AB 52 Consultation | 01-Sep-20 A | 2023-07-07
Coordination & Oversight: DWR, WAPA, CAISO, UPRR, Caltrans | 03-Jan-22 A | 2024-12-30