## Sheet1
Mitigation Measure | Start Implementation |  |  |  | Complete Implementation
| Pre- | During | Post | Operations | Pre-Construction | During Construction | Post Construction | Operations | Specific Timing | Schedule | Area Applicable | Estimated Budget for 2023
| Construction | Construction | Construction
Mitigation Measure WQ-1.1: Methylmercury Management | X | [6 empty] | X | Page 6-58 – “implement the following actions as part of the RMP” during operation; however, “Remove vegetation (e.g., brush, trees) in the inundation area prior to initial reservoir filling.” | Reservoir Management Plan (RMP) needs to be prepared prior to construction; implementation of veg removal prior to filling | Reservoir
Mitigation Measure WQ-2.1: Prevent Metals Impacts in Stone Corral Creek Associated with Sites Reservoir Discharge | X | [6 empty] | X | Page 6-94 – “Samples will be collected every other month for 1 year prior to construction and every other month after construction for a period sufficient to indicate that any impacts are less than significant, including during periods when the reservoir is at least 75% full.” | 1 year prior to construction | Reservoir
Mitigation Measure WQ-2.2: Prevent Net Detrimental Metal and Pesticide Effects Associated with Moving Colusa Basin Drain Water Through the Yolo Bypass |  |  |  | X |  |  |  | X | Page 6-95 – “Samples will be collected monthly during June–October to evaluate concentrations before and during the period of CBD discharge to the Yolo Bypass.”
Mitigation Measure VEG-1.1: Conduct Appropriately Timed Surveys for Special-Status Plant Species Prior to Construction Activities | X |  |  |  | X |  |  |  | Page 9-26- “conduct special-status plant surveys of the Project footprint, including all permanent and temporary construction impact areas and a 250-foot-wide buffer area to encompass areas where indirect effects may occur” and “Surveys will occur during the season that special-status plant species would be evident and identifiable, which generally is during their blooming period. The surveys will be conducted no more than 3 years prior to the start of ground-disturbing activities.”
Mitigation Measure VEG-1.2: Establish Activity Exclusion Zones Around Special-Status Plants in Temporary Impact Areas and Compensate for Permanent Impacts on Special-Status Plant Species | X | [5 empty] | X |  | Pages 9-26 and 9-27 – “avoid Project impacts on the species, if feasible, through the establishment of activity exclusion zones, in which no ground-disturbing activities will take place, including construction staging or other temporary work areas” and, “Prior to any construction activities that would result in permanent impacts on special-status plants, the Authority will acquire and permanently protect compensatory mitigation habitat for each affected species”
Mitigation Measure VEG-1.3: Establish Activity Exclusion Zones Around Special-Status Plants Prior to Vegetation Maintenance Activities |  |  |  | X |  |  |  | X | Page 9-27 – “Prior to surface-disturbing maintenance or herbicide use, the Authority will use the results of the surveys conducted under Mitigation Measure VEG-1.1 to mark the known locations of special-status plants in or within 50 feet of any maintenance areas.”
Mitigation Measure VEG-2.1: Conduct Surveys for Sensitive Natural Communities and Oak Woodlands in the Project Area Prior to Construction Activities | X |  |  |  | X |  |  |  | Page 9-38- “Prior to the start of any Project construction activities, the Authority will retain qualified botanists to conduct surveys of the Project area, including all permanent and temporary impact areas and an additional buffer of 250 feet to encompass potential indirectly affected areas.”
Mitigation Measure VEG-2.2: Avoid and Compensate for Adverse Effects on Sensitive Natural Communities | X | [5 empty] | X |  | Page 9-39 – “the Authority will avoid Project impacts on the community, if feasible, through the establishment of activity exclusion zones, in which no ground-disturbing activities will take place, including construction staging or other temporary work areas” and “Prior to any activities that would result in permanent impacts on sensitive natural communities, the Authority will acquire and permanently protect compensation habitat for each affected species”
Mitigation Measure VEG-2.3: Establish Activity Exclusion Zones Around Sensitive Natural Communities Prior to Vegetation Maintenance Activities |  |  | X |  |  |  |  | X | Page 9-40 – not specifically stated, “The Authority will fence and avoid any parts of sensitive natural communities that occur in or within 50 feet of the vegetation maintenance areas that could be affected by surface-disturbing maintenance activities.”
Mitigation Measure VEG-3.1: Avoid and Minimize Disturbance of Wetlands and Non-Wetland Waters During Construction Activities | X |  |  |  |  | X |  |  | Page 9-46 – “measures will be incorporated into contract specifications and implemented by the construction contractor” including design facilities to avoid
Mitigation Measure VEG-3.2: Compensate for Temporary and Permanent Impacts on State- or Federally Protected Wetlands | X | [5 empty] | X |  | Page 9-47 – “mitigation will be implemented immediately following temporary impacts and concurrent with or in advance of permanent impacts”
Mitigation Measure VEG-3.3: Compensate for Temporary and Permanent Impacts on State- or Federally Protected Non-Wetland Waters | X | [5 empty] | X |  | Page 9-49 – “mitigation will be implemented immediately following temporary impacts and concurrent with or in advance of permanent impacts”
Mitigation Measure VEG-3.4: Establish Activity Exclusion Zones Around Wetlands and Non-Wetland Waters Prior to Vegetation Maintenance Activities |  |  | X |  |  |  |  | X | Page 9-50 – “Prior to Vegetation Maintenance Activities”
Mitigation Measure VEG-4-1: Avoid and Minimize Potential Adverse Effects on Oak Woodlands During Construction |  | X |  |  |  | X |  |  | Page 9-55 – “avoid impacts on oak woodlands through the establishment of activity exclusion zones, within which no ground-disturbing activities will take place, including construction staging or other temporary work areas” and “measures will also be implemented during construction of each Project component to protect and minimize effects on retained oak woodland trees”
Mitigation Measure VEG-4.2: Compensate for Adverse Effects on Oak Woodlands | X | [5 empty] | X |  | Page 9-56 – “the Authority, in coordination with Colusa County, will develop a management plan for the protection and enhancement of oak woodlands to offset the loss of oak woodlands” and “Prior to any activities that would result in permanent impacts on oak woodlands, any permanent impacts to oak woodlands will be mitigated by creating or preserving oak woodlands”
Mitigation Measure VEG-4.3: Establish Activity Exclusion Zones Around Blue Oak Woodlands in Vegetation Maintenance Areas |  |  | X |  |  |  |  | X | Page 9-57 – “Prior to vegetation maintenance activities”
Mitigation Measure WILD-1.1: Assess Habitat Suitability and Survey Suitable Habitat for Vernal Pool Branchiopods | X |  |  |  | X |  |  |  | Page 10-37 – “Once property access is granted and prior to the start of construction”
Mitigation Measure WILD-1.2: Avoid and Minimize Potential Effects on Vernal Pool Branchiopods and Western Spadefoot |  | X |  |  |  | X |  |  | Page 10-38 – not specified, during construction
Mitigation Measure WILD-1.3: Compensate for Impacts on Occupied Vernal Pool Branchiopod Habitat | X | [5 empty] | X |  | Page 10-38 – not specified, likely prior, during and post-construction
Mitigation Measure WILD-1.4: Evaluate and Survey Potential Habitat for Antioch Dunes Anthicid and Sacramento Anthicid Beetles and Implement Protective Measures | X |  |  |  | X |  |  |  | Page 10-43 (Alternative 2 only) – “prior to the start of construction of the Sacramento River discharge”
Mitigation Measure WILD-1.5: Compensate for the Loss of Occupied Antioch Dunes Anthicid and Sacramento Anthicid Beetle Habitat | X | [5 empty] | X |  | Page 10-44 (Alternative 2 only) – not specified, likely prior, during and post-construction
Mitigation Measure WILD-1.6: Conduct Surveys for Suitable Valley Elderberry Longhorn Beetle Habitat | X |  |  |  | X |  |  |  | Page 10-47 - not specified, but prior to and during construction
Mitigation Measure WILD-1.7: Fence Elderberry Shrubs to be Protected | X |  |  |  |  | X |  |  | Page 10-47 – “Elderberry shrubs in or within 165 feet of work areas that will not be removed will be protected during construction”
Mitigation Measure WILD-1.8: Transplant Permanently Affected Elderberry Shrubs and Compensate for Loss of Valley Elderberry Longhorn Beetle and its Habitat | X | [5 empty] | X |  | Page 10-48 – “Before construction begins”
Mitigation Measure WILD-1.9: Protect Special-Status Invertebrates and Their Host and Food Plants from Herbicide and Pesticide Use |  | X | [5 empty] | X | Page 10-49 – prior to use of pesticides/herbicides
Mitigation Measure WILD-1.10: Assess Habitat Suitability and Survey for Presence of Monarch Butterfly Nectar and Larval Host Plants | X |  |  |  | X |  |  |  | Page 10-52 – “No more than 3 years prior to the start of ground-disturbing activities”
Mitigation Measure WILD-1.11: Compensate for Loss of Monarch Butterfly Nectar and Larval Host Plants | X | [5 empty] | X |  | Page 10- 52 - not specified, but likely prior to, during and post-construction
Mitigation Measure WILD-1.12: Assess Habitat Suitability and Survey for Presence of Crotch Bumble Bee and Western Bumble Bee Food Plants | X |  |  |  | X |  |  |  | Page 10-56 – “No more than 3 years prior to the start of ground-disturbing activities”
Mitigation Measure WILD-1.13: Compensate for Loss of Crotch Bumble Bee and Western Bumble Bee Habitat | X | [5 empty] | X |  | Page 10-56 - not specified, likely prior, during and post-construction
Mitigation Measure WILD-1.14: Assess Habitat Suitability and Survey Suitable Habitat for Western Spadefoot, California Red-legged Frog, and Western Pond Turtle | X |  |  |  | X |  |  |  | Page 10-63 – “Once property access is granted and prior to the start of construction”
Mitigation Measure WILD-1.15: Design and Construct Wildlife Crossings for New Roadways at Suitable Locations | X |  |  |  |  | X |  |  | Page 10-64 – “Prior to final roadway design for the Project”
Mitigation Measure WILD-1.16: Monitor and Maintain Wildlife Crossings | X | [6 empty] | X | Page 10-65 – “A monitoring and maintenance plan for wildlife crossings will be developed during design of wildlife crossings” monitoring will be ongoing during construction and operation
Mitigation Measure WILD-1.17: Implement California Red-legged Frog Protective Measures |  | X | [6 empty] | Page 10-69 – “If California red-legged frog is found in the Project area either incidentally or during surveys”
Mitigation Measure WILD-1.18: Compensate for Permanent and Temporary Losses of Occupied California Red-legged Frog Aquatic and Upland Habitats | X | [5 empty] | X |  | Page 10-71 - not specified, likely prior, during and post-construction
Mitigation Measure WILD-1.19: Conduct Preconstruction Surveys for Western Pond Turtle and Monitor Initial In-Water Work | X |  |  |  |  | X |  |  | Page 10-76 – “conduct preconstruction surveys within 24 hours of the start of activities that disturb occupied or suitable western pond turtle aquatic habitat”
Mitigation Measure WILD-1.20: Implement Protective Measures for Giant Gartersnake | X |  |  |  |  | X |  |  | Page 10-80 – “when working in or near giant gartersnake habitat”
Mitigation Measure WILD-1.21: Compensate for Permanent and Temporary Losses of Giant Gartersnake Aquatic and Upland Habitats | X | [5 empty] | X |  | Page 10-81 – not specified, likely prior, during and post-construction
Mitigation Measure WILD-1.22: Conduct Vegetation Removal During the Non-Breeding Season of Nesting Migratory Birds | X |  |  |  | X |  |  |  | Page 10-88 – “during the non-breeding season for most migratory birds (generally between September 1 and January 31)”
Mitigation Measure WILD-1.23: Conduct Preconstruction Surveys for Non-Raptor Nesting Migratory Birds and Implement Protective Measures if Found | X |  |  |  |  | X |  |  | Page 10-88 – “no more than 14 days prior to the start of construction”
Mitigation Measure WILD-1.24: Conduct Surveys for Western Burrowing Owl Prior to Construction and Implement Avoidance and Minimization Measures if Found | X |  |  |  |  | X |  |  | Page 10-89 – “will conduct four surveys during the breeding season” and “if suitable habitat is present in the Project area, take avoidance (preconstruction) surveys will be conducted in the Project area (i.e., the area of ground disturbance and surrounding 500 feet) no less than 14 days prior to and 24 hours before initiating ground-disturbing activities”
Mitigation Measure WILD-1.25: Restore Temporarily Disturbed Habitat and Compensate for the Permanent Loss of Occupied Burrowing Owl Habitat |  |  | X |  |  |  | X |  | Page 10-90 – not specified, likely prior, during and post-construction
Mitigation Measure WILD-1.26: Protect Special-Status Wildlife from Rodenticide Use |  |  | X |  |  |  |  | X | Page 10-91 – not specified but prior to and during maintenance
Mitigation Measure WILD-1.27: Construct Overhead Power Lines and Associated Equipment Following Suggested Practices to Reduce Bird Collisions with Power Lines | X | [6 empty] | X | Page 10-92 – “new transmission lines and associated equipment will be properly fitted with wildlife protective devices”
Mitigation Measure WILD-1.28: Conduct Focused Surveys for Golden Eagle and Bald Eagle and Implement Protective Measures if Found | X |  |  |  |  | X |  |  | Page 10-97 – “Prior to the start of construction” and monitoring during
Mitigation Measure WILD-1.29: Compensate for the Loss of Eagle Nest Trees | X |  |  |  | X |  |  |  | Page 10-98 – “Prior to the start of construction”
Mitigation Measure WILD-1.30: Conduct Focused Surveys for Nesting Swainson’s Hawk, White-tailed Kite, and Other Raptors Prior to Construction and Implement Protective Measures During Construction | X |  |  |  |  | X |  |  | Page 10-105 – “Surveys will generally be conducted from February to July”
Mitigation Measure WILD-1.31: Compensate for the Permanent Loss of Foraging Habitat for Swainson’s Hawk and White-tailed Kite | X | [5 empty] | X |  | Page 10-106 - not specified, likely prior, during and post-construction
Mitigation Measure WILD-1.32: Conduct Surveys and Implement Protection Measures for Special-Status Bat Species Prior to Building/Structure Demolition | X |  |  |  |  | X |  |  | Page 10-128 – “Prior to building/structure demolition”; “buildings/structures where bats are confirmed to be present will not be demolished during the maternity season (generally assumed to be between April 15 and August 15 for this Project) or the hibernation season (generally from November 1 to March 1)”; “Removal of occupied roosting habitat will be conducted only following the maternity season and prior to hibernation, generally between August 16 and October 31” and “Installation of exclusion devices will be conducted only before maternity colonies establish (generally after March 1) or after they disperse (generally August 15 to October 31)”
Mitigation Measure WILD-1.33: Conduct Surveys and Implement Protection Measures for Special-Status Bat Species Prior to Tree Trimming and Removal | X |  |  |  |  | X |  |  | Page 10-129 – “Prior to tree trimming or removal… Because of the limited timeframe for tree removal (September 15 to October 31), the tree habitat assessment should be conducted early enough to provide information to inform tree removal planning”
Mitigation Measure WILD-1.34: Compensate for Permanent Impacts on Occupied Roosting Habitat | X | [5 empty] | X |  | Page 10-130 - not specified, likely prior, during and post-construction
Mitigation Measure WILD-1.35: Implement Protective Measures to Avoid and Minimize Potential Impacts on American Badger |  | X |  |  |  | X |  |  | Page 10-135 – “preconstruction survey will be conducted no less than 14 days and no more than 30 days before the beginning of ground disturbance” and “For potentially occupied dens, a 50-foot exclusion zone will be applied around the den; for occupied dens, a 100-foot exclusion zone will be applied around the den … and will remain in place throughout the pup-rearing season (February 15 through July 1)”
Mitigation Measure FISH-2.1: Wilkins Slough Flow Protection Criteria |  |  |  | X |  |  |  | X | Page 11-131 – “during March through May of all water year types if…”
Mitigation Measure FISH-8.1: Prevent Detrimental Dissolved Oxygen and Water Temperature Effects to Fish Associated with Moving Colusa Basin Drain Water Through the Yolo Bypass |  |  |  | X |  |  |  | X | Page 11-266 – “when Project releases are made via the Dunnigan Pipeline to the Yolo Bypass DO and water temperature will be measured at 15-minute intervals… Measurements of DO and water temperature will occur before and during the period of CBD discharge to the Yolo Bypass”
Mitigation Measure FISH-9.1: Tidal Habitat Restoration for Longfin Smelt | [7 empty] | X | Page 11-275 – not specified
Mitigation Measure GEO-7.1: Retain a Qualified Paleontological Resource Specialist Prior to the Start of Construction | X |  |  |  | X |  |  |  | Page 12-61 – “The Authority will retain a qualified Paleontological Resource Specialist once the construction footprint can be accessed and the engineering design is at sufficient level of detail but at least 90 days prior to the start of construction.” | At least 90-days prior to each phase of construction | Reservoir, TRR and any deep excavations
Mitigation Measure GEO-7.2: Consultation with the Paleontological Resource Specialist Prior to and During Project Construction | X |  |  |  |  | X |  |  | Page 12-62 – “At least 30 days prior to the start of construction, the Authority will provide maps or drawings to the Paleontological Resource Specialist that show the planned construction footprint” and “If construction proceeds in phases, maps and drawings may be submitted prior to the start of each phase” | At least 90-days prior to each phase of construction | Reservoir, TRR and any deep excavations
Mitigation Measure GEO-7.3: Prepare and Implement a Paleontological Resources Monitoring and Mitigation Plan | X |  |  |  |  | X |  |  | Page 12-62 – “Once the construction footprint can be accessed and the engineering design is at sufficient level of detail, the Authority will prepare a PRMMP” | At least 90-days prior to each phase of construction | Reservoir, TRR and any deep excavations
Mitigation Measure GEO-7.4: Conduct Monitoring During Project Construction and Prepare Monthly Reports |  | X |  |  |  |  | X |  | Page 12-63 – “During Project Construction”
Mitigation Measure GEO-7.5: Ensure Implementation of the Paleontological Resources Monitoring and Mitigation Plan |  | X |  |  |  |  | X |  | Page 12-64 – “during construction”
Mitigation Measure AG-1.1: Purchase Agricultural Conservation Easements to Preserve Regional Important Farmland | X | [6 empty] | X | Page 15-19 – “Prior to the commencement of any Project activities that would result in the permanent conversion of Important Farmland” | Recommend starting this process at least a year before construction given need to comparable land and negotiate purchase of easements | Most areas - where agricultural use will be permanently coverted
Mitigation Measure AG-2.1: Minimize Impacts on Williamson Act-Contracted Lands, Comply with Government Code Sections 51290–51293, and Coordinate with Landowners and Agricultural Operators | X |  |  |  |  | X |  |  | Page 15-26 – “Whenever it appears that land within a preserve or under contract may be required for a public improvement, DOC and the local jurisdiction responsible for administering the preserve must be notified” | Recommend this be implemented as part of land acquisition process | In areas of Williamson Act contracts
Mitigation Measure AQ-1.1: Zero Emission and/or Near Zero Emission Vehicles and Off-Road equipment | X |  |  |  |  | X |  |  | Page 20-33 – “the Authority will require that construction contractors provide documentation to the Authority, on an annual basis at minimum, showing the percentage of vehicles and equipment that are ZE or NZE” | Before and during construction of all phases | All construction packages
Mitigation Measure AQ-1.2: Offset Construction and Operation-Generated Criteria Pollutants in CCAPCD, GCAPCD, and YSAQMD |  |  | X |  |  |  |  | X | Page 20-34 – “Prior to issuance of construction contracts, the Authority will enter into a memorandum or multiple memoranda of understanding (MOU) with CCAPCD, GCAPCD, YSAQMD, TCAPCD, or other air district located in the SVAB (collectively referred to as the Air Districts), to reduce NOX and PM10” |  | F- Permitting | $100K
Mitigation Measure AQ-2.1: Recreational Boat Emissions Minimization Plan | X | [6 empty] | X | Page 20-38- “the Authority will develop and implement an emissions reduction plan… that the Authority will implement during the operational lifetime of the recreational area at the reservoir ... The plan will be part of the Recreation Management Plan (Section 2D.8) and thus approved at the same time as the Recreation Management Plan” | Prior to opening recerational boating to public | Reservor - recreation areas
Mitigation Measure AQ-2.2: Offset Operation-Generated Criteria Pollutants in CCAPCD and GCAPCD |  |  |  | X |  |  |  | X | Page 20-38- “Prior to issuance of the commencement of recreational boating activities, the Authority will enter into a memorandum or multiple memoranda of understanding (MOU) with CCAPCD, GCAPCD, YSAQMD, TCAPCD, or other air district”
Mitigation Measure GHG-1.1: Achieve Net-Zero Emissions Through a GHG Reduction Plan | X | [7 empty] | Page 21-24 – “The Authority will prepare the GHG Reduction Plan prior to issuance of the first construction or grading permit for the Project. For Project operations, the GHG Reduction Plan will be prepared prior to the end of construction and prior to the start of the next five-year phase of operations.” | Before and during construction of all phases if equipment changes | All construction packages
Mitigation Measure CUL-1.1: Identify Significant Built Resources | X |  |  |  | X |  |  |  | Page 22-30 – “will be completed prior to construction”
Mitigation Measure CUL-1.2: Avoid Significant Built Resources | X |  |  |  |  | X |  |  | Page 22-30 – “implement feasible Project construction protocols to avoid significant historic built resources, including workers’ cultural resources sensitivity training, prior to and during construction activities”
Mitigation Measure CUL-1.3: Protect Significant Built Resources |  | X | [5 empty] | X | Page 22-30 – “develop feasible protection measures for significant historic built resources prior to and during construction activities and during operation activities.”
Mitigation Measure CUL-1.4: Significant Historic Built Resources Treatment | X | [5 empty] | X |  | Page 22-31 – “Prior to construction” and “implement the treatment plans prior to and during construction, and following construction, depending on the details of the resource-specific treatment”
Mitigation Measure CUL-2.1: Identify Significant Archaeological Resources | X |  |  |  |  | X |  |  | Pages 22-36 and 22-37 – all steps to be implemented prior to construction
Mitigation Measure CUL-2.2: Avoid Significant Archaeological Resources | X | [6 empty] | X | Page 22-37 – “design changes will be implemented to avoid significant archaeological resources” and “have a familiarity of the resource locations and identifications so that future operations or changes in operations can avoid those resources”
Mitigation Measure CUL-2.3: Protect Significant Archaeological Resources |  | X | [5 empty] | X | Page 22-37 – “develop feasible Project protection of significant archaeological resources during construction and operations”
Mitigation Measure CUL-2.4: Significant Archaeological Resources Treatment | X | [6 empty] | X | Page 22-38 – not specified but develop before and implement during construction and operation
Mitigation Measure CUL-3.1: Cemetery Relocation Plan | X |  |  |  | X |  |  |  | Page 22-42 - not specified but prior to construction in the inundation footprint
Mitigation Measure CUL-3.2: Avoid, Protect, and Treat Human Burials | X | [6 empty] | X | Page 22-42 – “avoid and protect any human remains encountered during pre-construction, construction, post-construction, operations, and maintenance”
Mitigation Measure TCR-1.1: Implement Mitigation Measures Recommended in Public Resources Code Section 21084.3 to Avoid Damaging Effects on Tribal Cultural Resources | X | [6 empty] | X | Page 23-15 – “planning and construction to avoid” and “Permanent conservation easements”
Mitigation Measure TCR-1.2: Tribal Monitoring |  | X |  |  |  | X |  |  | Page 23-16 – during “all ground-disturbing activities”
Mitigation Measure TCR-1.3: Implement Agreed-Upon Protocol for the Treatment of Human Remains and Cultural Items |  | X | [5 empty] | X | Page 23-17 – “If human remains or associated grave goods are discovered”