## RE Reprioritized 02172023
Exploration Name | Exploration Type | Table_Source | Location | Objective | Completion Detail | APN | County | Schedule Work Package 1-08/22 to 12/31/22 Work Package 2-1/23 to 6/30/23 Work Package 3-7/1/23 to 12/31/23 Work Package 4-1/24 to 12/31/24 Work Package 5 - 2023-2024, Priority points completed if access is provided; PIO items shown in this package are not funded in AM3. | Potential Eagle Impact Area Work Window Sept-Dec 30 | Potential GGS Habitat Work Window Nov-March 30 | Jan Inside Funks | PG&E Pipeline Inspector Needed | Needs to be cleared by GCID | RWQCB, USFW Permit Required | Completed | Notes
SB-TP-008 | TP | Core Borrow | Sites Dam Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-173-001-000 | Colusa | HOLD | X | [6 empty] | no access to this location will be currently provided
D-B-001a | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 1 | [6 empty] | X
D-B-001g | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 1 | [6 empty] | X
HM-B-029 | Auger | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Grout | No APN - Road | Colusa | Work Package 1 | [6 empty] | X
MD-B-001b | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 1 | [6 empty] | X
MD-B-001f | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 1 | [6 empty] | X
MD-B-001j | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 1 | [6 empty] | X
MD-B-001n | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 1 | [6 empty] | X
MD-B-001p | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 1 | [6 empty] | X
MD-B-005 | Auger | Roads | South side of box culvert | Design recommendations for box culvert replacement | Grout | No APN - Road | Colusa | Work Package 1 |  | X |  |  |  |  | X
MD-B-006d | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 1 |  | X |  |  |  |  | X
MD-B-006h | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 1 |  | X |  |  |  |  | X
MS-B-001d | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 1 |  |  |  | X |  |  | X
MS-B-001j | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 1 | [6 empty] | X
MS-B-001p | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 1 | [6 empty] | X
MS-B-002 | RW-Core | Roads | East side of bridge | Design recommendations for bridge replacement | Grout | No APN - Road | Colusa | Work Package 1 |  |  |  | X | X |  | X
MS-B-004c | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 1 | [6 empty] | X
MS-B-004g | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 1 | [6 empty] | X
MS-B-004m | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 1 | X | [5 empty] | X
MS-B-006 | RW-Core | Roads | West side of bridge | Design recommendations for bridge replacement | Grout | No APN - Road | Colusa | Work Package 1 | [6 empty] | X
S-B-006 | RW-Core | Sites Dam | US Channel | Far-field conditions | Piezometer | No APN - Road | Colusa | Work Package 1 | X
S-B-007 | RW-Core | Sites Dam | Sites Dam | Channel, Foundation depth | Grout | No APN - Road | Colusa | Work Package 1 | X | [5 empty] | X
S-B-008 | RW-Core | Sites Dam | Sites Dam | Channel, Foundation depth | Piezometer | No APN - Road | Colusa | Work Package 1 | X | [5 empty] | X
S-B-009 | RW-Core | Sites Dam | Sites Dam | Channel, Foundation depth | Grout | No APN - Road | Colusa | Work Package 1 | X | [5 empty] | X
S-B-010 | RW-Core | Sites Dam | Channel | Foundation depth, grout curtain depth | Grout | No APN - Road | Colusa | Work Package 1 | X | [5 empty] | X
SB-B-001 | Auger | Core Borrow | Sites Dam Borrow | Explore core borrow quantity and properties. | Piezometer | No APN - Road | Colusa | Work Package 1 | X | [5 empty] | X
SL-B-025c | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 1 | [6 empty] | X
S-SR-008 | SR | Channel | Sites Dam | Crest Centerline, Foundation depth | Not Applicable | No APN - Road | Colusa | Work Package 1 | X | [5 empty] | X
NA-B-001 | RW-Core | Roads | East side of bridge | Design recommendations for bridge replacement | Grout | No APN - Road | Glenn | Work Package 1 | [6 empty] | X
NA-B-003e | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Glenn | Work Package 1 | [6 empty] | X
NA-B-003i | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Glenn | Work Package 1 | [6 empty] | X
R68-B-001c | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Glenn | Work Package 1 |  | X |  |  |  |  | X
R68-B-001g | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Glenn | Work Package 1 |  | X |  |  |  |  | X
R68-B-001k | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Glenn | Work Package 1 |  | X |  |  |  |  | X
R68-B-002 | Auger | Roads | East side of box culvert | Design recommendations for box culvert replacement | Grout | No APN - Road | Glenn | Work Package 1 |  | X |  |  |  |  | X
R68-B-005 | Auger | Roads | West side of box culvert | Design recommendations for box culvert replacement | Grout | No APN - Road | Glenn | Work Package 1 |  | X |  |  |  |  | X
R69-B-001 | RW-Core | Roads | East side of bridge | Design recommendations for bridge replacement | Grout | No APN - Road | Glenn | Work Package 1 |  | X |  |  | X |  | X
R69-B-003a | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Glenn | Work Package 1 |  | X |  |  |  |  | X
R69-B-003c | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Glenn | Work Package 1 |  | X |  |  |  |  | X
R69-B-003e | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Glenn | Work Package 1 | [6 empty] | X
R69-B-003k | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Glenn | Work Package 1 | [6 empty] | X
RD-B-002 | Auger | Roads | South side of box culvert | Design recommendations for box culvert replacement | Grout | No APN - Road | Glenn | Work Package 1 |  | X |  |  |  |  | X
RD-B-005 | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Glenn | Work Package 1 |  | X |  |  |  |  | X
FNK-B-015 | Auger/Core | FNK | Funks | Stratigraphy; PGP foundation; substation | Grout | 011-190-001-000 | Colusa | Work Package 2.01 | [6 empty] | X
FNK-B-016 | Auger/Core | FNK | Funks | Stratigraphy; PGP foundation; substation | Grout | 011-190-001-000 | Colusa | Work Package 2.01 | [6 empty] | X
FNK-B-025 | Auger/Core | FNK | Funks | Substation foundations, upland area | Grout | 011-190-001-000 | Colusa | Work Package 2.01 | [6 empty] | X
Funks RES Survey FNK-B-016 | RES | FNK | Funks | Stratigraphy; PGP foundation; substation | Not Applicable | 011-190-001-000 | Colusa | Work Package 2.01 | [6 empty] | X
TRR-B-021 | Auger/Core | TRR | TRR Pipeline | TRR Pipeline trenchless crossing design at TC Canal | Grout | 011-190-002-000 | Colusa | Work Package 2.01 | [6 empty] | X
TRR-B-022 | Auger/Core | TRR | TRR Pipeline | TRR Pipeline trenchless crossing design at TC Canal | Grout | 011-190-002-000 | Colusa | Work Package 2.01 | [6 empty] | X
FNK-G-001 | Geologic Mapping | FNK | Funks | Strike/Dip Measurements, Geology mapping | Not Applicable | 011-190-001-000, 011-190-002-000 | Colusa | Work Package 2.02
FNK-G-002 | Geologic Mapping | FNK | Funks | Strike/Dip Measurements, Geology mapping | Not Applicable | 011-190-002-000 | Colusa | Work Package 2.02
TRW-C-025 | CPT | TRW | TRR Pipeline | Inlet/outlet connection to GCID; ground improvement; GCID plug design (also for TRRE) | Grout | GCID Canal APN | Colusa | Work Package 2.03 |  | X |  |  | X
TRW-C-029 | CPT | TRW | TRRW | Inlet/outlet connection to GCID; ground improvement; TRRE bridge foundation | Grout | GCID Canal APN | Colusa | Work Package 2.03 |  | X |  |  | X
HM-B-002b | Auger | Roads | along roadway | For design recommendations of fill, culvert and structural section. | Grout | 014-090-021-000 | Colusa | Work Package 2.03 | [7 empty] | is being relocated to the east outside of a water feature
TRR-B-023 | Auger/Core | TRR | TRR Pipeline | Transmission tower foundation design | Grout | 011-190-001-000 | Colusa | Work Package 2.03 | [7 empty] | area needs to dry out more before attempting access
TRR-B-025 | Auger/Core | TRR | TRR Pipeline | Transmission tower foundation design | Grout | 011-190-002-000 | Colusa | Work Package 2.03 | [7 empty] | access to areas needs a fence removed and area needs to dry out
IO-B-S-04 | RW-Core | Inlet-Outlet | IO Tower | Tunnel STA 17+00,Tunnel liner design; 2 tunnel Ø below invert | Grout | 011-150-022-000 | Colusa | Work Package 2.04 | X
IO-B-S-05 | RW-Core | Inlet-Outlet | IO Tower | Downstream portal design; 2 tunnel Ø below invert | Grout | 011-150-022-000 | Colusa | Work Package 2.04 | X
S-B-004 | RW-Core | Sites Dam | Sites Dam | Channel/Left Abutment, Foundation depth, grout curtain depth | Grout |  | Colusa | Work Package 2.04 | X
S-B-011b | RW-Core | Sites Dam | Sites Dam | Channel, Foundation depth, grout curtain depth, bedding | Grout |  | Colusa | Work Package 2.04 | X
S-B-107 | RW-Core | Sites Dam | Left Abutment | Foundation depth, grout curtain depth | Grout | 011-150-022-000 | Colusa | Work Package 2.04 | X
S-B-111 | RW-Core | Sites Dam | Left Abutment/Channel | Foundation depth | Grout | 011-150-022-000 | Colusa | Work Package 2.04 | X
S-Mapping | Geologic Mapping | Fault Study | Sites Dam | Evaluate geologic hazards and geotechnical properties to support dam study, as well as PSHA and FDHA (build on existing Q mapping and bedrock stratigraphic markers). Established detailed structure, faulting, landsliding, and Q map | Not Applicable | 011-150-021-000, 011-150-022-000 | Colusa | Work Package 2.04 | X
SQ-TP-001 | TP | Rock Quarries | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-150-022-000 | Colusa | Work Package 2.04 | X
S-SR-001 | SR | Sites Dam | Sites Dam | Crest Centerline, Foundation depth | Not Applicable | 011-150-021-000, 011-150-022-000 | Colusa | Work Package 2.04 | X
S-SR-002 | SR | US Toe | Sites Dam | Foundation depth | Not Applicable | 011-150-021-000, 011-150-022-000 | Colusa | Work Package 2.04 | X
S-SR-003 | SR | Sites Dam | Sites Dam | US Mid Slope, Foundation depth | Not Applicable | 011-150-021-000, 011-150-022-000 | Colusa | Work Package 2.04 | X
S-SR-004 | SR | Sites Dam | Sites Dam | DS Mid Slope, Foundation depth | Not Applicable | 011-150-021-000, 011-150-022-000 | Colusa | Work Package 2.04 | X
S-SR-005 | SR | DS Toe | Sites Dam | Foundation depth | Not Applicable | 011-150-021-000, 011-150-022-000 | Colusa | Work Package 2.04 | X
S-SR-006 | SR | Sites Dam | Sites Dam | Left Abutment, Foundation depth | Not Applicable | 011-150-022-000 | Colusa | Work Package 2.04 | X
FNK-P-003 | TP | FNK | Funks | Stratigraphy; material properties, CLSM compatability, excavatability | Backfill | 011-150-004-000 | Colusa | Work Package 2.04
SL-B-001d | PC | Roads | Along planned roadway (TBD) | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | 011-150-012-000 | Colusa | Work Package 2.04
SL-B-001f | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | 011-150-012-000 | Colusa | Work Package 2.04
SL-B-010 | Auger | Roads | Along roadway | For design recommendations of cuts, fills and structural section. | Grout | 011-150-004-000 | Colusa | Work Package 2.04
SL-B-012 | Auger | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Grout | 011-150-012-000 | Colusa | Work Package 2.04
SQ-B-002 | RW-Core | Rock Quarries | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 011-150-012-000 | Colusa | Work Package 2.04
SQ-B-008 | RW-Core | Rock Quarries | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Piezometer | 011-150-012-000 | Colusa | Work Package 2.04 | X
SQ-B-011 | RW-Core | Rock Quarries | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 011-150-012-000 | Colusa | Work Package 2.04 | X
SQ-D-001a | D | Dozer line | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-150-012-000 | Colusa | Work Package 2.04 | X
SQ-SR-001 | SR | Sites Dam Quarry | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Charactoristics | Not Applicable | 011-150-012-000, 011-150-010-000 | Colusa | Work Package 2.04 | X
SQ-SR-002 | SR | Sites Dam Quarry | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Charactoristics | Not Applicable | 011-150-012-000, 011-150-010-000 | Colusa | Work Package 2.04 | X
SQ-SR-003 | SR | Sites Dam Quarry | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Charactoristics | Not Applicable | 011-150-012-000 | Colusa | Work Package 2.04 | X
SQ-SR-004 | SR | Sites Dam Quarry | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Charactoristics | Not Applicable | 011-150-012-000 | Colusa | Work Package 2.04 | X
SQ-SR-005a | SR | Sites Dam Quarry | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Charactoristics | Not Applicable | 011-150-012-000 | Colusa | Work Package 2.04
SQ-TP-007 | TP | Rock Quarries | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-150-012-000 | Colusa | Work Package 2.04 | X
SQ-TP-010 | TP | Rock Quarries | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-150-012-000 | Colusa | Work Package 2.04
S-B-011a | RW-Core | Sites Dam | Sites Dam | Channel, Foundation depth, grout curtain depth | Piezometer |  | Colusa | Work Package 2.05 | X
S-SR-007 | SR | Right Abutment | Sites Dam | Foundation depth | Not Applicable | 011-150-021-000 | Colusa | Work Package 2.05 | X
S-T-002 | T | Fault Study | Sites Dam | Confirm location, Age, Width, Style, Length of Flting S-2 for Seismic Design Considerations | Backfill | 011-150-022-000 | Colusa | Work Package 2.05 | X
SB-TP-009 | TP | Core Borrow | Sites Dam Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | Colusa County APN | Colusa | Work Package 2.05 | X
IO-T-002 | T | Fault Study | I/O (Golden Gate) | Confirm Location of Fault S3 doesn't intersect Portal | Backfill | 011-150-004-000 | Colusa | Work Package 2.05
SL-B-001b | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | 011-200-006-000 | Colusa | Work Package 2.4
S-B-005 | RW-Core | Sites Dam | US Right Abutment | Landslide Investigation | Piezometer | 011-150-021-000 | Colusa | Work Package 2.x | X | [6 empty] | access to the location is uncertain until we are able to visit site
S-B-015a | RW-Core | Sites Dam | Sites Dam | Right Abutment, Foundation depth, grout curtain depth | Piezometer | 011-150-021-000 | Colusa | Work Package 2.x | X | [6 empty] | access to the location is uncertain until we are able to visit site
S-B-015b | RW-Core | Sites Dam | Sites Dam | Right Abutment, Foundation depth, grout curtain depth, bedding | Grout | 011-150-021-000 | Colusa | Work Package 2.x | X | [6 empty] | access to the location is uncertain until we are able to visit site
S-B-108 | RW-Core | Sites Dam | Right Abutment | Foundation depth, grout curtain depth | Grout | 011-150-021-000 | Colusa | Work Package 2.x | X | [6 empty] | access to the location is uncertain until we are able to visit site
S-B-110 | RW-Core | Sites Dam | Right Abutment | Foundation depth, grout curtain depth | Grout | 011-150-021-000 | Colusa | Work Package 2.x | X | [6 empty] | access to the location is uncertain until we are able to visit site
S-T-001 | T | Fault Study | Sites Dam | Confirm location, Age, Width, Style, Length of Flting S-2 for Seismic Design Considerations | Backfill | 011-150-021-000 | Colusa | Work Package 2.x | X | [6 empty] | access to the location is uncertain until we are able to visit site
TRR-B-026 | Auger/Core | TRR | TRR Pipeline | Transmission tower foundation design, TRR pipeline | Grout | 011-190-015-000 | Colusa | Work Package 3.07
TRW-B-014 | Auger/Core | TRW | TRRW | Paired with TRW-C-019; Stratigraphy; cut stability/seepage; geologic contact; borrow eval; transmission tower foundation design | Grout | 011-190-033-000 | Colusa | Work Package 3.07
TRW-B-016 | Auger/Core | TRW | TRRW | Stratigraphy; cut stability/seepage, borrow evaluation; transmission tower foundation design | Grout | 011-190-030-000 | Colusa | Work Package 3.07
TRW-B-018 | Auger/Core | TRW | TRRW | Stratigraphy; cut stability/seepage; borrow evaluation | Grout | 011-190-030-000 | Colusa | Work Package 3.07
TRW-B-020 | Auger | TRW | TRRW | Stratigraphy; cut stability/seepage; borrow evaluation | Grout | 011-190-030-000 | Colusa | Work Package 3.07
TRW-B-022 | Auger | TRW | TRRW | Stratigraphy; cut stability/seepage; borrow evaluation | Grout | 011-190-030-000 | Colusa | Work Package 3.07
TRW-B-037 | Auger/Core | TRW | TRW | Stratigraphy; cut stability/seepage, borrow evalaution | Piezometer | 011-190-015-000 | Colusa | Work Package 3.07
TRW-C-012 | Seismic CPT | TRW | TRRW | Paired with TRW-B-012; Stratigraphy; cut stability, seepage; geologic contact | Grout | 011-190-033-000 | Colusa | Work Package 3.07
TRW-C-018 | CPT | TRW | TRRW | Stratigraphy; cut stability, seepage; geologic contact | Grout | 011-190-033-000 | Colusa | Work Package 3.07
TRW-C-019 | CPT | TRW | TRRW | Paired with TRW-B-014; Stratigraphy; cut stability, seepage; geologic contact; transmission tower foundation | Grout | 011-190-033-000 | Colusa | Work Package 3.07
GG-B-034 | RW-Core | Golden Gate Dam | Saddle Dam, Channel | Foundation depth | Grout | 011-130-009-000 | Colusa | Work Package 3.07
GGB-B-013 | Auger | Core Borrow | Golden Gate Dam Borrow | Explore core borrow quantity and properties. | Grout | 011-130-009-000 | Colusa | Work Package 3.07
GGB-TP-012 | TP | Core Borrow | Golden Gate Dam Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-130-009-000 | Colusa | Work Package 3.07
GGB-TP-013 | TP | Core Borrow | Golden Gate Dam Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-130-009-000 | Colusa | Work Package 3.07
GGB-TP-014 | TP | Core Borrow | Golden Gate Dam Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-130-009-000 | Colusa | Work Package 3.07
GGB-TP-016 | TP | Core Borrow | Golden Gate Dam Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-130-009-000 | Colusa | Work Package 3.07
GGB-TP-018 | TP | Core Borrow | Golden Gate Dam Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-130-009-000 | Colusa | Work Package 3.07
GGB-TP-019 | TP | Core Borrow | Golden Gate Dam Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-130-009-000 | Colusa | Work Package 3.07
GGB-TP-021 | TP | Core Borrow | Golden Gate Dam Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-130-009-000 | Colusa | Work Package 3.07
GGB-TP-022 | TP | Core Borrow | Golden Gate Dam Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-130-009-000 | Colusa | Work Package 3.07
GGB-TP-023 | TP | Core Borrow | Golden Gate Dam Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-130-009-000 | Colusa | Work Package 3.07
GG-Mapping-2 | Geologic Mapping | Fault Study | Golden Gate Dam (Saddle Dam Area) | Evaluate geologic hazards and geotechnical properties to support dam study, as well as PSHA and FDHA (build on existing Q mapping and bedrock stratigraphic markers). Established detailed structure, faulting, landsliding, and Q map | Not Applicable | 011-130-009-000 | Colusa | Work Package 3.07
GG-SR-010 | SR | GG Dam | Golden Gate Dam | Saddle Dam Section, Foundation depth | Not Applicable | 011-130-009-000 | Colusa | Work Package 3.07
IO-B-GG-02 | RW-Core | Inlet-Outlet | IO Tower | Tunnel Sta 25+00, Tunnel liner design; 2 tunnel Ø below invert | Grout | 011-150-003-000 | Colusa | Work Package 3.07
IO-B-GG-03 | RW-Core | Inlet-Outlet | IO Tower | Tunnel Sta 30+00, Tunnel liner design; 2 tunnel Ø below invert | Piezometer | 011-150-003-000 | Colusa | Work Package 3.07
IO-GG-Mapping-1a | Geologic Mapping | Fault Study | I/O (Golden Gate) | Evaluate geologic hazards and geotechnical properties to support dam study, as well as PSHA and FDHA (build on existing Q mapping and bedrock stratigraphic markers). Established detailed structure, faulting, landsliding, and Q map | Not Applicable | 011-150-003-000 | Colusa | Work Package 3.07
IO-T-001 | T | Fault Study | I/O (Golden Gate) | Confirm GG-F2 fault location, width and kinematics; assess age of absence of faulting (location will be based on detailed mapping and air photo analysis) | Backfill | 011-150-003-000 | Colusa | Work Package 3.07
IO-T-003 | T | Fault Study | I/O (Golden Gate) | Confirm Location of Fault GG2 to evaluate southwest projection and to determine if fault ends north of IO for tunnel relocation | Backfill | 011-150-003-000 | Colusa | Work Package 3.07
IO-B-S-01 | RW-Core | Inlet-Outlet | IO Tower | Upstream portal design; 2 tunnel Ø below invert | Grout | 011-150-010-000 | Colusa | Work Package 3.09 | X
IO-B-S-02 | RW-Core | Inlet-Outlet | IO Tower | Tunnel STA 8+00, Tunnel liner design; 2 tunnel Ø below invert | Grout | 011-150-010-000 | Colusa | Work Package 3.09 | X
S-B-001a | RW-Core | Sites Dam | Sites Dam | Left Abutment, Foundation depth, grout curtain depth | Grout | 011-150-010-000 | Colusa | Work Package 3.09 | X
S-B-001b | RW-Core | Sites Dam | Sites Dam | Left Abutment, Foundation depth, grout curtain depth, bedding | Grout | 011-150-010-000 | Colusa | Work Package 3.09 | X
S-Mapping | Geologic Mapping | Fault Study | Sites Dam | Evaluate geologic hazards and geotechnical properties to support dam study, as well as PSHA and FDHA (build on existing Q mapping and bedrock stratigraphic markers). Established detailed structure, faulting, landsliding, and Q map | Not Applicable | 011-150-010-000 | Colusa | Work Package 3.09 | X
SQ-B-013 | RW-Core | Rock Quarries | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Piezometer | 011-150-010-000 | Colusa | Work Package 3.09 | X
SQ-SR-001 | SR | Sites Dam Quarry | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Charactoristics | Not Applicable | 011-150-010-000 | Colusa | Work Package 3.09 | X
SQ-SR-002 | SR | Sites Dam Quarry | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Charactoristics | Not Applicable | 011-150-010-000 | Colusa | Work Package 3.09 | X
SQ-TP-002 | TP | Rock Quarries | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-150-010-000 | Colusa | Work Package 3.09 | X
SQ-TP-003 | TP | Rock Quarries | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-150-010-000 | Colusa | Work Package 3.09 | X
SQ-TP-004 | TP | Rock Quarries | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-150-010-000 | Colusa | Work Package 3.09 | X
S-SR-001 | SR | Sites Dam | Sites Dam | Crest Centerline, Foundation depth | Not Applicable | 011-150-010-000 | Colusa | Work Package 3.09 | X
S-SR-002 | SR | US Toe | Sites Dam | Foundation depth | Not Applicable | 011-150-010-000 | Colusa | Work Package 3.09 | X
S-SR-003 | SR | Sites Dam | Sites Dam | US Mid Slope, Foundation depth | Not Applicable | 011-150-010-000 | Colusa | Work Package 3.09 | X
S-SR-004 | SR | Sites Dam | Sites Dam | DS Mid Slope, Foundation depth | Not Applicable | 011-150-010-000 | Colusa | Work Package 3.09 | X
FNK-G-002 | Geologic Mapping | FNK | Funks | Strike/Dip Measurements, Geology mapping | Not Applicable | 011-140-012-000 | Colusa | Work Package 3.09
FNK-B-026 | Auger/Core | FNK | Funks | Funks Pipeline Design, deep section | Grout | 011-150-018-000 | Colusa | Work Package 3.oct
GG-B-004a | RW-Core | Golden Gate Dam | Golden Gate Dam | Right Abutment/Centerline, Foundation depth, grout curtain depth | Piezometer | 011-130-011-000 | Colusa | Work Package 3.oct
GG-B-004b | RW-Core | Golden Gate Dam | Golden Gate Dam | Right Abutment/Centerline, Grout curtain depth, bedding angle | Grout | 011-130-011-000 | Colusa | Work Package 3.oct
GG-B-008 | RW-Core | Golden Gate Dam | Golden Gate Dam | Channel, Foundation depth, grout curtain depth | Grout | 011-130-011-000 | Colusa | Work Package 3.oct
GG-B-013a | RW-Core | Golden Gate Dam | Golden Gate Dam | Channel/Centerline, Foundation depth, grout curtain depth | Grout | 011-130-011-000 | Colusa | Work Package 3.oct | X
GG-B-013b | RW-Core | Golden Gate Dam | Golden Gate Dam | Channel/Centerline, Grout curtain depth, bedding angle | Grout | 011-130-011-000 | Colusa | Work Package 3.oct | X
GG-B-015a | RW-Core | Golden Gate Dam | Golden Gate Dam | Left Abutment/Centerline, Foundation depth, grout curtain depth | Grout | 011-130-011-000 | Colusa | Work Package 3.oct | X
GG-B-015b | RW-Core | Golden Gate Dam | Golden Gate Dam | Left Abutment/CenterlineGrout curtain depth, bedding angle | Grout | 011-130-011-000 | Colusa | Work Package 3.oct | X
GG-B-025 | RW-Core | Golden Gate Dam | Golden Gate Dam | US Ridge permeability | Grout | 011-130-011-000 | Colusa | Work Package 3.oct
GG-B-030 | RW-Core | Golden Gate Dam | Golden Gate Dam | Saddle Dam, Left Abutment/Centerline, Foundation Depth, ridge permeability, grout curtain depth | Grout | 011-130-011-000 | Colusa | Work Package 3.oct
GG-B-033 | RW-Core | Golden Gate Dam | Golden Gate Dam | Saddle Dam, Right Abutment/Centerline, Foundation depth, grout curtain depth | Piezometer | 011-130-011-000 | Colusa | Work Package 3.oct
GG-B-036 | RW-Core | Golden Gate Dam | Golden Gate Dam | Saddle Dam, US Toe, Foundation depth, far-field conditions | Piezometer | 011-130-011-000 | Colusa | Work Package 3.oct
GG-Mapping-1 | Geologic Mapping | Fault Study | Golden Gate Dam | Evaluate geologic hazards and geotechnical properties to support dam study, as well as PSHA and FDHA (build on existing Q mapping and bedrock stratigraphic markers). Established detailed structure, faulting, landsliding, and Q map | Not Applicable | 011-130-011-000 | Colusa | Work Package 3.oct | X
GG-Mapping-2 | Geologic Mapping | Fault Study | Golden Gate Dam (Saddle Dam Area) | Evaluate geologic hazards and geotechnical properties to support dam study, as well as PSHA and FDHA (build on existing Q mapping and bedrock stratigraphic markers). Established detailed structure, faulting, landsliding, and Q map | Not Applicable | 011-130-011-000 | Colusa | Work Package 3.oct
GGQ-B-010 | RW-Core | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Piezometer | 011-130-004-000 | Colusa | Work Package 3.oct
GGQ-B-012 | RW-Core | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 011-130-004-000 | Colusa | Work Package 3.oct
GGQ-SR-001 | SR | GG Quarry | Golden Gate Dam Z3Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Charactoristics | Not Applicable | 011-130-004-000 | Colusa | Work Package 3.oct
GGQ-SR-003a | SR | GG Quarry | Golden Gate Dam Z3Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Charactoristics | Not Applicable | 011-130-011-000 | Colusa | Work Package 3.oct
GGQ-SR-004 | SR | GG Quarry | Golden Gate Dam Z3 Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Charactoristics | Not Applicable | 011-130-004-000 | Colusa | Work Package 3.oct
GG-SR-001 | SR | GG Dam | Golden Gate Dam | Alternate Alignment Crest, Ridge, Saddle Dam Crest, Foundation depth | Not Applicable | 011-130-011-000 | Colusa | Work Package 3.oct | X
GG-SR-002 | SR | Curved Alignment Crest Line | Golden Gate Dam | Foundation depth | Not Applicable | 011-130-011-000 | Colusa | Work Package 3.oct | X
GG-SR-005 | SR | Upstream Toe | Golden Gate Dam | Foundation depth | Not Applicable | 011-130-011-000 | Colusa | Work Package 3.oct | X
GG-SR-006 | SR | Downstream Toe | Golden Gate Dam | Foundation depth | Not Applicable | 011-130-011-000 | Colusa | Work Package 3.oct | X
GG-SR-007 | SR | GG Dam | Channel | Foundation depth | Not Applicable | 011-130-011-000 | Colusa | Work Package 3.oct | X
GG-SR-008 | SR | GG Dam | Golden Gate Dam | Saddle Dam Section, Foundation depth | Not Applicable | 011-130-011-000 | Colusa | Work Package 3.oct
GG-SR-009 | SR | Saddle Dam Crest | Golden Gate Dam | Foundation depth | Not Applicable | 011-130-011-000 | Colusa | Work Package 3.oct
GG-SR-010 | SR | GG Dam | Golden Gate Dam | Saddle Dam Section, Foundation depth | Not Applicable | 011-130-011-000 | Colusa | Work Package 3.oct
TRW-B-029 | Auger/Core | TRW | TRRW | Gate foundation; inlet/outlet connection to GCID; ground improvement; TRRE bridge foundation | Grout | GCID Canal APN | Colusa | Work Package 3.nov |  | X
TRW-B-030 | Auger/Core | TRW | TRRW | Inlet/outlet connection to GCID; ground improvement; TRRE bridge foundation | Grout | GCID Canal APN | Colusa | Work Package 3.nov |  | X
TRW-C-020 | CPT | TRW | TRRW | Inlet/outlet connection to GCID; pipeline foundation, ground improvement | Grout | GCID Canal APN | Colusa | Work Package 3.nov |  | X
TRW-C-021 | CPT | TRW | TRRW | Inlet/outlet connection to GCID; pipeline foundation, ground improvement | Grout | GCID Canal APN | Colusa | Work Package 3.nov |  | X
TRW-C-022 | Seismic CPT | TRW | TRRW | Gate foundation; inlet/outlet connection to GCID; ground improvement; TRRE bridge foundation | Grout | GCID Canal APN | Colusa | Work Package 3.nov |  | X
TRW-C-023 | CPT | TRW | TRR Pipeline | Inlet/outlet connection to GCID; ground improvement; GCID plug design (also for TRRE) | Grout | GCID Canal APN | Colusa | Work Package 3.nov |  | X
TRW-C-024 | CPT | TRW | TRR Pipeline | Inlet/outlet connection to GCID; ground improvement; GCID plug design (also for TRRE) | Grout | GCID Canal APN | Colusa | Work Package 3.nov |  | X
DNG-B-001 | Auger/Core | DNG | DNG | Dunnigan Intake Structure, material properties for foundation design, stability/settlement | Grout | 52100005000 | Yolo | Work Package 3.nov
DNG-B-002 | Auger/Core | DNG | DNG | Dunnigan Intake Structure, foundation design, stability/settlement, paired with DNG-C-001 | Grout | 52100005000 | Yolo | Work Package 3.nov
DNG-C-001 | Seismic CPT | DNG | DNG | Paired with DNG-B-002, material properties, structure foundation, liquefaction check, continuous strata | Grout | 52100005000 | Yolo | Work Package 3.nov
DNG-G-001 | Geologic Mapping | DNG | DNG | Desktop study, followed up with ground observations along access routes to borings within the area at the time of drilling | Not Applicable | 52100005000 | Yolo | Work Package 3.nov
DNG-B-007 | Auger/Core | DNG | DNG | trenchless crossing design; material properties, pipeline excavation and backfill, groundwater | Piezometer | Yolo County APN | Yolo | Work Package 3.nov
DNG-B-005 | Auger/Core | DNG | DNG | trenchless crossing design; material properties, pipeline excavation and backfill, groundwater | Piezometer | 52060005000 | Yolo | Work Package 3.dec
DNG-B-006 | Auger/Core | DNG | DNG | trenchless crossing design; material properties, pipeline excavation and backfill, paired with DNG-C-002 | Grout | 52060005000 | Yolo | Work Package 3.dec
DNG-C-002 | Seismic CPT | DNG | DNG | Paired with DNG-B-006, material properties, trenchless crossing, liquefaction check, continuous strata | Grout | 52060005000 | Yolo | Work Package 3.dec
DNG-G-001 | Geologic Mapping | DNG | DNG | Desktop study, followed up with ground observations along access routes to borings within the area at the time of drilling | Not Applicable | 52060005000 | Yolo | Work Package 3.dec
NA-B-003o | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | 142100029 | Glenn | Work Package 3.x
NA-B-003q | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | 142100029 | Glenn | Work Package 3.x
NA-B-003s | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | 142100029 | Glenn | Work Package 3.x
NA-B-003u | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | 142100019 | Glenn | Work Package 3.x
NA-B-003w | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | 142100019 | Glenn | Work Package 3.x
NA-B-004 | Auger | Roads | Along roadway | For design recommendations of cuts, fills and structural section. | Grout | 142100029 | Glenn | Work Package 3.x
SD3-B-005 | RW-Core | Saddle Dams | Saddle Dam 3 | US Shell, Foundation depth | Grout | 142200019 | Glenn | Work Package 3.x
SD3-B-006 | RW-Core | Saddle Dams | Saddle Dam 3 | Channel Centerline, Foundation depth, grout curtain depth | Piezometer | 142200019 | Glenn | Work Package 3.x | [5 empty] | X
SD3-B-007 | RW-Core | Saddle Dams | Saddle Dam 3 | DS Shell, Foundation depth | Grout | 142200019 | Glenn | Work Package 3.x
SD3-B-010a | RW-Core | Saddle Dams | Saddle Dam 3 | Channel Centerline, Foundation depth, grout curtain depth | Piezometer | 142200019 | Glenn | Work Package 3.x
SD3-B-010b | RW-Core | Saddle Dams | Saddle Dam 3 | Channel Centerline, Foundation depth, grout curtain depth | Grout | 142200019 | Glenn | Work Package 3.x
SD3-Mapping | Geologic Mapping | Fault Study | Saddle Dam 3 | Evaluate geologic hazards and geotechnical properties to support dam study, as well as PSHA and FDHA (build on existing Q mapping and bedrock stratigraphic markers). Established detailed structure, faulting, landsliding, and Q map | Not Applicable | 142100019, 142100059, 142200019 | Glenn | Work Package 3.x
SD3-SR-001 | SR | Saddle Dams | Saddle Dam 3 | Centerline, Foundation depth | Not Applicable | 142200019, 142100059 | Glenn | Work Package 3.x
SD3-SR-003 | SR | Saddle Dams | Saddle Dam 3 | Right Channel, Foundation depth | Not Applicable | 142200019 | Glenn | Work Package 3.x
SD3-SR-004 | SR | Saddle Dams | Saddle Dam 3 | Channel Center, Foundation depth | Not Applicable | 142200019 | Glenn | Work Package 3.x
SD3-SR-005 | SR | Saddle Dams | Saddle Dam 3 | Left Channel, Foundation depth | Not Applicable | 142200019, 142100059 | Glenn | Work Package 3.x
SD3-SR-006 | SR | Left Abutment | Saddle Dams | Foundation depth | Not Applicable | 142100059 | Glenn | Work Package 3.x
SD5-B-003 | RW-Core | Saddle Dams | Saddle Dam 5 | DS Channel, Far-field conditions | Grout | 142100059 | Glenn | Work Package 3.x
SD5-B-004a | RW-Core | Saddle Dams | Saddle Dam 5 | Right Abutment, Foundation depth, grout curtain depth | Piezometer | 142100059 | Glenn | Work Package 3.x
SD5-B-004b | RW-Core | Saddle Dams | Saddle Dam 5 | Right Abutment, Foundation depth, grout curtain depth | Grout | 142100059 | Glenn | Work Package 3.x
SD5-B-006 | RW-Core | Saddle Dams | Saddle Dam 5 | US Right Abutment/Channel, Far-field conditions | Grout | 142100059 | Glenn | Work Package 3.x
SD5-Mapping | Geologic Mapping | Fault Study | Saddle Dam 5 | Evaluate geologic hazards and geotechnical properties to support dam study, as well as PSHA and FDHA (build on existing Q mapping and bedrock stratigraphic markers). Established detailed structure, faulting, landsliding, and Q map | Not Applicable | 142100059, 142400049, 142400069 | Glenn | Work Package 3.x
SD5-SR-001 | SR | Saddle Dams | Saddle Dam 5 | Crest Centerline, Foundation depth | Not Applicable | 142100059 | Glenn | Work Package 3.x
SD5-SR-002 | SR | Saddle Dams | Saddle Dam 5 | Right Abutment, Foundation depth | Not Applicable | 142100059 | Glenn | Work Package 3.x
SD5-SR-003 | SR | Channel | Saddle Dams | Foundation depth | Not Applicable | 142100059 | Glenn | Work Package 3.x
SD5-SR-004 | SR | Saddle Dams | Saddle Dam 5 | Left Abutment, Foundation depth | Not Applicable | 142100059 | Glenn | Work Package 3.x
SD5-T-001 | T | Fault Study | Saddle Dam 5 | Confirm location, width, style and activity of unnamed mapped fault (may be insignificant) | Backfill | 142100059 | Glenn | Work Package 3.x
SD6-Mapping | Geologic Mapping | Fault Study | Saddle Dam 6 | Evaluate geologic hazards and geotechnical properties to support dam study, as well as PSHA and FDHA (build on existing Q mapping and bedrock stratigraphic markers). Established detailed structure, faulting, landsliding, and Q map | Not Applicable | 142400049 | Glenn | Work Package 3.x
SD6-SR-001 | SR | Transverse Section | Saddle Dams | Foundation depth | Not Applicable | 142100019, 142400049 | Glenn | Work Package 3.x
SD6-SR-002 | SR | Longitudinal Section | Saddle Dams | Foundation depth | Not Applicable | 142400049 | Glenn | Work Package 3.x
SD8-Mapping | Geologic Mapping | Fault Study | Saddle Dam 8 | Evaluate geologic hazards and geotechnical properties to support dam study, as well as PSHA and FDHA (build on existing Q mapping and bedrock stratigraphic markers). Established detailed structure, faulting, landsliding, and Q map | Not Applicable | 142100019, 142400039 | Glenn | Work Package 3.x
SD8-SR-001 | SR | Saddle Dams | Saddle Dam 8 | Centerline, Foundation depth | Not Applicable | 142400039 | Glenn | Work Package 3.x
SD8-SR-002 | SR | Right Abutment | Saddle Dams | Foundation depth | Not Applicable | 142400049 | Glenn | Work Package 3.x
SD8-SR-003 | SR | Saddle Dams | Saddle Dam 8 | Channel, Foundation depth | Not Applicable | 142400049 | Glenn | Work Package 3.x
SD8-SR-004 | SR | Left Abutment | Saddle Dams | Foundation depth | Not Applicable | 142400049 | Glenn | Work Package 3.x
SD8-SR-005 | SR | Spillway | Saddle Dams | Foundation depth | Not Applicable | 142400049 | Glenn | Work Package 3.x
SDB-TP-003 | TP | Core Borrow | Saddle Dam 5,6,8A Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 142400049 | Glenn | Work Package 3.x
SDB-TP-005 | TP | Core Borrow | Saddle Dam 5,6,8A Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 142400049 | Glenn | Work Package 3.x
SDB-TP-006 | TP | Core Borrow | Saddle Dam 5,6,8A Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 142400049 | Glenn | Work Package 3.x
SDB-TP-008 | TP | Core Borrow | Saddle Dam 5,6,8A Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 142400049 | Glenn | Work Package 3.x
SDB-TP-009 | TP | Core Borrow | Saddle Dam 5,6,8A Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 142400049 | Glenn | Work Package 3.x
SDI1-SR-001 | SR | Transverse Section | Saddle Dams | Foundation depth | Not Applicable | 142400049 | Glenn | Work Package 3.x
SDI1-SR-002 | SR | Longitudinal Section | Saddle Dams | Foundation depth | Not Applicable | 142400049 | Glenn | Work Package 3.x
SDI2-SR-001 | SR | Transverse Section | Saddle Dams | Foundation depth | Not Applicable | 142400049 | Glenn | Work Package 3.x
SDQ-B-005 | RW-Core | Rock Quarries | Saddle Dam 3,5,6,8A Z3 Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 142100059 | Glenn | Work Package 3.x
SDQ-B-008 | RW-Core | Rock Quarries | Saddle Dam 3,5,6,8A Z3 Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Piezometer | 142100059 | Glenn | Work Package 3.x
SDQ-B-011 | RW-Core | Rock Quarries | Saddle Dam 3,5,6,8A Z3 Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 142200019 | Glenn | Work Package 3.x
SDQ-B-022 | RW-Core | Rock Quarries | Saddle Dams 1, 2, 3 Z3 Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 142100039 | Glenn | Work Package 3.x
SDQ-D-002 | D | Dozer line | Saddle Dams 1, 2, 3 Z3 Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 142100059 | Glenn | Work Package 3.x
SDQ-D-003 | D | Dozer line | Saddle Dams 1, 2, 3 Z3 Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 142200019 | Glenn | Work Package 3.x
SDQ-SR-001 | SR | Saddle Dam Quarry | Saddle Dam 3,5,6,8A Z3 Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Charactoristics | Not Applicable | 142100059 | Glenn | Work Package 3.x
SDQ-SR-002 | SR | Saddle Dam Quarry | Saddle Dam 3,5,6,8A Z3 Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Charactoristics | Not Applicable | 142100059 | Glenn | Work Package 3.x
SDQ-SR-003 | SR | Saddle Dam Quarry | Saddle Dam 3,5,6,8A Z3 Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Charactoristics | Not Applicable | 142200019 | Glenn | Work Package 3.x
SDQ-SR-006 | SR | Saddle Dam Quarry | Saddle Dams 1, 2, 3 Z3 Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Charactoristics | Not Applicable | 142100029, 142100039 | Glenn | Work Package 3.x
SDQ-SR-007 | SR | Saddle Dam Quarry | Saddle Dams 1, 2, 3 Z3 Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Charactoristics | Not Applicable | 142100029, 142100039 | Glenn | Work Package 3.x
SDQ-SR-008 | SR | Saddle Dam Quarry | Saddle Dams 1, 2, 3 Z3 Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Charactoristics | Not Applicable | 142100029, 142100039 | Glenn | Work Package 3.x
SDQ-TP-002 | TP | Rock Quarries | Saddle Dam 3,5,6,8A Z3 Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 142100059 | Glenn | Work Package 3.x
SDQ-TP-004 | TP | Rock Quarries | Saddle Dam 3,5,6,8A Z3 Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 142100059 | Glenn | Work Package 3.x
SDQ-TP-006 | TP | Rock Quarries | Saddle Dam 3,5,6,8A Z3 Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 142100059 | Glenn | Work Package 3.x
SDQ-TP-008 | TP | Rock Quarries | Saddle Dam 3,5,6,8A Z3 Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 142200019 | Glenn | Work Package 3.x
SDQ-TP-013 | TP | Rock Quarries | Saddle Dams 1, 2, 3 Z3 Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 142100039 | Glenn | Work Package 3.x
FNK-B-014 | Auger/Core | FNK | Funks | Sediment environmental characterization; coffer dam foundation | Grout | 011-190-001-000 | Colusa | Work Package 3.x |  |  | X |  |  | X |  | no access currently to the below water line areas of Funks Res
FNK-B-019 | Auger/Core | FNK | Funks | Stratigraphy; coffer dam & pipeline design | Grout | 011-190-002-000 | Colusa | Work Package 3.x |  |  | X |  |  | X |  | no access currently to the below water line areas of Funks Res
FNK-B-024 | Auger/Core | FNK | Funks | Stratigraphy; coffer dam & pipeline design | Grout | 011-190-001-000 | Colusa | Work Package 3.x |  |  | X |  |  | X |  | no access currently to the below water line areas of Funks Res
DNG-G-001 | Geologic Mapping | DNG | DNG | Desktop study, followed up with ground observations along access routes to borings within the area at the time of drilling | Not Applicable | 52060011000 | Yolo | Work Package 4
DNG-P-001 | TP | DNG | DNG | Stratigraphy; material properties, CLSM compatability | Backfill | 52060011000 | Yolo | Work Package 4
SL-B-020 | Auger | Roads | along roadway | For design recommendations of fill, culvert and structural section. | Grout | 011-080-013-000 | Colusa | Work Package 4
DNG-B-004 | Auger/Core | DNG | DNG | Material Properties, pipeline excavation and backfill | Grout | 52060012000 | Yolo | Work Package 4
DNG-G-001 | Geologic Mapping | DNG | DNG | Desktop study, followed up with ground observations along access routes to borings within the area at the time of drilling | Not Applicable | 52060012000 | Yolo | Work Package 4
DNG-G-001 | Geologic Mapping | DNG | DNG | Desktop study, followed up with ground observations along access routes to borings within the area at the time of drilling | Not Applicable | 52110006000 | Yolo | Work Package 4
DNG-G-001 | Geologic Mapping | DNG | DNG | Desktop study, followed up with ground observations along access routes to borings within the area at the time of drilling | Not Applicable | 52130013000 | Yolo | Work Package 4
SB-B-007 | Auger | Core Borrow | Sites Dam Borrow | Explore core borrow quantity and properties. | Piezometer | 011-172-001-000 | Colusa | Work Package 4 | X
SB-TP-007 | TP | Core Borrow | Sites Dam Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-171-001-000 | Colusa | Work Package 4 | X
HM-B-016 | Auger | Roads | Along roadway | For design recommendations of cuts, fills and structural section. | Grout | 014-080-016-000 | Colusa | Work Package 4
HM-B-018 | Auger | Roads | Along roadway | For design recommendations of cuts, fills and structural section. | Grout | 014-180-002-000 | Colusa | Work Package 4 | X
HM-SR-005 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 014-080-012-000 | Colusa | Work Package 4
DNG-G-001 | Geologic Mapping | DNG | DNG | Desktop study, followed up with ground observations along access routes to borings within the area at the time of drilling | Not Applicable | 52130017000 | Yolo | Work Package 4
DNG-G-001 | Geologic Mapping | DNG | DNG | Desktop study, followed up with ground observations along access routes to borings within the area at the time of drilling | Not Applicable | 52130018000, 52130021000 | Yolo | Work Package 4
TRRW RES Survey TRW-B-014 | RES | TRW | TRR West | Paired with TRW-C-019; Stratigraphy; cut stability/seepage; geologic contact; borrow eval; transmission tower foundation design | Not Applicable | 011-190-033-000 | Colusa | Work Package 4
TRW-B-012 | Auger/Core | TRW | TRRW | Paired with TRW-C-012; Stratigraphy; cut stability/seepage; geologic contact; borrow eval; transmission tower foundation design | Piezometer | 011-190-033-000 | Colusa | Work Package 4
TRW-B-013 | Auger/Core | TRW | TRRW | Stratigraphy; cut stability/seepage; geologic contact; borrow eval; transmission tower foundation design, TRR pipeline | Piezometer | 011-190-033-000 | Colusa | Work Package 4
TRW-B-015 | Auger/Core | TRW | TRRW | Tunnel design; cut stability/seepage; switchyard alternative | Piezometer | 011-190-030-000 | Colusa | Work Package 4
TRW-B-017 | Auger/Core | TRW | TRRW | Stratigraphy; cut stability/seepage; borrow evaluation | Piezometer | 011-190-030-000 | Colusa | Work Package 4
TRW-B-019 | Auger/Core | TRW | TRRW | Stratigraphy; cut stability/seepage; borrow evaluation | Piezometer | 011-190-030-000 | Colusa | Work Package 4
TRW-B-021 | Auger | TRW | TRRW | Stratigraphy; cut stability/seepage; borrow evaluation | Piezometer | 011-190-030-000 | Colusa | Work Package 4
TRW-B-032 | Auger/Core | TRW | TRRW | Paired with TRW-C-026; Stratigraphy; cut stability/seepage, borrow evaluation; transmission tower foundation design, TRR pipeline | Grout | 011-190-030-000 | Colusa | Work Package 4
TRW-B-039 | Auger/Core | TRW | TRRW | Stratigraphy; cut stability/seepage, borrow evaluation; approach channel foundation, TRR pipeline | Grout | 011-190-015-000 | Colusa | Work Package 4
TRW-C-026 | CPT | TRW | TRRW | Paired with TRW-B-032; Stratigraphy; cut stability, seepage; geologic contact; transmission tower foundation | Grout | 011-190-030-000 | Colusa | Work Package 4
TRW-C-027 | CPT | TRW | TRRW | Stratigraphy; cut stability, seepage; geologic contact | Grout | 011-190-015-000 | Colusa | Work Package 4
TRW-C-030 | CPT | TRW | TRRW | Inlet/outlet connection to GCID; ground improvement; TRRE bridge foundation | Grout | 011-190-030-000 | Colusa | Work Package 4
TRW-P-001 | TP | TRW | TRR Pipeline | Cut stability/seepage; site variability along geologic contact | Backfill | 011-190-030-000 | Colusa | Work Package 4
TRW-P-002 | TP | TRW | TRR Pipeline | Cut stability/seepage; site variability along geologic contact | Backfill | 011-190-030-000 | Colusa | Work Package 4
TRW-P-003 | TP | TRW | TRR Pipeline | Cut stability/seepage; site variability along geologic contact | Backfill | 011-190-030-000 | Colusa | Work Package 4
TRW-P-004 | TP | TRW | TRR Pipeline | Cut stability/seepage; site variability along geologic contact | Backfill | 011-190-030-000 | Colusa | Work Package 4
FNK-P-001 | TP | FNK | Funks | Stratigraphy; material properties, CLSM compatability, excavatability | Backfill | 011-150-018-000 | Colusa | Work Package 4
FNK-P-002 | TP | FNK | Funks | Stratigraphy; material properties, CLSM compatability, excavatability | Backfill | 011-150-017-000 | Colusa | Work Package 4
GG-B-009 | RW-Core | Golden Gate Dam | Golden Gate Dam | Channel, Foundation depth | Piezometer | 011-130-011-000 | Colusa | Work Package 4
GG-B-037 | RW-Core | Golden Gate Dam | Golden Gate Dam | Saddle Dam, Right Abutment/Centerline,Foundation depth, grout curtain depth | Grout | 011-130-011-000 | Colusa | Work Package 4
GGQ-B-002 | RW-Core | Rock Quarries | Golden Gate Dam Z3Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 011-130-004-000 | Colusa | Work Package 4
GGQ-B-005 | RW-Core | Rock Quarries | Golden Gate Dam Z3Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 011-130-004-000 | Colusa | Work Package 4
GGQ-B-008 | RW-Core | Rock Quarries | Golden Gate Dam Z3Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 011-130-011-000 | Colusa | Work Package 4
GGQ-B-013 | RW-Core | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 011-130-004-000 | Colusa | Work Package 4
GGQ-TP-002 | TP | Rock Quarries | Golden Gate Dam Z3Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-130-004-000 | Colusa | Work Package 4
GGQ-TP-003 | TP | Rock Quarries | Golden Gate Dam Z3Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-130-004-000 | Colusa | Work Package 4
GGQ-TP-004 | TP | Rock Quarries | Golden Gate Dam Z3Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-130-004-000 | Colusa | Work Package 4
GG-SR-003 | SR | GG Dam | Golden Gate Dam | Left Abutment, Foundation depth | Not Applicable | 011-130-011-000 | Colusa | Work Package 4 | X
GG-SR-004 | SR | GG Dam | Golden Gate Dam | Right Abutment, Foundation depth | Not Applicable | 011-130-011-000 | Colusa | Work Package 4 | X
GG-T-001 | T | Fault Study | Golden Gate Dam | Confirm GG-F2 fault location, width and kinematics; assess age of absence of faulting | Backfill | 011-130-011-000 | Colusa | Work Package 4 | X
GG-T-002 | T | Fault Study | Golden Gate Dam (Saddle Dam Area) | Confirm GG-F2 fault location, width and kinematics; assess age of absence of faulting | Backfill | 011-130-011-000 | Colusa | Work Package 4
GG-T-003 | T | Fault Study | Golden Gate Dam | Establish Age of Unfaulted Deposits (OSL or similar age dating) | Backfill | 011-130-011-000 | Colusa | Work Package 4 | X
GG-T-004 | T | Fault Study | Golden Gate Dam | Confirm GG-F2 fault location, width and kinematics; assess age of absence of faulting | Backfill | 011-130-011-000 | Colusa | Work Package 4
SD3-Mapping | Geologic Mapping | Fault Study | Saddle Dam 3 | Evaluate geologic hazards and geotechnical properties to support dam study, as well as PSHA and FDHA (build on existing Q mapping and bedrock stratigraphic markers). Established detailed structure, faulting, landsliding, and Q map | Not Applicable | 142200050, 142200040 | Glenn | Work Package 4
SD3-SR-001 | SR | Saddle Dams | Saddle Dam 3 | Centerline, Foundation depth | Not Applicable | 142200050 | Glenn | Work Package 4
SDQ-SR-004 | SR | Saddle Dam Quarry | Saddle Dam 3,5,6,8A Z3 Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Charactoristics | Not Applicable | 142200040 | Glenn | Work Package 4
FNK-G-001 | Geologic Mapping | FNK | Funks | Strike/Dip Measurements, Geology mapping | Not Applicable | 011-140-026-000 | Colusa | Work Package 4
GGQ-B-018 | RW-Core | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Piezometer | 011-130-003-000 | Colusa | Work Package 4
GGQ-B-020 | RW-Core | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 011-130-003-000 | Colusa | Work Package 4
GGQ-B-028 | RW-Core | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 011-030-007-000 | Colusa | Work Package 4
GGQ-D-001a | D | Dozer line | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-130-003-000 | Colusa | Work Package 4
GGQ-D-001b | D | Dozer line | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-130-003-000 | Colusa | Work Package 4
GGQ-D-003 | D | Dozer line | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-130-003-000 | Colusa | Work Package 4
GGQ-SR-005 | SR | GG Quarry | Golden Gate Dam Z3 Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Charactoristics | Not Applicable | 011-130-003-000 | Colusa | Work Package 4
GGQ-SR-006 | SR | GG Quarry | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Charactoristics | Not Applicable | 011-030-007-000 | Colusa | Work Package 4
GGQ-TP-005 | TP | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-130-003-000 | Colusa | Work Package 4
GGQ-TP-007 | TP | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-130-003-000 | Colusa | Work Package 4
GGQ-TP-009 | TP | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-130-003-000 | Colusa | Work Package 4
GGQ-TP-011 | TP | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-130-003-000 | Colusa | Work Package 4
GGQ-TP-013 | TP | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-130-003-000 | Colusa | Work Package 4
GGQ-TP-015 | TP | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-030-007-000 | Colusa | Work Package 4
SD1-Mapping | Geologic Mapping | Fault Study | Saddle Dam 1 | Evaluate geologic hazards and geotechnical properties to support dam study, as well as PSHA and FDHA (build on existing Q mapping and bedrock stratigraphic markers). Established detailed structure, faulting, landsliding, and Q map | Not Applicable | 011-030-002-000 | Colusa | Work Package 4
SD2-Mapping | Geologic Mapping | Fault Study | Saddle Dam 2 | Evaluate geologic hazards and geotechnical properties to support dam study, as well as PSHA and FDHA (build on existing Q mapping and bedrock stratigraphic markers). Established detailed structure, faulting, landsliding, and Q map | Not Applicable | 011-030-002-000 | Colusa | Work Package 4
SDB-TP-021 | TP | Core Borrow | Saddle Dam 1,2 Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-030-002-000 | Colusa | Work Package 4
SDB-TP-023 | TP | Core Borrow | Saddle Dam 1,2 Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-030-002-000 | Colusa | Work Package 4
SDQ-TP-009 | TP | Rock Quarries | Saddle Dam 3,5,6,8A Z3 Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 142200040 | Glenn | Work Package 4
SDQ-TP-010 | TP | Rock Quarries | Saddle Dam 3,5,6,8A Z3 Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 142200040 | Glenn | Work Package 4
SDB-TP-014 | TP | Core Borrow | Saddle Dam 3 Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-030-012-000 | Colusa | Work Package 4
SDB-TP-015 | TP | Core Borrow | Saddle Dam 3 Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-030-013-000 | Colusa | Work Package 4
SDB-TP-016 | TP | Core Borrow | Saddle Dam 3 Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-030-012-000 | Colusa | Work Package 4
SDB-TP-019 | TP | Core Borrow | Saddle Dam 3 Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-030-012-000 | Colusa | Work Package 4
HM-B-003b | Auger | Roads | Along roadway | For design recommendations of fill, culvert and structural section. | Grout | 014-090-036-000 | Colusa | Work Package 4
HM-B-003f | Auger | Roads | Along roadway | For design recommendations of fill, culvert and structural section. | Grout | 014-080-004-000 | Colusa | Work Package 4
HM-B-006a | Auger | Roads | Along roadway | For design recommendations of cuts, fills and structural section. | Grout | 014-080-004-000 | Colusa | Work Package 4
HM-B-006c | Auger | Roads | Along roadway | For design recommendations of cuts, fills and structural section. | Grout | 014-080-004-000 | Colusa | Work Package 4
HM-B-007 | Auger | Roads | Along roadway | For design recommendations of cuts, fills and structural section. | Grout | 014-080-003-000 | Colusa | Work Package 4
HM-B-010 | RW-Core | Roads | Along roadway | For design recommendations of cuts, fills and structural section. | Grout | 014-080-003-000 | Colusa | Work Package 4
HM-B-023 | Auger | Roads | Along roadway | For design recommendations of cuts, fills and structural section. | Grout | 014-180-004-000 | Colusa | Work Package 4 | X
HM-SR-001 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 014-080-003-000 | Colusa | Work Package 4
HM-SR-011 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 014-180-004-000 | Colusa | Work Package 4 | X
HM-B-025 | Auger | Roads | Along roadway | For design recommendations of cuts, fills and structural section. | Grout | 014-180-003-000 | Colusa | Work Package 4
HM-SR-013 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 014-180-003-000, 014-180-012-000 | Colusa | Work Package 4
HM-SR-015 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 014-180-003-000 | Colusa | Work Package 4
DNG-B-009 | Auger/Core | DNG | DNG | CBD outlet structure foundation design, paired with DNG-C-003 | Grout | 53150030000 | Yolo | Work Package 4 |  | X
DNG-C-003 | Seismic CPT | DNG | DNG | Paired with DNG-B-009, CBD Outlet structure foundation, liquefaction check, continuous strata | Grout | 53150030000 | Yolo | Work Package 4 |  | X
DNG-G-001 | Geologic Mapping | DNG | DNG | Desktop study, followed up with ground observations along access routes to borings within the area at the time of drilling | Not Applicable | 53150030000 | Yolo | Work Package 4
DNG-G-001 | Geologic Mapping | DNG | DNG | Desktop study, followed up with ground observations along access routes to borings within the area at the time of drilling | Not Applicable | 52130020000, 52130023000 | Yolo | Work Package 4
DNG-B-008 | Auger/Core | DNG | DNG | Material properties, pipeline excavation and backfill | Grout | 52130023000 | Yolo | Work Package 4 |  | X
DNG-B-003 | Auger/Core | DNG | DNG | Material Properties, pipeline excavation and backfill | Grout | 52100003000 | Yolo | Work Package 4
DNG-G-001 | Geologic Mapping | DNG | DNG | Desktop study, followed up with ground observations along access routes to borings within the area at the time of drilling | Not Applicable | 52100003000, 52070013000, 52060016000 | Yolo | Work Package 4
DNG-G-001 | Geologic Mapping | DNG | DNG | Desktop study, followed up with ground observations along access routes to borings within the area at the time of drilling | Not Applicable | 52120008000 | Yolo | Work Package 4
DNG-G-001 | Geologic Mapping | DNG | DNG | Desktop study, followed up with ground observations along access routes to borings within the area at the time of drilling | Not Applicable | 52130007000 | Yolo | Work Package 4
FNK-B-021 | Auger/Core | FNK | Funks | Stratigraphy, stability of hillside; coffer dam & pipeline design | Piezometer | 011-190-002-000 | Colusa | Work Package 4.x | [7 empty] | no access to be provided this year, erosion gully took out access
FNK-B-022 | Auger/Core | FNK | Funks | Stratigraphy, stability of hillside; coffer dam & pipeline design | Piezometer | 011-190-001-000 | Colusa | Work Package 4.x | [7 empty] | no access to be provided this year, erosion gully took out access
TRR-B-024 | Auger/Core | TRR | TRR Pipeline | Transmission tower foundation design | Grout | 011-190-001-000 | Colusa | Work Package 4.x | [7 empty] | no access to be provided this year, erosion gully took out access
HM-B-027b | Auger | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Grout | 014-170-005-000 | Colusa | Work Package 5
SL-B-023 | Auger | Roads | along roadway | For design recommendations of fill, culvert and structural section. | Grout | No APN - Road | Colusa | Work Package 5
SL-SR-014 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | No APN - Road | Colusa | Work Package 5
SL-SR-015 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | No APN - Road | Colusa | Work Package 5
IO-B-S-03 | RW-Core | Inlet-Outlet | Tunnel STA 12+00 | Tunnel liner design; 2 tunnel Ø below invert | Piezometer | 011-150-010-000 | Colusa | Work Package 5 | X
D-B-001c | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 5
D-B-001e | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 5 |  | X
D-B-001i | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 5 |  | X
MD-B-001d | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 5 |  | X
MD-B-001h | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 5 |  | X
MD-B-001l | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 5 |  | X
MD-B-001r | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 5 |  | X
MD-B-001t | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 5 |  | X
MD-B-006b | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 5 |  | X
MD-B-006f | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 5 |  | X
MS-B-001b | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 5 |  | X |  | X
MS-B-001f | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 5
MS-B-001h | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 5
MS-B-001l | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 5
MS-B-001n | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 5
MS-B-001r | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 5
MS-B-004a | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 5
MS-B-004e | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 5
MS-B-004i | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 5
MS-B-004k | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 5 | X
SL-B-025a | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 5
SL-B-025e | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Colusa | Work Package 5 | X
HM-B-017a | Auger | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Grout | 014-080-016-000 | Colusa | Work Package 5
HM-B-019 | Auger | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Grout | 014-180-002-000 | Colusa | Work Package 5 | X
HM-SR-006 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 014-080-017-000 | Colusa | Work Package 5
HM-SR-007 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 014-180-002-000 | Colusa | Work Package 5 | X
HM-SR-008 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 014-180-002-000 | Colusa | Work Package 5 | X
TRW-B-028 | Auger/Core | TRW | TRRW | Paired with TRW-C-028; Stratigraphy; inlet/outlet stability/settlement/ground improvement; siphon foundation | Piezometer | 011-220-079-000 | Colusa | Work Package 5
TRW-C-028 | Seismic CPT | TRW | TRRW | Paired with TRW-B-028; Stratigraphy; inlet/outlet stability/settlement/ground improvement; siphon foundation | Grout | 011-220-079-000 | Colusa | Work Package 5
GCD-B-001 | Auger/Core | GCID | GCID | GCID Headworks structure design | Grout | GCID Canal APN | Glenn | Work Package 5 |  | X |  |  | X
GCD-B-002 | Auger/Core | GCID | GCID | GCID Headworks structure design | Grout | 370900070 | Glenn | Work Package 5 |  | X |  |  | X
NA-B-003a | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Glenn | Work Package 5
NA-B-003c | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Glenn | Work Package 5
NA-B-003g | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Glenn | Work Package 5
NA-B-003k | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Glenn | Work Package 5
NA-B-003m | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Glenn | Work Package 5
R68-B-001a | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Glenn | Work Package 5 |  | X
R68-B-001e | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Glenn | Work Package 5 |  | X
R68-B-001i | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Glenn | Work Package 5 |  | X
R68-B-001m | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Glenn | Work Package 5 |  | X
R68-B-001o | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Glenn | Work Package 5 |  | X
R69-B-003g | PC | Roads | Along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Glenn | Work Package 5
R69-B-003i | PC | Roads | along roadway | Coring is for measuring depth of AC and AB. Auger is for tesing subgrade. All is for establishing FDR design mix recommendation | Grout | No APN - Road | Glenn | Work Package 5
TRW-B-031 | Auger/Core | TRW | TRW | Tunnel design; cut stability/seepage | Piezometer | 011-190-030-000 | Colusa | Work Package 5
TRW-B-033 | Auger/Core | TRW | TRW | Stratigraphy; reservoir subrade evaluation; borrow eval | Grout | 011-190-030-000 | Colusa | Work Package 5
TRW-B-034 | Auger/Core | TRW | TRW | Stratigraphy; cut stability/seepage, borrow evalaution; transmission tower foundation design | Grout | 011-190-030-000 | Colusa | Work Package 5
TRW-B-035 | Auger/Core | TRW | TRW | Stratigraphy; cut stability/seepage, borrow evalaution | Piezometer | 011-190-030-000 | Colusa | Work Package 5
TRW-B-036 | Auger/Core | TRW | TRW | Stratigraphy; cut stability/seepage, borrow evalaution | Grout | 011-190-030-000 | Colusa | Work Package 5
TRW-B-038 | Auger/Core | TRW | TRW | Stratigraphy; cut stability/seepage, borrow evalaution | Grout | 011-190-015-000 | Colusa | Work Package 5
TRW-B-040 | Auger/Core | TRW | TRW | Stratigraphy; cut stability/seepage, borrow evalaution; transmission tower foundation design | Grout | 011-190-015-000 | Colusa | Work Package 5
TRW-B-041 | Auger/Core | TRW | TRW | Stratigraphy (substation), transmission tower foundation design; borrow evaluation; cut stability/seepage | Piezometer | 011-190-015-000 | Colusa | Work Package 5
TRW-B-042 | Auger/Core | TRW | TRW | Stratigraphy (substation); borrow evaluation; cut stability/seepage | Grout | 011-190-015-000 | Colusa | Work Package 5
TRW-B-043 | Auger/Core | TRW | TRW | Stratigraphy; PGP foundation; borrow evaluation | Grout | 011-190-015-000 | Colusa | Work Package 5
TRW-B-044 | Auger/Core | TRW | TRW | Transmission tower foundation design | Grout | 011-190-015-000 | Colusa | Work Package 5
GG-B-003 | RW-Core | Golden Gate Dam | Upstream Channel | Far-field conditions | Grout | 011-130-011-000 | Colusa | Work Package 5
GG-B-005 | RW-Core | Golden Gate Dam | Channel | Foundation depth | Piezometer | 011-130-011-000 | Colusa | Work Package 5
GG-B-006 | RW-Core | Golden Gate Dam | Right Abutment/Centerline | Foundation depth, grout curtain depth | Grout | 011-130-011-000 | Colusa | Work Package 5
GG-B-010 | RW-Core | Golden Gate Dam | Channel | Foundation depth | Piezometer | 011-130-011-000 | Colusa | Work Package 5
GG-B-014 | RW-Core | Golden Gate Dam | Golden Gate Dam | Channel, Core Trench, Foundation depth, grout curtain depth | Piezometer | 011-130-011-000 | Colusa | Work Package 5 | X
GG-B-016 | RW-Core | Golden Gate Dam | Left Abutment | Foundation depth, grout curtain depth | Piezometer | 011-130-011-000 | Colusa | Work Package 5
GG-B-018 | RW-Core | Golden Gate Dam | Centerline | Foundation depth, grout curtain depth | Grout | 011-130-011-000 | Colusa | Work Package 5 | X
GG-B-020 | RW-Core | Golden Gate Dam | Golden Gate Dam | Channel Core Trench, Foundation depth, grout curtain depth | Piezometer | 011-130-011-000 | Colusa | Work Package 5 | X
GG-B-027 | RW-Core | Golden Gate Dam | US Ridge | Ridge permeability | Piezometer | 011-130-011-000 | Colusa | Work Package 5
GG-B-028a | RW-Core | Golden Gate Dam | Centerline/Right Abutment | Foundation depth, grout curtain depth | Piezometer | 011-130-011-000 | Colusa | Work Package 5
GG-B-028b | RW-Core | Golden Gate Dam | Centerline/Right Abutment | Grout curtain depth, bedding angle | Grout | 011-130-011-000 | Colusa | Work Package 5
GG-B-031 | RW-Core | Golden Gate Dam | Saddle Dam, Centerline | Foundation depth, grout curtain depth | Grout | 011-130-011-000 | Colusa | Work Package 5
GG-B-035 | RW-Core | Golden Gate Dam | Saddle Dam, Centerline | Foundation depth, grout curtain depth | Grout | 011-130-011-000 | Colusa | Work Package 5
GGQ-B-011 | RW-Core | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 011-130-004-000 | Colusa | Work Package 5
SDQ-B-014 | RW-Core | Rock Quarries | Saddle Dam 3,5,6,8A Z3 Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 142200040 | Glenn | Work Package 5
GGQ-B-019 | RW-Core | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 011-130-003-000 | Colusa | Work Package 5
GGQ-B-021 | RW-Core | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 011-130-003-000 | Colusa | Work Package 5
GGQ-B-026 | RW-Core | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Piezometer | 011-030-007-000 | Colusa | Work Package 5
GGQ-B-027 | RW-Core | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 011-030-007-000 | Colusa | Work Package 5
GGQ-B-029 | RW-Core | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 011-030-007-000 | Colusa | Work Package 5
GGQ-TP-006 | TP | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-130-003-000 | Colusa | Work Package 5
GGQ-TP-008 | TP | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-130-003-000 | Colusa | Work Package 5
GGQ-TP-010 | TP | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-130-003-000 | Colusa | Work Package 5
GGQ-TP-012 | TP | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-130-003-000 | Colusa | Work Package 5
GGQ-TP-014 | TP | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-030-007-000 | Colusa | Work Package 5
GGQ-TP-016 | TP | Rock Quarries | Golden Gate Dam Z3Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-030-007-000 | Colusa | Work Package 5
SD1-B-002a | RW-Core | Saddle Dams | Channel | Foundation depth, grout curtain depth | Piezometer | 011-030-002-000 | Colusa | Work Package 5
SD1-B-002b | RW-Core | Saddle Dams | Channel | Foundation depth, grout curtain depth | Grout | 011-030-002-000 | Colusa | Work Package 5
SD1-SR-002 | SR | Longitudinal Section | Saddle Dams | Foundation depth | Not Applicable | 011-030-002-000 | Colusa | Work Package 5
SD2-B-003a | RW-Core | Saddle Dams | Channel | Foundation depth, grout curtain depth | Piezometer | 011-030-002-000 | Colusa | Work Package 5
SD2-B-003b | RW-Core | Saddle Dams | Channel | Foundation depth, grout curtain depth | Grout | 011-030-002-000 | Colusa | Work Package 5
SD2-SR-001 | SR | Transverse Section | Saddle Dams | Foundation depth | Not Applicable | 011-030-002-000 | Colusa | Work Package 5
SD2-SR-002 | SR | Longitudinal Section | Saddle Dams | Foundation depth | Not Applicable | 011-030-002-000 | Colusa | Work Package 5
SD2-T-001 | T | Fault Study | Saddle Dam 2 | Confirm location, width, style and activity SLF | Backfill | 011-030-002-000 | Colusa | Work Package 5
SD1-SR-001 | SR | Transverse Section | Saddle Dams | Foundation depth | Not Applicable | 142200050, 011-030-002-000 | Glenn, Colusa | Work Package 5
SD3-B-014 | RW-Core | Saddle Dams | Saddle Dam 3 | Right Abutment, Foundation depth, grout curtain depth | Piezometer | 142200050 | Glenn | Work Package 5
SD3-SR-002 | SR | Right Abutment | Saddle Dams | Foundation depth | Not Applicable | 142200050 | Glenn | Work Package 5
SDB-TP-012 | TP | Core Borrow | Saddle Dam 3 Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-030-012-000 | Colusa | Work Package 5
SDB-TP-013 | TP | Core Borrow | Saddle Dam 3 Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-030-012-000 | Colusa | Work Package 5
SDB-TP-017 | TP | Core Borrow | Saddle Dam 3 Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-030-012-000 | Colusa | Work Package 5
SDB-TP-018 | TP | Core Borrow | Saddle Dam 3 Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-030-012-000 | Colusa | Work Package 5
SDB-TP-020 | TP | Core Borrow | Saddle Dam 3 Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-030-012-000 | Colusa | Work Package 5
SDB-TP-022 | TP | Core Borrow | Saddle Dam 1,2 Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-030-002-000 | Colusa | Work Package 5
SDB-TP-024 | TP | Core Borrow | Saddle Dam 1,2 Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-030-002-000 | Colusa | Work Package 5
GGQ-SR-007 | SR | Golden Gate Dam Z3Quarry2 | Rock Quarries | Verify Zone 3 and 4 Borrow Materials Quantities and Charactoristics | Not Applicable | 011-030-004-000 | Colusa | Work Package 5
GGQ-SR-008 | SR | Golden Gate Dam Z3Quarry2 | Rock Quarries | Verify Zone 3 and 4 Borrow Materials Quantities and Charactoristics | Not Applicable | 011-030-004-000 | colusa | Work Package 5
SD1-Mapping | Geologic Mapping | Fault Study | Saddle Dam 1 | Evaluate geologic hazards and geotechnical properties to support dam study, as well as PSHA and FDHA (build on existing Q mapping and bedrock stratigraphic markers). Established detailed structure, faulting, landsliding, and Q map | Not Applicable | 011-030-003-000 | colusa | Work Package 5
HM-B-003d | Auger | Roads | along roadway | For design recommendations of fill, culvert and structural section. | Grout | 014-090-036-000 | Colusa | Work Package 5
HM-B-004 | Auger | Roads | along roadway | For design recommendations of fill, culvert and structural section. | Grout | 014-080-004-000 | Colusa | Work Package 5
HM-B-006g | Auger | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Grout | 014-080-003-000 | Colusa | Work Package 5 | X
HM-B-009 | Auger | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Grout | 014-080-003-000 | Colusa | Work Package 5 | X
HM-B-021 | Auger | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Grout | 014-180-004-000 | Colusa | Work Package 5 | X
HM-SR-002 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 014-080-003-000 | Colusa | Work Package 5
HM-SR-003 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 014-080-003-000 | Colusa | Work Package 5
HM-SR-004 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 014-080-003-000 | Colusa | Work Package 5
HM-SR-010 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 014-180-004-000 | Colusa | Work Package 5 | X
HM-SR-009 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 014-180-012-000 | Colusa | Work Package 5 | X
HM-SR-012 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 014-180-012-000 | Colusa | Work Package 5
HM-SR-014 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 014-180-012-000 | Colusa | Work Package 5
HM-SR-016 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 014-180-003-000 | Colusa | Work Package 5
SD3-B-003a | RW-Core | Saddle Dams | Left Abutment | Foundation depth, grout curtain depth | Piezometer | 142100059 | Glenn | Work Package 5
SD3-B-003b | RW-Core | Saddle Dams | Left Abutment | Foundation depth, grout curtain depth | Grout | 142100059 | Glenn | Work Package 5
SD3-B-004 | RW-Core | Saddle Dams | Saddle Dam 3 | US Channel, Far-field conditions | Grout | 142200019 | Glenn | Work Package 5
SD3-B-008 | RW-Core | Saddle Dams | Saddle Dam 3 | DS Channel, Far-field conditions | Grout | 142200019 | Glenn | Work Package 5
SD3-B-009 | RW-Core | Saddle Dams | US Channel | Far-field conditions | Grout | 142200019 | Glenn | Work Package 5
SD3-B-011 | RW-Core | Saddle Dams | DS Shell | Foundation depth | Grout | 142200019 | Glenn | Work Package 5
SD3-B-012 | RW-Core | Saddle Dams | DS Channel | Far-field conditions | Grout | 142200019 | Glenn | Work Package 5
SD5-B-005 | RW-Core | Saddle Dams | Right Abutment | Foundation depth | Grout | 142100059 | Glenn | Work Package 5
SD5-B-007 | RW-Core | Saddle Dams | Right Abutment | Foundation depth, grout curtain depth | Grout | 142100059 | Glenn | Work Package 5
SD6-B-002a | RW-Core | Saddle Dams | Channel | Foundation depth, grout curtain depth | Piezometer | 142400049 | Glenn | Work Package 5
SD6-B-002b | RW-Core | Saddle Dams | Channel | Foundation depth, grout curtain depth | Grout | 142400049 | Glenn | Work Package 5
SD8-B-001 | RW-Core | Saddle Dams | Left Abutment | Foundation depth, grout curtain depth | Grout | 142400049 | Glenn | Work Package 5
SD8-B-002 | RW-Core | Saddle Dams | Saddle Dam 8 | DS Channel, Far-field conditions | Grout | 142400049 | Glenn | Work Package 5
SD8-B-004 | RW-Core | Saddle Dams | Saddle Dam 8 | US Channel,Far-field conditions | Grout | 142400049 | Glenn | Work Package 5
SD8-B-005a | RW-Core | Saddle Dams | Channel | Foundation depth, grout curtain depth | Piezometer | 142400049 | Glenn | Work Package 5
SD8-B-005b | RW-Core | Saddle Dams | Channel | Foundation depth, grout curtain depth | Grout | 142400049 | Glenn | Work Package 5
SDB-TP-001 | TP | Core Borrow | Saddle Dam 5,6,8A Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 142400049 | Glenn | Work Package 5
SDB-TP-002 | TP | Core Borrow | Saddle Dam 5,6,8A Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 142400049 | Glenn | Work Package 5
SDB-TP-007 | TP | Core Borrow | Saddle Dam 5,6,8A Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 142400049 | Glenn | Work Package 5
SDB-TP-010 | TP | Core Borrow | Saddle Dam 5,6,8A Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 142400049 | Glenn | Work Package 5
SDB-TP-011 | TP | Core Borrow | Saddle Dam 5,6,8A Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 142400049 | Glenn | Work Package 5
SDI1-B-002 | RW-Core | Saddle Dams | Centerline | Foundation Depth and Quality Data, grout curtain design | Piezometer | 142400049 | Glenn | Work Package 5
SDI2-B-002 | RW-Core | Saddle Dams | Centerline | Foundation Depth and Quality Data, grout curtain design | Piezometer | 142400049 | Glenn | Work Package 5
SDQ-B-002 | RW-Core | Rock Quarries | Saddle Dam 3,5,6,8A Z3 Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 142100059 | Glenn | Work Package 5
SDQ-B-020 | RW-Core | Rock Quarries | Saddle Dams 1, 2, 3 Z3 Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 142100039 | Glenn | Work Package 5
SDQ-B-026 | RW-Core | Rock Quarries | Saddle Dams 1, 2, 3 Z3 Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 142100039 | Glenn | Work Package 5
SDQ-TP-001 | TP | Rock Quarries | Saddle Dam 3,5,6,8A Z3 Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 142100059 | Glenn | Work Package 5
SDQ-TP-003 | TP | Rock Quarries | Saddle Dam 3,5,6,8A Z3 Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 142100059 | Glenn | Work Package 5
SDQ-TP-005 | TP | Rock Quarries | Saddle Dam 3,5,6,8A Z3 Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 142100059 | Glenn | Work Package 5
SDQ-TP-007 | TP | Rock Quarries | Saddle Dam 3,5,6,8A Z3 Quarry 1 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 142200019 | Glenn | Work Package 5
SDQ-TP-014 | TP | Rock Quarries | Saddle Dams 1, 2, 3 Z3 Quarry2 | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 142100039 | Glenn | Work Package 5
SQ-B-003 | RW-Core | Rock Quarries | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 011-150-012-000 | Colusa | Work Package 5
SQ-B-009 | RW-Core | Rock Quarries | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 011-150-012-000 | Colusa | Work Package 5 | X
SQ-B-012 | RW-Core | Rock Quarries | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Grout | 011-150-012-000 | Colusa | Work Package 5 | X
SQ-TP-005 | TP | Rock Quarries | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-150-012-000 | Colusa | Work Package 5 | X
SQ-TP-008 | TP | Rock Quarries | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-150-012-000 | Colusa | Work Package 5 | X
SQ-TP-011 | TP | Rock Quarries | Sites Dam Z3 Quarry | Verify Zone 3 and 4 Borrow Materials Quantities and Characteristics | Backfill | 011-150-012-000 | Colusa | Work Package 5
GG-SR-005 | SR | Upstream Toe | Golden Gate Dam | Foundation depth | Not Applicable | 011-130-011-000 | Colusa | Work Package 5 | X
SB-TP-003 | TP | Core Borrow | Sites Dam Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-150-009-000 | Colusa | Work Package 5 | X
SB-TP-004 | TP | Core Borrow | Sites Dam Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-150-009-000 | Colusa | Work Package 5 | X
SB-TP-005 | TP | Core Borrow | Sites Dam Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-150-009-000 | Colusa | Work Package 5 | X
SB-TP-006 | TP | Core Borrow | Sites Dam Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-150-009-000 | Colusa | Work Package 5 | X
SL-B-006 | RW-Core | Roads | along roadway | For design recommendations for fill prism and possible bridge abutment. | Grout | 011-150-002-000 | Colusa | Work Package 5
SL-B-013 | RW-Core | Roads | along roadway | For design recommendations for possible bridge abutment. | Grout | 011-150-001-000 | Colusa | Work Package 5
SL-B-017 | RW-Core | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Grout | 011-150-001-000 | Colusa | Work Package 5
SL-B-019 | Auger | Roads | along roadway | For design recommendations of fill, culvert and structural section. | Grout | 011-100-004-000 | Colusa | Work Package 5
SL-B-033 | RW-Core | Roads | Borrow site | For determining adequacy of material for causeway fill prism. | Grout | 011-150-002-000 | Colusa | Work Package 5
SL-B-034 | RW-Core | Roads | Borrow site | For determining adequacy of material for causeway fill prism. | Grout | 011-150-002-000 | Colusa | Work Package 5
SL-B-035 | RW-Core | Roads | Borrow site | For determining adequacy of material for causeway fill prism. | Grout | 011-150-002-000 | Colusa | Work Package 5
SL-B-039 | RW-Core | Roads | Borrow site | For determining adequacy of material for causeway fill prism. | Grout | 011-150-001-000 | Colusa | Work Package 5
SL-B-040 | RW-Core | Roads | Borrow site | For determining adequacy of material for causeway fill prism. | Grout | 011-150-001-000 | Colusa | Work Package 5
SL-B-041 | RW-Core | Roads | Borrow site | For determining adequacy of material for causeway fill prism. | Grout | 011-150-002-000 | Colusa | Work Package 5
SLB-B-001 | RW-Core | Bridges | West Bridge Abutment 1 | Determine depth to foundation | Piezometer | 011-150-001-000 | Colusa | Work Package 5
SLB-B-004 | RW-Core | Bridges | West Bridge Pier 4 | Determine depth to foundation | Piezometer | 011-150-001-000 | Colusa | Work Package 5
SLB-B-006 | RW-Core | Bridges | West Bridge Pier 6 | Determine depth to foundation | Piezometer | 011-150-001-000 | Colusa | Work Package 5
SLB-B-009 | RW-Core | Bridges | East Bridge Pier 2 | Determine depth to foundation | Piezometer | 011-150-002-000 | Colusa | Work Package 5
SLB-B-012 | RW-Core | Bridges | East Bridge Pier 5 | Determine depth to foundation | Piezometer | 011-150-002-000 | Colusa | Work Package 5
SLB-B-015 | RW-Core | Bridges | East Bridge Abutment 8 | Determine depth to foundation | Piezometer | 011-150-002-000 | Colusa | Work Package 5
SL-SR-001 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 011-150-001-000 | Colusa | Work Package 5
SL-SR-002 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 011-150-001-000 | Colusa | Work Package 5
SL-SR-003 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 011-150-001-000 | Colusa | Work Package 5
SL-SR-004 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 011-100-004-000 | Colusa | Work Package 5
SL-SR-005 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 011-100-004-000 | Colusa | Work Package 5
SL-SR-006 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 011-100-004-000 | Colusa | Work Package 5
SL-SR-007 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 011-100-004-000 | Colusa | Work Package 5
SL-SR-008 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 011-100-004-000 | Colusa | Work Package 5
SL-SR-009 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 011-100-004-000 | Colusa | Work Package 5
SL-SR-010 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 011-080-011-000 | Colusa | Work Package 5
SL-SR-011 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 011-080-011-000 | Colusa | Work Package 5
SL-SR-012 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 011-080-011-000 | Colusa | Work Package 5
SL-SR-013 | SR | Roads | along roadway | For design recommendations of cuts, fills and structural section. | Not Applicable | 011-080-011-000 | Colusa | Work Package 5
SL-SR-018 | SR | Borrow site | source area | For determining adequacy of material for causeway fill prism. | Not Applicable | 011-150-002-000 | Colusa | Work Package 5
SL-SR-019 | SR | Borrow site | source area | For determining adequacy of material for causeway fill prism. | Not Applicable | 011-150-002-000 | Colusa | Work Package 5
SL-SR-020 | SR | Borrow site | source area | For determining adequacy of material for causeway fill prism. | Not Applicable | 011-150-001-000 | Colusa | Work Package 5
SL-SR-021 | SR | Borrow site | source area | For determining adequacy of material for causeway fill prism. | Not Applicable | 011-150-001-000 | Colusa | Work Package 5
SL-SR-022 | SR | Borrow site | source area | For determining adequacy of material for causeway fill prism. | Not Applicable | 011-150-001-000 | Colusa | Work Package 5
SL-SR-023 | SR | Borrow site | source area | For determining adequacy of material for causeway fill prism. | Not Applicable | 011-150-006-000 | Colusa | Work Package 5
S-Mapping | Geologic Mapping | Fault Study | Sites Dam | Evaluate geologic hazards and geotechnical properties to support dam study, as well as PSHA and FDHA (build on existing Q mapping and bedrock stratigraphic markers). Established detailed structure, faulting, landsliding, and Q map | Not Applicable | 011-150-009-000 | Colusa | Work Package 5 | X
GGB-B-007 | Auger | Core Borrow | Golden Gate Dam Borrow | Explore core borrow quantity and properties. | Grout | 011-130-008-000 | Colusa | Work Package 5
GGB-TP-007 | TP | Core Borrow | Golden Gate Dam Z1 Borrow | Explore Core Borrow quantity and Properties | Backfill | 011-130-008-000 | Colusa | Work Package 5
SL-B-027 | RW-Core | Roads | Borrow site | For determining adequacy of material for causeway fill prism. | Grout | 011-130-008-000 | Colusa | Work Package 5
SL-B-028 | RW-Core | Roads | Borrow site | For determining adequacy of material for causeway fill prism. | Grout | 011-130-008-000 | Colusa | Work Package 5
SL-B-029 | RW-Core | Roads | Borrow site | For determining adequacy of material for causeway fill prism. | Grout | 011-130-008-000 | Colusa | Work Package 5
SL-SR-016 | SR | Borrow site | source area | For determining adequacy of material for causeway fill prism. | Not Applicable | 011-130-008-000 | Colusa | Work Package 5
SL-SR-017 | SR | Borrow site | source area | For determining adequacy of material for causeway fill prism. | Not Applicable | 011-130-008-000 | Colusa | Work Package 5
SL-SR-018 | SR | Borrow site | source area | For determining adequacy of material for causeway fill prism. | Not Applicable | 011-130-008-000 | Colusa | Work Package 5