NEPA Process/Requirements

Minutes

Agenda

| Date: | May 21, 2020 | Location: | Call In: 1-510-338-9438; Access code: 625 931 038 WebEx Link included in Outlook Invitation |
| --- | --- | --- | --- |
| Time: | 10:00 AM to 11:00 AM |  |  |

| Leader: | Sites Integration/ICF |  | Recorder: | Sites Integration |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Purpose: Assuming Federal Investment - Discuss Logistics of Preparing a Joint CEQA/NEPA Document |  |  |  |  |  |  |  |
| Attendees: |  |  |  |  |  |  |  |
| Monique Briard, ICF Ryan Davis, Reclamation Linda Fisher, Sites Integration |  | Russ Grimes, Reclamation Erin Heydinger, Sites Integration Nate Martin, Reclamation Ray Sahlberg, Reclamation |  |  | Laurie Warner Herson, Sites Integration Nicole Williams, ICF Natalie Wolder, Reclamation |  |  |
| Agenda: |  |  |  |  |  |  |  |
| Discussion Topic |  |  |  |  |  | Topic Leader | Time Allotted |
| - Introductions – Roll Call/Purpose of Meeting |  |  |  |  |  | Laurie | 5 min |
| - Prior Action Items - Authority to more fully describe federal role. - Authority Team will prepare a matrix to identify: the differences between the 2017 EIR/EIS, what will be proposed in the revised EIR/EIS, what is proposed in Reclamation’s feasibility report, and what will be proposed in the Authority’s feasibility report; and, the potential differences in the analysis/results between the 2017 EIR/EIS and the Revised EIR/EIS. - Authority to consider inclusion of an alternative in the EIR/EIS that is in Reclamation’s feasibility report once we have a draft of the revised feasibility report. |  |  |  |  |  | Laurie | 10 |
| - Status of Reclamation Feasibility Report |  |  |  |  |  | Ryan | 10 |
| - Assume Federal Investment, Need for EIS - Joint Document - Recirculated Revised Draft EIR/Supplemental Draft EIS - Document Format - Secretarial Order and page / time limits - Scope of NEPA document - 508 compliance - Reclamation review cycles (e.g., number/duration) for a Revised supplemental Draft EIS |  |  |  |  |  | Nicole/ Russ | 30 min |
| - Next Steps - Confirm Points of Contact for Technical Questions - Biweekly or Monthly Meetings? |  |  |  |  |  | All | 5 min |

Meeting Minutes:

Agenda Item 1

- Authority provided introduction and purpose of meeting – assuming federal investment and joint EIR/EIS, need to discuss the logistics of preparing the joint document

Agenda Item 2

- Discussed the ongoing status of action items from April 23, 2020 meeting:

  - Item a. is under review at the Authority Board level

  - ICF has initiated Item b. – completion pending refinement of value planning alternatives and review of Reclamation revised Feasibility Report

  - Item c. also pending final decision; however, the Authority may not choose to conduct analysis of Delevan pipeline/intake included in Feasibility Report

Agenda Item 3

- Reclamation provided an update on the status of the Feasibility Report

  - Reclamation to receive complete report for review week of 5/25

  - Will be sent to Policy June 8 for 1 month review

  - After commissioner and assistant Secretary review will go to OMB for 2-3 months

  - November/December 2020 determination

Agenda Item 4

- Discussed the ‘type’ of document – given new alternatives and because original alternatives will not be carried forward, Reclamation indicated that appropriate NEPA document would be a Revised EIS

  - New public review period (minimum 45-days)

  - No new NOI, just NOA when released

- Reclamation indicated that NODOS/Sites has been paused within Reclamation due to stalled process and when the project is taken off paused status will determine timing of the ROD

- Discussed page limitations – Reclamation will research existing waivers (see action item #4, below); however, even with waiver there will be a need to show a reasonable effort to reduce size and improve accessibility

- Discussed review periods – Reclamation indicated that with a July 2021 release, there should be sufficient time for their review process

  - Planning is typically in charge of the review process; Environmental supports the review process

  - Planning typically has a month of review time, but environmental generally has two weeks.

  - Reclamation will want to review the document at least twice.

    - technical staff from Planning and Environmental look at the document and make comments

    - after the comments from technical folks have been incorporated the document gets sent to the Front Office and solicitor

  - After the two types of review described above, there may be additional review; normally Regional Director/solicitor and comments should be addressed before going through the next level of review.

    - Reclamation may schedule review team briefing for Deputy Secretary

    - The document sent to the review team put together by the Deputy Secretary should be the document expected to post for the public Reclamation Environmental indicated at least 2 rounds of review

- ICF and Authority to revisit project schedule and work with Reclamation to develop revised  schedule that includes Reclamation process; also coordinate with Nate on other topics via email

- Reclamation confirmed 508 compliance; recommended keep figures simple so as to be able to describe figures; no formal criteria/guidance provided; ICF to review recent Reclamation document(s) to develop 508 compliant template.

Agenda Item 5

- Authority suggested setting regular meetings and discussed communication protocols with Reclamation

| Action items |  |  |
| --- | --- | --- |

| Action Item |  | Owner | Deadline | Notes |
| --- | --- | --- | --- | --- |
| 1 | Authority to more fully describe federal role | Authority | ongoing |  |
| 2 | Authority Team will prepare a matrix to identify: the differences between the 2017 EIR/EIS, what will be proposed in the revised EIR/EIS, what is proposed in Reclamation’s feasibility report, and what will be proposed in the Authority’s feasibility report; and, the potential differences in the analysis/results between the 2017 EIR/EIS and the Revised EIR/EIS. | Authority/ICF | ongoing |  |
| 3 | Authority to consider inclusion of an alternative in the EIR/EIS that is in Reclamation’s feasibility report once we have a draft of the revised feasibility report. | Authority | ongoing |  |
| 4 | Reclamation Environmental to look at existing waivers and provide summary to ICF/Authority as to the scope/content of waivers (e.g., schedule, pages/length, other) | Reclamation | 6/8 | ICF and Authority will follow up with Reclamation but need to confirm soon to develop annotated outline for the EIR/EIS |
| 5 | Authority and ICF to develop a project schedule that includes Reclamation review process, including checking with other recent projects and sources and will coordinate with Reclamation to confirm assumptions | Authority/ICF | 4 weeks | Follow up meeting with Reclamation management on 5/26 also included discussion of schedule for EIS and the Authority committed to have schedule for discussion at 6/23 meeting |
| 6 | ICF to follow up with additional questions regarding EIS format/requirements via email | ICF | 5/22 | Email sent 5/22 to confirm: - All standard topics related to NEPA will be included - NEPA guidance/modifications to climate change assessments and cumulative assessments not applicable since guidance hasn’t been approved yet - Reclamation will review the Indian Trust Asset database and provide the Authority the results. |
| 7 | ICF to review recent Reclamation document(s) to develop 508 compliant template. | ICF | ongoing |  |