NEPA Process/Requirements

Minutes

Agenda

| Date: | June 25, 2020 | Location: | WebEx Link included in Outlook Invitation Call In by Phone: 1-510-338-9438; Access code: 126 943 6823; Password: 76872769 |
| --- | --- | --- | --- |
| Time: | 10:00 AM to 11:00 AM |  |  |

| Leader: | Sites Integration/ICF |  | Recorder: | Sites Integration |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Purpose: Assuming Federal Investment - Discuss Logistics of Preparing a Joint CEQA/NEPA Document |  |  |  |  |  |  |  |
| Attendees: |  |  |  |  |  |  |  |
| Monique Briard, ICF Ryan Davis, Reclamation Linda Fisher, Sites Integration |  | Russ Grimes, Reclamation Erin Heydinger, Sites Integration Nate Martin, Reclamation |  |  | Laurie Warner Herson, Sites Integration Nicole Williams, ICF Natalie Wolder, Reclamation |  |  |
| Agenda: |  |  |  |  |  |  |  |
| Discussion Topic |  |  |  |  |  | Topic Leader | Time Allotted |
| - Introductions – Roll Call/Purpose of Meeting |  |  |  |  |  | Laurie | 2 min |
| - Prior Action Items - Authority to more fully describe federal role - Authority Team will prepare a comparison matrix of alternatives - Reclamation Environmental to look at existing waivers and provide summary to ICF/Authority as to the scope/content of waivers (e.g., schedule, pages/length, other) - Authority and ICF to develop a project schedule that includes Reclamation review process, including checking with other recent projects and sources and will coordinate with Reclamation to confirm assumptions - ICF to follow up with additional questions regarding EIS format/requirements via email - ICF to review recent Reclamation document(s) to develop 508 compliant template |  |  |  |  |  | Laurie | 5 min |
| - Status of Reclamation Feasibility Report |  |  |  |  |  | Ryan | 10 min |
| - Alternatives – Cross Walk Table |  |  |  |  |  | Laurie | 10 min |
| - Objectives/ Purpose and Need - Revised CEQA Objectives - NEPA Purpose and Need – update ? |  |  |  |  |  | Nicole | 10 min |
| - EIS Preparation - Waivers - scope/content - 508 compliance – schedule meeting with our technical specialists and the Reclamation contact |  |  |  |  |  | Nicole | 10 min |
| - Schedule - Reclamation Review Process/Steps - Sites Constraints due to California Water Commission Deadline |  |  |  |  |  | Linda | 10 min |
| - Next Steps |  |  |  |  |  | All | 3 min |

Meeting Minutes:

Agenda Item 1

- Authority provided introduction and purpose of meeting – continued discussion of joint EIR/EIS process under assumption that there is federal investment and joint EIR/EIS

Agenda Item 2

- Authority provided brief recap of action items with more detail to follow under other agenda items

Agenda Item 3

- Reclamation provided an update on the status of the Feasibility Report (FR)

  - FR in policy for review, primary concerns include:

    - Waiver required for environmental feasibility

    - Lack of detailed operations and water rights

Agenda Item 4

- Authority presented comparative cross walk table of alternatives, developed by ICF, illustrating differences between Authority’s Alternatives 1 and 2 and Alternatives A and D from the 2017 EIR/EIS. Discussed the primary differences including size of reservoirs, limited hydropower (no pump back storage), no Delevan Intake and release to Colusa Basin Drain and/or Sacramento River via new pipeline from the Tehema Colusa Canal near Dunnigan.

Agenda Item 5

- ICF provided an overview of proposed revisions to the CEQA project objectives

- Discussion of NEPA purpose and need and changes in the 2020 FR objectives to replace the water quality objective with:

  - CVP Operational Flexibility (OpFlex)

  - Delta Ecosystem Enhancement

- Follow up focused discussion of NEPA purpose and need to be included in next meeting

Agenda Item 6

- Discussion of the existing waivers

  - Reclamation clarified that there is a page limitation waiver from the required limit of 150 pages for an EIS to 300 pages for this project; these page limits do not apply to appendices and Reclamation suggested liberal use of appendices in presenting information

  - Time limit waiver – project is currently paused in Reclamation’s data base and time limits are suspended; current deadline for ROD is August 2021 but would be based on when project is reinitiated in Reclamation data base; suggested this be addressed closer to when the draft EIS is proposed to be released; however the project will need to be reinitiated in the database once Reclamation begins working in earnest on the document

Agenda Item 7

- Authority presented Sites EIR milestone schedule with Reclamation review process added

  - Need to meet California Water Commission deadlines requires release of Revised Draft EIR in July 2021; current schedule confirms ability to meet that w/ concurrent reviews

  - Preliminary comments from Reclamation indicate review timeframes are ok; removal of in-house briefing process – not an Authority task

  - Authority to update milestone schedule based on Reclamation preliminary comments and send out for more review and any further comments

Action Items

- ICF (Nicole) to coordinate with Reclamation (Nate) to set up meeting regarding 508 compliance

- Authority to forward schedule to Reclamation for comments